## Master Tracker
RoamReady — Master Bug/Todo Tracker (combined • Verified 06-02 against main)
Combines the original tracker (full item set + Type/Area/Source) with the 06-02 read-only CC audit verdicts. DONE/PARTIAL/OPEN reflect code-presence in current main. 'Eyeball/Device' = needs runtime/device check. Items with no audit coverage keep their pre-audit status.
ID | Priority | Item | Type / Area | Status | Verify next | Source | Notes / location & what remains
LB-1 | P0 | PDF lazy-loading (code-split out of main bundle) | Perf / Build | DONE | — | LAUNCH_STATUS #1 | Dynamic import @react-pdf/renderer; TripMapPage:1412 / TripSummaryPage:764. No static path into main bundle. Confirmed 06-02.
LB-2 | P0 | updateTrip footgun — schema allowed raw date writes | Bug / Schema | DONE | — | LAUNCH_STATUS #2 | startDate/endDate/totalNights absent from TripUpdateSchema; .strict() at trip.ts:65. Confirmed 06-02.
LB-3 | P0 | Modify-AI long-conversation tag-loss | Bug / AI | DONE | Runtime re-verify | LAUNCH_STATUS #3 / 05-23 | annotateAppliedModify ai.ts:449; tagless auto-retry 604-679; amber notice ModifyTripPanel:625. Highest-stakes AI path — confirm runtime.
LB-4 | P0 | Weather live forecast — forecast_days + .split() bug | Bug / Weather | DONE | — | LAUNCH_STATUS #4 | No .split('T')[0] in live branch; anchor fallback parseTripDate trips.ts:1935-1936. Confirmed 06-02.
LB-5 | P0 | Weather per-stop live→historical fallback | Bug / Weather | DONE | — | LAUNCH_STATUS #5 | LIVE_WINDOW_END_DAYS=15 trips.ts:1908; per-stop fitness vs liveWindowEnd + modeMatch. Confirmed 06-02.
LB-6 | P0 | aiConversation silent 400 — dead write + stale query | Bug / AI | DONE | Runtime re-verify | LAUNCH_STATUS #6 | Dead client write removed SessionPage:664-674; surprise-trip exclusion reads PlanningSession.messages ai.ts:560-586. Confirm runtime (user-visible if regressed).
LB-11 | P0 | UTC-midnight arrival timezone artifact | Bug / Weather | DONE | — | LAUNCH_STATUS #11 | parseTripDate dates.ts:67; used trip-anchor 1935 + per-stop 1973. Confirmed 06-02.
EV-1 | P1 | Email verification | Feature / Auth | DONE | — | memory / RR22 | WAS OPEN→now DONE. Fully enforced: requireVerifiedEmail middleware on ~10 route groups; controllers/services; VerifyEmailPage + Gate; migration 20260511. No longer a launch question.
TM-1 | P1 | Map route polyline doesn't recompute when AI adds stop | Bug / Trip Map | DONE | Eyeball (runtime) | recap 05-27 #1 | WAS OPEN→now DONE. Hot-swap onTripUpdated→setTrip TripMapPage:2302-2305; coords-keyed directions effect 903-905. Confirm via click-through.
AUDIT-1 | P1 | Systematic capture-vs-display field audit | Audit / Whole app | PARTIAL | Dedicated pass | recap 05-27 | Rate cluster narrowed (actualRate ?? siteRate consistent); locationName canonical. campgroundName/locationName clusters NOT certified. Needs the full walk-every-page pass — still real work.
TM-2 | P2 | Map popup shows estimated rate, not actual after booking | Bug / Trip Map | DONE | — | recap 05-27 #2 | WAS OPEN→now DONE. displayRate = actualRate ?? siteRate TripMapPage:227 (bdb4192 pattern).
TM-4 | P2 | 'Start trip' / ACTIVE status behavior | Scout / Trip Map | DONE | — | recap 05-27 #4 | CLARIFIED — cosmetic only. ACTIVE = schema enum + display badge (1769/1773) + dashboard grouping. No functional ACTIVE-only behavior; no Start-trip mutation. Nothing to fix.
TM-5 | P2 | Weather sub-tab non-interactive | Bug / Weather | DONE | Eyeball (runtime) | recap 05-27 #5 | WAS SCOUT→now DONE (wired). SidebarWeatherTab renders StopWeatherCard per stop from getWeather; forecasts shown inline (no click affordance by design). Confirm runtime.
IOS-1 | P2 | iOS Safari zoom-stuck bug | Bug / Mobile | CAN'T TELL | Device repro | memory / RR22 | Viewport meta correct (no maximum-scale/user-scalable=no); 16px inputs. No code-level signal of residual bug. Needs real-device reproduction. Affects core mobile users.
TM-3 | P3 | 'Book campgrounds' button hover state | Cosmetic / Trip Map | DONE | — | recap 05-27 #3 | WAS OPEN→now DONE. Hover variants both states: L1859 (all-booked) / L1867 (in-progress).
PW-1 | P3 | Dead feature-gates (rigCompatibilityFilter / aiPlannerUnlimited) | Cleanup / Paywall | PARTIAL | Decide wire/delete | recap 05-23 | SPLIT. aiPlannerUnlimited WIRED/enforced (ai.ts:26-37, trips.ts:63-67, 403→paywall). rigCompatibilityFilter still cosmetic — no requireFeature/hasAccess. Wire it or delete from both gate tables.
PW-2 | P3 | Extract TRIAL_DURATION_MS constant | Cleanup / Paywall | OPEN | — | recap 05-23 | STILL OPEN. 7*24*60*60*1000 duplicated at auth.ts:86 + passport.ts:38. No constant. Drift risk, not a bug.
PW-3 | P3 | Two parallel FEATURE_GATES tables (server+client) | Cleanup / Paywall | OPEN | — | recap 05-23 | STILL OPEN. Hand-synced tables middleware/auth.ts + store/authStore.ts. Extract a shared module. Drift risk, not a bug.
AI-1 | P4 | Meter AI for free/trial users (usage count + free limit) | Feature / AI | OPEN | — | recap 05-23 / memory | Confirmed by design: AI hard-gated via requireFeature('aiPlannerUnlimited'); hasAccess true only PRO/active trial. AIUsageLog = cost tracking only, no count gate. Best built against real usage data. Deferred.
OHV-CHECK | P4 | OHV link-checker — activation | Ops / OHV | DONE | Wire scheduler | this session / LS #17 | Three-state checker (OK/DEAD/REVIEW) BUILT+merged on main, commit b507861; cron emails on DEAD/REVIEW. DORMANT — not scheduled (external trigger unwired). To activate: wire monthly cron + smoke-test a known 404.
OHV-LAZY | P4 | Code-split OhvDestinationsPage with lazy() | Perf / OHV | OPEN | — | this session / LS #15 | STILL BACKLOG. App.tsx:48 static import; route L173 not lazy(). First-app-load only; per-visit load already fixed.
OHV-RETAIN | P4 | Client-side OHV result retention | Perf / OHV | OPEN | — | this session / LS #16 | STILL BACKLOG. No sessionStorage/store retention in OhvDestinationsPage.tsx. Cache last GPS+result for instant back-nav. Nice-to-have.
OHV-POC | P4 | OHV Destinations real data POC (directions/pass/fee) | Feature / OHV | OPEN | — | memory / RR21-22 | NOT in 06-02 audit scope. Page still only resource links (metadata was hardcoded). Recreation.gov scout was in progress. Build real data once scout evaluated.
OHV-TRIP | P4 | OHV add-to-trip | Feature / OHV | OPEN | — | memory / RR21-22 | NOT in 06-02 audit scope. Let users add an OHV destination into a trip. Deferred feature.
BOOK-WAVE | P4 | Full booking modal wave (conf #, site #, hookup, rate, etc.) | Feature / Booking | OPEN | — | memory | NOT in 06-02 audit scope. Larger booking feature set (gate code, notes, edit/cancel, conflict detection). Post-launch.

## Summary
Status roll-up (Verified 06-02)
Status | Count
DONE | 14
OPEN | 8
PARTIAL | 2
CAN'T TELL | 1
TOTAL | 25
Note: | 3 P4 items (OHV-POC, OHV-TRIP, BOOK-WAVE) carried over from original tracker were NOT in audit scope — status is pre-audit.