## Bug Tracker
RoamReady.ai - Bug Tracker
End of day: Thursday, June 11, 2026 (session ran into June 12). Maintained by Claude.
ID | Title / Symptom | Severity | Source | Status | Resolution | Key commits
AI-MODIFY-1 | Modify-with-AI showed '[checkmark] change already applied' x4 but only the first stop was applied to the itinerary (Cindy's Mesa-Niagara trip) | High | Prod user (Cindy) | Fixed - deployed | MESA-10 multi-action architecture: server is the single parse authority (actions[] in envelope), per-action applied state stamped server-side at execution, Apply-all sequential UI, model-emitted 'applied' claims stripped, legacy histories degrade to neutral text. Synthetic success bubbles removed. | 1a3e8b4, 5a9c740
MODIFY-UI-1 | Duplicate-stop guard error reported the wrong stop number (counted HOME departure) | Low | User test (Benny) | Fixed - deployed | Guard now numbers against the displayed (non-HOME) stop list; add-home duplicates say 'as your home stop'. | bc71580
FB-HONESTY-1 | Feedback modal showed 'Thanks for your feedback!' even when the request failed (seen live on prod with a 401) | High | Internal test | Fixed - deployed | try/catch with status-specific messages, visible error box, disabled 'Sending...' state; raw req.body replaced with strict Zod validation (FeedbackSubmitSchema) via validateBody; unvalidated PUT /feedback/:id/status removed in favor of PATCH /admin/feedback/:id. | c8df51f
FB-ZOD-1 | Strict feedback schema rejected valid minimal submissions - title/importance became required (Zod v4 preprocess/optional placement gotcha) | Medium | Internal test | Fixed - deployed | Outer .optional() added to preprocessed fields; 8-case safeParse verification; gotcha saved to project memory. | a6addbd
MIGRATE-EOL-1 | Prisma 'migration modified after applied' checksum failures, three incidents in one day (founder-rate migration); migrate dev offered destructive DB resets | High | Dev infrastructure | Fixed - deployed | Root cause: core.autocrlf=true rewriting applied migration SQL CRLF on checkout; pre-pin worktrees stayed poisoned. Fix: .gitattributes eol=lf pin, repo-local core.autocrlf=false, byte repairs across all trees, DB checksum corrections (zero data loss, no resets). Guards: scripts/check-migration-eol.js, npm run preflight, hard-abort check wired into save-progress.bat. | 4305e98, 2be0de4
AI-PACK-1 | Packing list AI generation silently persisted an EMPTY list (200 + ~0.9 kB) - max_tokens 4096 truncation broke JSON parse, code swallowed it as []. Live on prod; regenerate could silently wipe an existing list. | High | User test (Benny) | Fixed - push pending | max_tokens raised to 8192 with stop_reason detection and loud parse logging; controller 502s on empty/non-array generation and never overwrites the stored list; carry-over extracted to utils/packingMerge.ts with a 10-case regression check (npm run check:packing-merge). | 3851ca3
PACK-PERSIST-1 | Packing list checkmarks did not persist - checked state lived only in React state; regenerate also wiped all checks | High | User report (Benny) | Fixed - push pending | New PUT /trips/:id/packing-list (ownership-checked, strict Zod, 30x100 caps); optimistic toggle + 500ms debounced save with flush-on-unmount and visible failure banner + retry; regenerate carries checked state over by case-insensitive name match; per-item remove (x) for curation. | fd58085
PDF-GATE-1 | pdfExport: ['PRO'] feature-table rule was never enforced - free users could download trip PDFs (client-side render skipped the gate) | Medium (revenue) | CC audit | Fixed - push pending | All three PDF surfaces (trip summary, trip map, packing list) now call the gated exportPdf endpoint first; 403 opens the paywall via the central interceptor; one deletable line per surface if ever ungated. | 4ad4329
UI-GLYPH-1 | TripMapPage stop-row glyphs unintelligible: purple weather badge was a bare count; tent/bed/red-triangle/booking-dot had no labels | Low | User report (Benny) | Fixed - push pending | Badge replaced with a labeled pill (CloudRain + 'N weather alert(s)', brand purple, compact form on narrow widths) with detail tooltip; all four glyphs now have explanatory title tooltips. | 46ea101
UI-PALETTE-1 | Three off-palette purples (TripMapPage text-purple-600, TripPDF #7C3AED, SessionTipCard #8458B4) | Low | CC sweep | Fixed - push pending | All consolidated to the registered brand token purple.DEFAULT #7F77DD; every client purple now derives from one token. | a3444de
PACK-UI-1 | Redundant 'Generate with AI' + 'Generate packing list' buttons; regenerate had no confirm despite replacing the list | Low | User report (Benny) | Fixed - push pending | One action per state: empty state owns the CTA, header shows 'Regenerate with AI' only when a list exists, gated by a ConfirmModal that honestly warns removed items will return. | 3851ca3
UI-DOT-1 | Purple dots on the dashboard journal map questioned as possible bug | Low | User report (Benny) | Closed - by design | Per-trip marker colors on AllTripsMap (active trip = RV Blue, others cycle a deliberate 4-color ramp; gold ring = journal entry). Registered brand accent; no change made. | n/a
Summary
Total items | 12
Fixed - deployed | 5
Fixed - push pending | 6
Closed - by design | 1
High severity | 5
NOTE: 'push pending' items are merged to local main but NOT on prod. AI-PACK-1's bug IS live on prod - push is the first priority tomorrow.

## Features Shipped
Features shipped today
Feature | What it does | Status | Key commits
Feedback pipeline (core) | Validated submissions (strict Zod), honest error states, screenshot attachments (up to 3, client downscale, magic-byte + size checks server-side, route-scoped 25mb JSON limit), support notification email, submitter acknowledgment email, private-by-default (isPublic false + migration), admin PATCH endpoint. | Deployed | c8df51f, 5cda816, d436834-era
Feedback lifecycle emails + refs | [FB-XXXX] reference code in subject/body of all three system emails; automatic 'shipped' email on status transition (plain-language copy, BUG vs FEATURE variants, once-ever via shippedNotifiedAt stamp); 'Notified' badge in admin; silent declines by design. | Push pending | 2e2b977, dd5af5a, 0280989
Admin feedback workspace | Five filter tabs (Active default / Shipped / Declined / Archived / All) with count badges; reversible archive (archivedAt) that never touches public roadmap; submitter line with Find in Gmail (ref search) as the sole reply path; mailto removed. | Tabs deployed; Gmail/Reply changes push pending | d436834, 64771ed, 3500328
MESA-10 multi-action modify | Server-parsed actions[], per-action Apply cards with persisted applied state, Apply-all, deterministic strip of model 'applied' claims, state-aware model-bound history. Closes AI-MODIFY-1. | Deployed | 1a3e8b4, 5a9c740
Packing list system | Persistence (PUT + debounced saves), per-item remove, regenerate carry-over of checks, blank-checklist PDF export (PackingListPDF, TripPDF pattern), one-button-per-state UI with regenerate confirm, empty-generation 502 guard. | Push pending | fd58085, 3851ca3
PDF Pro gate | pdfExport enforced on all three PDF surfaces for the first time; paywall opens cleanly on 403. | Push pending | 4ad4329
Trip card lifecycle dates | 'Started <date> - Edited <relative>' bottom row on dashboard cards; 'Created <date>' on trip detail header. | Deployed | a6c6436
Plain-language customer copy | Shipped email rewritten without dev jargon (fixed/built/available, 'Happy travels' sign-off); public roadmap third column relabeled 'Completed'; Help page blurb aligned. | Push pending | 0280989, 98b791e

## Backlog & Open Items
Backlog and open items
Priority | Item | Notes
1 - First | Push pending batches (save-progress.bat) | Everything from packing persistence onward is local-only. AI-PACK-1's silent-empty bug IS live on prod (a user regenerate could wipe a list) - push before other work. Verify with: git log origin/main..main.
1 - First | Review CC's overnight report | Worktree cleanup (~40 stale .claude/worktrees + merged feature trees) and the one-time repo-wide EOL renormalize were assigned overnight. Confirm renormalize commit is clean (diff --ignore-cr-at-eol empty) and npm run preflight passes before pushing.
2 - High | Prod verifications after push | Packing generate on a meaty prod trip (the known truncation shape); packing check-and-return persistence; one shipped-flip to confirm the plain-language email sends from prod; paywall behavior on PDF buttons as a free user.
2 - High | Confirm Cindy's trip re-run | Her Mesa-Niagara itinerary should now have the honest return route (Toledo - Kansas City - Albuquerque - Mesa). Verify it happened post-MESA-10; re-run if not.
3 - Pre-launch | Render cold start mitigation | Prod request observed at 50.88s (service sleeping). Keep-alive ping or always-on tier before launch. Add to LAUNCH_STATUS.md.
3 - Pre-launch | LAUNCH_STATUS.md update | Record: feedback pipeline shipped, FROM_EMAIL display name set ('RoamReady <noreply@send.roamready.ai>'), PDF gate enforced, cold-start item.
4 - Polish | Packing generation progress UI | Generation honestly takes ~10-15s of AI authoring; show 'Building your list - about 15 seconds' instead of a bare spinner.
4 - Polish | Add-your-own packing item | PUT endpoint already supports it; small client addition (e.g. 'Cindy's medication', 'dog ramp').
4 - Polish | Roadmap-page feedback modal default type | Default Type to Feature Request when opened from the roadmap page; one-line tweak.
4 - Polish | Duplicate-card 'Try again' dead end | Deterministic rejections (duplicate stop) could offer Dismiss instead of a retry that can never succeed.
4 - Polish | Admin type filter | Old mixed status+type chips were replaced by status tabs; re-add a type dropdown inside tabs if bug-vs-feature filtering is missed.
5 - Someday | Declined-email revisit | Declines are silent by design today; machinery exists if an automated gentle 'no' is ever wanted.
5 - Someday | Packing PDF 'current progress' variant | Blank checklist is the shipped default; a packed-state printout is a small variant if users ask.