## Bug Tracker
RoamReady.ai - Bug Tracker
Updated June 18, 2026 (RR45). Open items at top by severity; fixed/closed hidden by default - use the Status filter to view. Only Severity is colored. VERIFY items are uncertain carry-overs - confirm on prod and close if resolved.
ID | Item | Severity | Status | Category | Notes | Key commits
BUG-DRIVECAP | Per-trip drive-time limit stated in chat not respected as an override; final summary quotes profile default (6h) when user said 5h in chat. | Low | Open - to fix | Bug | Profile max drive time is the default; a chat-stated limit overrides ONLY its leg/trip (either direction - shorter cap OR a deliberate long haul, which the chat must explicitly call out). Summary must quote the OPERATIVE number, never silently revert to profile default. NIGHTS-PROSE-1 family. | -
BUG-NIGHTS-PROSE | Model free-text narration can misstate the night count vs the (correct) card; also covers the drive-cap summary number. | Low | Open - polish | Bug | Card/badge always truthful; model prose can still drift. Feed derived totals + operative constraints into the model summary. | -
BUG-DEADCODE-ROUTESTRINGS | Dead code: generateRouteStringsAI (server/src/services/ai.ts) defined but never called - Google Directions (fetchAllSegmentRoutes) replaced it. Not imported anywhere. | Low | Open - cleanup | Tech debt | Confirmed dead during the LS-AI-USAGE-CAP cost scout. Safe to delete in a standalone post-launch chore commit; deliberately not bundled into launch work. | -
BUG-RESV-PASTDATE | Reservations tab buckets Upcoming vs Past with raw new Date(stop.arrivalDate) (ReservationsTabContent.tsx:77) while displaying via formatTripDate. UTC-midnight family (like fixed #11/#11b): in a negative-offset zone a stop labeled e.g. "Jul 10" can sort to Past a day early. | Low | Open - to fix | Bug | One-line fix: parseTripDate(stop.arrivalDate) at line 77. Negative-offset, day-of edge. Found by RR43 CAPTURE-AUDIT sweep. ALSO (separate, very low): resolvePackingCounts (packingMeta.ts:31-47) returns 0 adults when party is null, ignoring legacy TravelProfile.adults - legacy account w/ profile but no party could show "Made for 0 adults". self-person backfill makes it rare. | -
BUG-TM-POLYLINE | Map polyline stale on AI add-stop - when the AI adds a stop, the route line on the map may not refresh. Flagged P1 in an earlier session; status unconfirmed - may already be fixed. | High | Fixed - deployed | Bug | Fixed by composite Polyline key (commit 21b3f4c, May 28); also fixed sibling trash-delete stale-line bug. Reactive wiring re-confirmed June 10 audit. Verified working by Benny (RR43). Closed. | -
BUG-PLANNER-FIDELITY | Planner dropped previously-agreed stops on long trips and omitted legs past the headline destination (last-10-message window, no agreed-stops grounding). Confirmed on Cindy prod Mesa->Poulsbo. | High | Fixed - deployed | Bug | Persist agreed stop-set to partialTripData; re-inject as ground-truth every planning turn (survives HISTORY_CAP). Multi-destination directive added. Proven on prod with Austin 24-stop round-trip. | 3da0ac8, 6f84089
BUG-SESSION-INSPECTOR | No way to inspect a customer conversation + built trip without manual prod DB spelunking (Cindy diagnosis took ~1 hr). | High | Fixed - deployed | Bug | Admin-only read-only Session Inspector (/admin/session-inspector). Lookup by trip id or email (case-insensitive). Shows conversation, persisted stops, emitted-vs-built diff, AI usage tokens. Owner-gated; no schema. | 35ca9ec, 661dd9d
BUG-AI-MODIFY | Modify-with-AI claimed x4 applied but only first stop applied (Cindy). | High | Fixed - deployed | Bug | MESA-10 multi-action: server single parse authority, per-action applied state stamped server-side. | 1a3e8b4, 5a9c740
BUG-RT-STRIP | Round-trip return leg silently amputated; AI narrated an unbuilt stop. | High | Fixed - deployed | Bug | Root cause our own stripUnrequestedReturnLeg guard; return legs now persist for natural phrasing. | 79c97f6
BUG-SELF-PERSON | Account holder never counted as an adult; party undercounted. | High | Fixed - deployed | Bug | Self-person lazy auto-creation on default party. | 8e3dafd
BUG-SESS-HOOKS | SessionPage crashed in a loop after composer relayout. | High | Fixed - deployed | Bug | Rules-of-Hooks fix; hook cluster moved above early return. | 8944b56
BUG-FB-HONESTY | Feedback modal showed "Thanks!" even on failure (401). | High | Fixed - deployed | Bug | try/catch status messages, visible error box, strict Zod. | c8df51f
BUG-MIGRATE-EOL | Prisma checksum failures (CRLF rewrite of applied migrations). | High | Fixed - deployed | Bug | .gitattributes eol=lf, autocrlf=false, byte repairs, preflight guard. | 4305e98, 2be0de4
BUG-AI-PACK | Packing AI silently persisted an EMPTY list (truncation broke parse). | High | Fixed - deployed | Bug | max_tokens 8192 + stop_reason detection; 502 on empty, never overwrites. | 3851ca3
BUG-PACK-PERSIST | Packing checkmarks did not persist; regenerate wiped checks. | High | Fixed - deployed | Bug | PUT packing-list, optimistic+debounced save, carry-over by name. | fd58085
BUG-KBD | Mobile keyboard pushed chat input off-screen. | High | Fixed - deployed | Bug | visualViewport listener lifts input above keyboard. Confirmed closed this session. | -
BUG-MOBILE-PLACEHOLDER | Mobile placeholder truncation - chat input placeholder cut off on mobile. (Former launch-blocker.) | High | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-STOP-COUNT | Stop count accuracy - displayed stop count vs actual. (Former launch-blocker.) | High | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ITINERARY-BTN-FOLD | When the itinerary is built, the "View itinerary" button sits below the fold on mobile - user cannot see it without knowing to scroll, so they think nothing happened. | Medium | Fixed - deployed | Bug (mobile) | FIXED (mobile only, desktop untouched). Final approach after iteration: "View itinerary" is now a gold btn-primary button IN the mobile action-bar row next to PDF (wraps with Journal/Packing/Share/PDF) - so it is visible on load regardless of trip-detail height, the robust fix for ANY trip. Mobile map reverted to original 45vh. Earlier attempts (combined pin legend / 34vh shrink / full-width top strip) superseded. Desktop keeps its sidebar CTA unchanged. One CTA per breakpoint, no duplicates. Built + merged local main (c23d246/db14c62); VERIFY on prod after push on a content-heavy trip (Mesa-to-Maine). Confirmed pushed + live on prod (RR45 scout: git in sync with origin). | -
BUG-MAP-PDF | Itinerary PDF map shows only a Start (S) pin on round trips - Finish pin stacked at identical coords, so it reads as one-way on the printed map. | Medium | Fixed - deployed | Bug | Round-trip PDF map now collapses stacked Start/Finish pins into ONE combined marker: a hosted S/F teardrop icon (client/public/sf-pin.png, served from the app - no external dependency) on prod, auto-falling back to an orange "S" pin on localhost where Google cannot fetch the icon. Plus a PDF legend ("Start / Finish (round trip)" + "Stop"), gated on tripLoopsToOrigin so legend and pin always agree. One-way trips unchanged (separate green S/F pins). Aligned last-stop H/F to FINISH-ORIGIN-1 origin rule. Verified working on PROD by Benny (RR43). | -
BUG-PLANNER-CACHE | ~8k planner prompt re-sent uncached every turn - dominant input cost. | Medium | Fixed - deployed | Bug | Anthropic prompt caching on the static prefix; 5 interpolations moved to an uncached suffix. ~half input cost on long trips. | 3da0ac8, 6f84089
BUG-ORIGIN-FREETEXT | Origin in first message ("from mesa") ignored. | Medium | Fixed - deployed | Bug | Origin directive honors an origin already named in the message. | 16ed35a
BUG-SCOPE-META | Scope guard refused an app meta-question. | Medium | Fixed - deployed | Bug | IN-SCOPE carve-out for questions about RoamReady/the conversation. | d18e932
BUG-PDF-GATE | pdfExport PRO rule not enforced on all surfaces. | Medium | Fixed - deployed | Bug | All three PDF surfaces Pro-gated. | 4ad4329
BUG-STALE-SNAPSHOT | Regenerate gave no why/when; packing list silently stale. | Medium | Fixed - deployed | Bug | packingListMeta snapshot + made-for banner. | c315f06, 2260e58
BUG-PACK-SPEED | Packing generation ~60-65s. | Medium | Fixed - deployed | Bug | Prompt size cap ~120 items; single warm call. | 26fc6c2, 39b932d
BUG-FB-ZOD | Strict schema rejected valid minimal feedback. | Medium | Fixed - deployed | Bug | Outer .optional() on preprocessed fields. | a6addbd
BUG-PILL-CTA | Trip-summary pill CTA - booking pill call-to-action wording/behavior. (Former launch-blocker.) | Medium | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ROUNDTRIP-PROMPT | Round-trip vs one-way prompt handling. (Former launch-blocker; related to PLANNER-FIDELITY-1.) | Medium | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ADMIN-HDR-MOBILE | Admin page header + tab row do not wrap or scroll on mobile. The admin header info and the top tabs run off the right edge on a phone; you cannot scroll right to see them - must rotate to landscape to read it all. | Medium | Fixed - deployed | Bug (mobile) | Fixed RR45. Admin landing header packed title + 5 nav buttons into one non-wrapping flex row; on mobile they overflowed and were clipped by the global overflow-x:clip rule, forcing landscape. Mobile-scoped fix (AdminDashboardPage.tsx): outer header flex-col gap-3 sm:flex-row sm:items-center sm:justify-between (stacks title over buttons on mobile, side-by-side at sm+); button group flex-wrap gap-2. Desktop unchanged. No shared class or global CSS touched. | fix(admin): wrap landing-page header tabs on mobile (BUG-ADMIN-HDR-MOBILE) [4edc4ea]
BUG-CAPTURE-AUDIT | Capture-vs-display audit - recurring consistency check between what the app captures (stops, dates, counts) and what it shows. Flagged P1 in an earlier session; status unconfirmed. | Low | Closed - swept | Bug | Systematic capture-vs-display sweep run RR43 (read-only scout, hand-verified). Write and read agree across dates, counts, costs, status flags, field shapes. Two agent over-claims verified false. One straggler split to BUG-RESV-PASTDATE. Umbrella resolved. | -
BUG-INSPECTOR-LABELS | Inspector list had no headers; bare "COMPLETED" (conversation status) read as the trip status. | Low | Fixed - deployed | Bug | Column headers + relabeled "Conversation: ..." pill + legend + separate "Trip: ..." status pill. trip.status added to selects. | b136f7c, ca560ff
BUG-MODIFY-UI | Duplicate-stop guard reported the wrong stop number. | Low | Fixed - deployed | Bug | Numbers against the displayed (non-HOME) list. | bc71580
BUG-SESS-COMPOSER | Chat composer clipped at viewport bottom on mobile. | Low | Fixed - deployed | Bug | Flex layout replaced hardcoded viewport arithmetic. | bd8cc05
BUG-BUILD-DUPE | Build full itinerary twice could double-build. | Low | Fixed - deployed | Bug | Build made idempotent. | a8b4897
BUG-UI-DOT | Purple dots on dashboard journal map questioned. | Low | Closed - by design | Bug | Per-trip marker colors are intentional. | n/a
BUG-CHATPULSE-CLIP | Awaiting-reply input pulse glow was clipped at the bottom by the fixed bottom nav (nav z-40 opaque painted over the lower half of the glow; input sat flush with no bottom padding). | Low | Fixed - deployed | Bug (mobile) | Added pb-3 to the fixed chat-input wrapper (md:pb-0 desktop reset) so the full pulse ring renders in the gap above the nav. Part of the onboarding-cue work (Fixes 4+2 added the awaiting pulse + bottom-anchored layout; this fixed the glow clipping). Built+merged; verify on prod. Confirmed pushed + live on prod (RR45 scout: git in sync with origin). | -

## Features & Roadmap
RoamReady.ai - Features, Improvements & Roadmap
Updated June 18, 2026 (RR45). Open/planned items at top by severity; shipped hidden by default - use the Status filter to view. Only Severity is colored (yellow P2 / blue P3 / green Shipped).
ID | Item | Severity | Status | Category | Notes | Key commits
FR-DRIVECAP | Drive-cap override + summary number (DRIVECAP-OVERRIDE-1) | Low | Planned - P3 | Feature | See Bug Tracker. Profile default; chat overrides its leg; summary quotes operative number. | -
FR-MAP-PDF | Round-trip PDF map Start/Finish marker (MAP-PDF-STARTFINISH-1) | Low | Planned - P3 | Feature | Combined S/F marker on the PDF map for round trips. See Bug Tracker. | -
FR-NIGHTS-PROSE | Night-count prose mismatch (NIGHTS-PROSE-1) | Low | Planned - P3 | Feature | Feed derived totals into the model summary. | -
FR-FEEDBACK-DEFAULT | Roadmap-page feedback modal default type | Low | Planned - P3 | Feature | Default Type to Feature Request when opened from the roadmap page. | -
FR-DUPE-RETRY | Duplicate-card "Try again" dead end | Low | Planned - P3 | Feature | Deterministic rejections should offer Dismiss, not an impossible retry. | -
FR-PARTY-EMPTYSTATE | Travel Party "Add yourself" empty-state copy | Low | Planned - P3 | Feature | Self-person now auto-appears; empty-state wording slightly redundant. | -
FR-EV-FUEL | EV support + auto-MPG + estimate disclosures (EV-FUEL-1) | Low | Planned - P3 | Feature | EV + charging stations as a route-aware resource (NREL API). Auto-MPG by year/make/model from fueleconomy.gov (EPA). Liability disclosure on any auto MPG/range/cost estimate. | -
FR-DECLINE-EMAIL | Declined-email revisit | Low | Planned - P3 | Feature | Declines silent by design; machinery exists if an automated gentle no is wanted. | -
FR-PDF-ROADS | PDF map route follows real roads (match on-screen map) - optional future polish so the printed route curves along highways instead of straight lines between stops. | Low | Planned - P3 | Feature (polish) | Move from Bug Tracker to roadmap (RR43): NOT a bug - the straight-line PDF route is pre-existing and the map is functionally correct. This is an OPTIONAL future polish to make the PDF route follow real roads like the on-screen map. SCOUT FINDINGS (scenario b): road polyline is fetched client-side via the new Routes API and never persisted, so the server cannot reuse it. Two build options - (1) QUICK: in getTripMapImage make one whole-trip Directions call, emit path=enc:<overview_polyline>, keep straight-line as fallback; +1 Google Directions call per PDF render, within free credit; needs a ~8KB URL-length guard (long multi-stop trips can exceed the Static Maps URL cap and would fall back to straight lines). (2) BETTER (later): persist the encoded polyline at itinerary-generation time so the PDF just reads it - no per-PDF API call, but a bigger change. No schema change for option 1; option 2 needs a polyline field. Medium effort. Not launch-blocking. | -
FR-SAVED-PACKING | Reusable / saved packing lists | Medium | Shipped (dev) | Feature | v1 SHIPPED on dev + code pushed to prod (Render deployed); PROD MIGRATION HELD until cutover (see LS-PROD-MIGRATE-PACKING). v1 = save-as-template (Pro) + copy-from-previous-trip (free, MERGE). AI-seed-from-base deferred to v2. Additive PackingTemplate model; reuses mergePackedState + staleness snapshot unchanged. Tested on dev: 3-option chooser, save/start-from-template (Pro-gated), copy-from-previous (free) all working. Merge semantics = source becomes base, target custom items + checks preserved on top (same as Regenerate contract). NOTE on prod: feature CODE is live but save/start-from-template endpoints will 404 until the prod migration runs; copy-from-previous + generate work (no new table). | 09c00f3, d97e63b
FR-RIG-MISMATCH | Rig-mismatch detection + update prompt (RIG-MISMATCH-1) | Low | Deployed | Shipped | COMPLETE end-to-end (RR42). Detection: AI emits a <rig> tag capturing the user OWN stated rig - context-aware, excludes a friend/hypothetical rig (verified: "my friend has a fifth wheel but we are in our Class C" -> RV_CLASS_C). Banner: dismissable amber notice on the planning page when statedRig != profile rig, links to /profile/rig, states mileage/cost depend on rig. Calcs unchanged (run off profile rig). No false nag. | d37f48d, bed9065
FR-PLANNER-FIDELITY | Planner fidelity (agreed-stops grounding) | Low | Deployed | Shipped | Running agreed-stops list re-injected every planning turn; supports legs past the headline destination + return legs. | 3da0ac8, 6f84089
FR-PLANNER-CACHE | Planner prompt caching | Low | Deployed | Shipped | Static ~8k planner prefix cached; ~half input cost on long trips. | 3da0ac8, 6f84089
FR-SESSION-INSPECTOR | Admin Session Inspector | Low | Deployed | Shipped | Read-only owner-gated lookup of any customer conversation + built trip; emitted-vs-built diff; AI usage tokens. | 35ca9ec, 661dd9d, b136f7c
FR-FEEDBACK-PIPELINE | Feedback pipeline + admin workspace | Low | Deployed | Shipped | Validated submissions, honest error states, lifecycle emails w/ refs, 5 admin filter tabs. | c8df51f, d436834
FR-MESA-MODIFY | MESA-10 multi-action modify | Low | Deployed | Shipped | Server-parsed actions[], per-action Apply cards. | 1a3e8b4, 5a9c740
FR-PACKING-SYSTEM | Packing list system | Low | Deployed | Shipped | Persistence, per-item remove, regenerate carry-over, custom items, staleness banner, current-state PDF, speed cap. | fd58085, 3851ca3
FR-PDF-GATE | PDF Pro gate | Low | Deployed | Shipped | pdfExport enforced on all three PDF surfaces. | 4ad4329
FR-ROUNDTRIP-ORIGIN | Round-trip honesty + origin capture | Low | Deployed | Shipped | Return legs persist; origin captured from first message. | 79c97f6, 16ed35a
FR-SELF-PERSON | Self-person auto-creation | Low | Deployed | Shipped | Account holder counted in the party. | 8e3dafd
FR-RESOURCE-DISTANCE | Resource distance (Near me / Near my stop) | Low | Deployed | Shipped | Distance from GPS or a chosen stop. | cb77f46, 88ea738
FR-COLD-START | Cold-start mitigation (infra) | Low | Deployed | Shipped | roamready-api always-on Standard. | config
FR-ADMIN-USERLIST | Admin user list - all users (free + Pro) as sortable/filterable table with CSV export (ADMIN-USERLIST-1) | Medium | Shipped (prod) | Feature | Shipped RR45. Admin Subscribers page previously listed PRO users only (backend filtered subscriptionTier != FREE). Now shows ALL users. Backend (getSubscribers): removed the where filter. Frontend (AdminSubscribersPage) rebuilt as a spreadsheet-style table: columns Name / Email / Tier (PRO green, FREE muted gray badge) / Joined / Renews (em-dash for free); live search over name+email; tier filter All/Pro/Free; sortable column headers (caret, free sinks to bottom); Download CSV of currently-visible rows (plain JS Blob, roamready-users-YYYY-MM-DD.csv); header Users (N) - X Pro - Y Free. Owner-gated, read-only PII. Works dev + prod (same page, reads pointed DB). | feat(admin): all-users sortable/filterable table with CSV export (FR-ADMIN-USERLIST) [c2ef7fe]
FR-UX-SENIOR-INPUTS-1 | Senior-friendly chat inputs: voice-clear, non-slashed red mic, blue caret, home start-here pulse (iOS-safe rounded glow) | Medium | Shipped (prod) | Feature | Shipped RR45 (prod-verified on iPhone Safari). Four senior-friendly chat-input fixes: (1) voice input clears the box after send (stoppedRef guard in useVoiceInput.ts drops the trailing post-stop SpeechRecognition result that was re-filling the box); (2) recording mic is now a NON-slashed red Mic + red pulse (was lucide MicOff/slashed, which read as off/broken to non-technical users); (3) visible blue caret-[#1F6F8B] on chat textareas (hero+compact); (4) blue-gold start-here pulse added to the home/hero input, gated isAwaiting && !focused && !value.trim(), self-suppressing on focus/type. Pulse done iOS-safe: box-shadow-only glow on the rounded WRAPPER (new .hero-input-awaiting class) so it hugs the rounded box, + isolation:isolate on the mic button. IMPORTANT iOS NOTE: the voice mic is HIDDEN on dev over http:// (LAN IP/localhost) because iOS Safari disables the Web Speech API over insecure http - this is EXPECTED, not a bug. Desktop shows the mic over http; prod (https) shows it on phone. We are NOT using ngrok. Test voice logic on desktop dev; verify phone view on PROD https. Long detour this session: mic appeared to vanish after the first batch -> chased as a code regression (pulse-on-wrapper theory) -> full rollback to c2ef7fe -> root cause was the http/https environment, never the code -> reapplied all four, then fixed the hero glow to hug the rounded box. | feat(ux): senior-input batch [d24debe]; reapply [e7fadb3]; rounded glow [74e9f0f/bd44c91]
FR-RIG-ADD-SCROLL | Add-a-rig button scrolls the revealed form into view + focuses first field | Low | Shipped (prod) | Feature | Shipped RR45. The rig page Add-a-rig button toggled showForm to reveal an inline form but never scrolled to it - on a long page / mobile it looked like nothing happened. Fix (RigPage.tsx): useEffect keyed on showForm -> requestAnimationFrame -> formRef.scrollIntoView({behavior:smooth, block:start}) with scroll-mt-20 to clear the fixed header, then setFocus(vehicleType) so the cursor lands ready (focus delayed ~400ms so it does not cut the smooth scroll; instant + immediate focus under prefers-reduced-motion). Client-only, scoped to RigPage. Verify on prod after push. | fix(rigs): scroll Add a rig form into view [ae7276f / 6c1e70e]

## Launch Status
RoamReady.ai - Launch Status
Source of truth: LAUNCH_STATUS.md (repo root). Updated June 18, 2026 (RR45). Open blockers/gates/security at top by severity; done/deferred hidden by default - use the Status filter to view. Only Severity is colored. VERIFY/OPEN items need Benny to confirm or close.
ID | Item | Severity | Status | Category | Notes | Key commits
LS-BANK-ACCOUNT | Open a business bank account for Martini AI Media LLC. | High | OPEN - blocker | Launch gate / action | In progress - bank asked for a "business license." AZ has NO general business license, so this is loose wording. EIN is DONE (LS-EIN) - have it ready. NEXT ACTION: call the bank and ask the EXACT document needed (stamped Articles of Organization / EIN letter / Operating Agreement / TPT?). Likely set: EIN (have) + Articles + Operating Agreement (multi-member, you + Cindy). TPT only if SaaS taxable in AZ - confirm w/ tax pro. Unblocks Stripe. | -
LS-STRIPE | Stripe live flip - sandbox -> live payments. | High | OPEN - blocker | Launch gate | Sandbox -> live payments. Blocked on the business bank account (LS-BANK-ACCOUNT), which is blocked on EIN (LS-EIN). Launch chain: EIN -> bank account -> Stripe live flip -> DNS. THE true critical path. TPT/SaaS-tax question -> confirm w/ tax pro. | -
LS-DBPW-ROTATE | Prod DB password rotation - the production Postgres password was pasted into chat during RR27 diagnosis and flagged for rotation before launch. Still not rotated. | High | OPEN - security | Launch gate / security | Rotate the Render Postgres password before the Stripe live flip / public launch. Update DATABASE_URL in Render env. Plaintext-in-chat credential = real exposure once live + public. Pair with LS-STRIPE. | -
LS-PROD-TESTPASS | Full feature test pass on the LIVE Render site - plan a real trip on prod, hit the paywall, run a Stripe TEST payment, download a PDF, verify Modify-AI + AI planning in the real prod environment. | High | OPEN - gate | Launch gate / QA | The pre-launch regression check. Catches "worked in dev, broke in prod" before a customer does. Does NOT depend on the bank account - buildable now. Highest-value at-keyboard launch-prep task. | -
LS-DNS | DNS cutover - point roamready.ai at the app (apex A + www CNAME to Render; remove GoDaddy forwarding; protect Google Workspace MX/SPF/DKIM). | Medium | OPEN - gate | Launch gate | Deliberate LAST step, done right before launch. Not blocked externally; kept private behind onrender.com until payments live. | -
LS-S3 | AWS S3 credentials activation (wired, not active). | Medium | OPEN - gate | Launch gate | Needs credentials. | -
LS-PROD-MIGRATE | One-trip dev->prod migration - move a test trip from dev into the live DB to verify the migration path works end to end. | Medium | OPEN - gate | Launch gate | Needs a schema-dependency scout FIRST (Trip->stops->candidates/POIs/bookings/party, insertion order, unique-constraint collisions, non-trip-owned refs like Rig). Uses Render External DB URL. Not started. | -
LS-PROD-MIGRATE-PACKING | Run the add_packing_template migration on PROD (held since RR43). | Medium | OPEN - gate | Launch gate / migration | The PackingTemplate code is LIVE on prod but the migration is intentionally UNAPPLIED (guardrail: held until cutover). Until run, save-as-template / start-from-template 404 on prod (copy-from-previous + generate still work). RUN AT CUTOVER: from project ROOT, backend context, npx prisma migrate deploy (or migrate dev on a connected prod URL per your process) - confirm the preflight phantom tripwire is in place first so the JournalEntry.search phantom cannot apply. Migration file sha256 0b160b7f..., byte-identical to the dev-applied one. Do NOT forget at cutover. | -
LS-IOS-ZOOM | iOS Safari zoom-stuck bug | Low | PARTIAL | Post-launch | Mitigations shipped; exact repro elusive. | -
LS-DEPLOY-WEBHOOK | Render auto-deploy webhook flaky - auto-deploy missed pushes on 06-02. Workaround in use. | Low | OPEN - monitor | Infrastructure | Workaround: if no deploy within ~1 min of a push, use Manual Deploy -> Deploy latest commit. Check GitHub->Render webhook health. Logging so it is not just tribal knowledge. | -
LS-TRAVEL-PARTY-BC | Travel Party Phase B / C | Low | DEFERRED | Post-launch | Per-person accessibility, dormant fields. | -
LS-OHV-DATA | OHV/off-road destinations data source | Low | DEFERRED | Post-launch | Rec.gov/RIDB does not index most USFS/BLM OHV areas. | -
LS-OHV-LINK-CHECKER | OHV link-checker activation | Low | DEFERRED | Post-launch | Built+merged; needs migration + scheduler + smoke test. | -
LS-PRIOR-BLOCKERS | Prior launch-blocking set (PDF lazy-load, updateTrip schema, modify-AI tag-loss, weather live/historical, share trip, reservation honesty, travel party v1, +more) | High | DONE | Launch-blocking | All verified/deployed RR33-39. See Features tab + commit history. | -
LS-AI-USAGE-CAP | Per-user daily AI-call cap + owner alert - hard 200/day auto-cap and 100/day warning email across all 7 AI-spending endpoints. | High | DONE | Launch gate | Tier-agnostic (Pro/trial/owner all bounded). Warn email via feedbackNotification Resend client to support@roamready.ai, once/user/day. Route-cache paths gated post-cache. Client shows friendly "resets in X hours" message (also fixed the free-tier DAILY_LIMIT message). No schema change. Shipped + live June 17, 2026 (RR43). Closes the pre-launch uncapped-cost gap before the Stripe live flip. | -
LS-EIN | Confirm or obtain an EIN (federal tax ID) for Martini AI Media LLC. | Low | DONE | Launch gate / action | EIN obtained for Martini AI Media LLC. Confirmed by Benny. Have it ready to supply when opening the business bank account. | -
LS-COLD-START | Render cold-start mitigation | Low | RESOLVED | Infrastructure | roamready-api Standard always-on. | -
MAINT-FTS-PHANTOM | Permanent fix for the recurring migration drift (JournalEntry.search phantom). | High | DONE - RR43 | Infrastructure / maintenance | ROOT-CAUSED & FIXED this session (the recurring "erase database" drift, 7-8 prior incidents). Cause: Prisma v6 cannot model the GENERATED ALWAYS tsvector column JournalEntry.search, so every migrate dev re-proposes ALTER COLUMN "search" DROP DEFAULT, which Postgres rejects (42601). Was hand-patched each time; slipped through in RR43 and failed. PERMANENT FIX: new scripts/check-migration-phantom.js wired into npm run preflight - mechanically BLOCKS any migration containing that statement from being committed/applied (strips comments so documented precedent passes). Tested both ways. This class of failure can no longer silently recur. | -
MAINT-MIGRATION-REBASELINE | Squash migration history to a clean baseline (post-launch). | Medium | DEFERRED - post-launch | Infrastructure / maintenance | The durable cleanup beyond the RR43 tripwire: collapse the accumulated migration history (tombstones, hand-patched phantoms, checksum scars from 7-8 incidents) into one clean baseline so dev + prod agree from a known-good foundation. Do as its OWN dedicated session AROUND prod cutover, DB BACKUP FIRST, scout full migration state, squash, re-baseline dev then prod. Not urgent; the tripwire (MAINT-FTS-PHANTOM) stops the bleeding in the meantime. Natural to fold into the cutover since you sync dev->prod schema then anyway. | -