## Bug Tracker
RoamReady.ai — Bug Tracker
Updated RR51. Claude owns this file. Open items on top; completed (green) hidden — reveal via the Status filter.
ID | Title / Symptom | Severity | Source | Status | Resolution / Notes
BUG-MODIFY-INTENT-CONFUSION | “Create a stop in [city]” on an open trip is sometimes mistaken for new-trip planning; AI asks planning questions instead of adding the stop | P2 | User test (Benny) | Open | Prompt-clarity fix: modify AI should confidently treat “create/add a stop in X” as a modify action when a trip is open. Logged RR51, not built.
TZ-OFFBYONE | Off-by-one dates on weather day, journal edit prefill, reservations bucketing, admin session inspector | P2 | User test (Benny) | Done | Routed four surfaces through parseTripDate; weather day numeric. Pushed.
BUG-ROUNDTRIP-MODIFY-DROP | Round trip on an already-built trip via modify did not insert the return leg | P1 | Prod behavior | Done | buildModifyInstructions gained a round-trip action. Pushed.
BUG-ROUNDTRIP-PLANNING | Mid-planning “make it a round trip” didn’t rebuild; malformed <modify> tags leaked | P2 | User test (Benny) | Done | Planning re-emits full itinerary inline; stray tags scrubbed; strip regex broadened. Pushed.
BUG-AI-NODATE-ASK-B | recomputeStopDates fabricated + persisted today’s date for dateless trips (silent fake DB write) | P1 | CC audit | Done | Leaves stop dates null when no real anchor. Anchor path byte-identical. Pushed.
BUG-PDF-TOSTRING | Cindy’s PDF crashed on free-text times without a colon (“3pm”) | P1 | Prod user (Cindy) | Done | Finite-check fallback to raw string. DEPLOYED TO PROD (roamready-client).
STORED-NIGHTS-OFFBYONE | Stored Stop.nights one short for stays entered as “N days” via modify (9-day stay stored as 8) | P1 | User test (Benny) | Done | Root: modify prompt said days-minus-1 while planning said days=nights. Aligned both + added date-range rule. Pinecrest row corrected manually + backfill. Pushed. (Fresh-thread test pending.)
ITIN-NIGHTS-MISMATCH | Itinerary stay card showed 3 disagreeing numbers (badge 8 / span 8 / cost 9) for one stop | P1 | User test (Benny) | Done | Display-only fix: badge, date range, day-span all show true booked window (true nights, arrival→checkout). PDF matches. Pushed.
BUG-MODIFY-ADDSTOP-SEQUENCE | Stop added via modify landed in the wrong geographic position (Fort Stockton before Toyahvale) | P2 | User test (Benny) | Done | Server geocodes the new stop + re-slots only it by min-added-detour; origin/finish/booked pinned. Pushed.
BUG-PLAN-BUILD-DIVERGE (Part 1) | Built trip differed from approved plan: phantom transit stop + scrambled nights | P1 | User test (Benny) | Done | Part 1: removed expandLongLegs + reconcileNights from build chain; plan now flows to map verbatim. UNPUSHED. Part 2 (real check in planning) is RR52’s first task.

## Features & Roadmap
RoamReady.ai — Features & Roadmap
Updated RR51. Open/upcoming on top by priority; shipped (green) hidden — reveal via the Status filter.
ID | Feature | Priority | Status | Notes
PLAN-IS-TRUTH-PART2 | Real Google drive-time check DURING planning — transit stops appear in the approved plan + AI explains them honestly | P1 / Next | Next session | RR52 first task. 4 coordinated steps (extract planTransitInserts → call in chat() on itinerary change → grounded drive-time note → soften planner prompt). Then persist to agreed-stops + retire build-time controllers. Cost decision pending: run check only when stops change (rec) vs every turn.
FR-MARKETING-OPTIN | Marketing opt-in popup after signup | P2 | Queued | Captures explicit marketing consent (none exists today) — legal blocker gating win-back export under CAN-SPAM. Store consent flag+timestamp; wire to marketing email only. After Part 2.
FR-WINBACK | Cancelled-customer export for win-back | P3 | Deferred | Gated on FR-MARKETING-OPTIN (no opt-in basis today).
FR-TIME-INPUT-PICKER | Scrolling time picker (AM/PM) replacing free-text time field | P3 | Deferred | Root-cause cure for the PDF time crash. Standardized input.
FR-RIG-SPEC-AUTOFILL | Pick RV make/model/year → autofill specs | P3 | Deferred | Hybrid recommended: curated common-rig set + per-class defaults + manual override. No clean free RV spec DB exists; build curated, grow over time.
FR-ROUTE-HWYPREF-1 | Rig-aware “prefer major highways / 4-lane” routing preference | P3 | Deferred | Post-launch, low severity.
FR-SCOPE-HUMOR-1 | Scope-guard tone improvement with on-brand deflection | P3 | Deferred | A/B test before shipping.
FR-FEEDBACK-NOTIFY | 5th dev@ alert on feedback submission | P3 | Deferred | Scoped, not built.
JOURNAL-LOCATION | Optional place picker on freeform journal entries (pin stopless entries) | P3 | Deferred | Reuse AddressAutocomplete in AddEntryModal; columns exist from step 7; needs scout.
MOBILE-CHAT-INPUT | Chat input off-screen when keyboard opens (mobile) | P3 | Deferred | Pre-existing (baseline bf89b0a). Fix = visualViewport listener to lift input. Measure-first. Not pushed.
RIG-CHANGE | Full rig-change feature: trip-page selector + larger-rig warning + per-stop “booked for [rig]” + AI modify action | — | Shipped | All routed through one guarded swap path. Migration: 7 bookedForRig* cols. Dev-tested. Pushed, not yet deployed to prod.
STOP-GEO-RESLOT | Geo-reslot modify-added stops + booked-stop date-shift modal + originalBookedDate record | — | Shipped | Server geocode + min-detour reslot; center-screen modal; backfill done. Pushed.
STAY-CARD-TRUE-WINDOW | Itinerary stay card shows true booked window (nights + arrival→checkout); PDF matches | — | Shipped | Display-only (Option 1). Pushed.
NIGHTS-CONVERSION | Align modify days→nights with planning + explicit date-range rule | — | Shipped | Pushed. Fresh-thread test pending.

## Launch Status
RoamReady.ai — Launch Status
Snapshot of LAUNCH_STATUS.md (repo root = live source of truth). Updated RR51.
Item | Status | Category | Notes
Site live at roamready.ai | LIVE | Launch | Real Stripe payments, DNS cutover complete, Render deployed.
PDF time-crash fix | DEPLOYED | Prod fix | Live on roamready-client (Cindy’s PDF works).
RR51 batch (rig, stop-sequence, nights, stay-card) | PUSHED, NOT DEPLOYED | Deploy pending | On GitHub. Deploy needs BOTH roamready-api (server) and roamready-client (client). Deliberate step.
Plan-is-Truth Part 1 | LOCAL ONLY | Unpushed | Built + merged to local main; not pushed. Drive-time net OFF until Part 2.
Plan-is-Truth Part 2 | NOT STARTED | Next session | RR52 first task — see handoff doc.