## Tracker
ID | Item | Type | Area | Proposed Priority | Status | Verify vs current code? | Source | Notes / What remains
LB-1 | PDF lazy-loading — @react-pdf/renderer code-split out of main bundle | Perf | Build/Bundle | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #1 | react-pdf lands in own chunk, not index. Closed.
LB-2 | updateTrip footgun — schema permitted raw startDate/endDate/totalNights write | Bug | Trips/Schema | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #2 | Fields removed from TripUpdateSchema; .strict() rejects. Closed.
LB-3 | Modify-AI long-conversation tag-loss — model stops emitting <modify> tags | Bug | AI | P0 — Launch blocker | DONE (audit 05-28) | YES — highest stakes, re-verify | LAUNCH_STATUS.md #3 / recap 05-23 | Was flagged biggest launch risk. Fixed commit b3994ff 05-23 (annotate not strip + retry + amber notice). RE-VERIFY against current ai.ts before launch.
LB-4 | Weather Tab live forecast — forecast_days param + .split() date bug | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #4 | Three sub-fixes in weatherFetch.ts/trips.ts. Closed.
LB-5 | Weather per-stop live→historical fallback for late stops | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #5 | LIVE_WINDOW_END_DAYS=15 + per-stop fitness/modeMatch. Closed.
LB-6 | aiConversation silent 400 — dead client write + stale exclusion query | Bug | AI/Trips | P0 — Launch blocker | DONE (audit 05-28) | YES — AI path, re-verify | LAUNCH_STATUS.md #6 | Dead write removed; surprise-trip exclusion rewired to PlanningSession.messages. RE-VERIFY (AI path, user-visible if regressed).
LB-11 | UTC-midnight arrival timezone artifact in server weather path | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #11 | parseTripDate helper added server-side. Verified in 3 timezones. Closed.
TM-1 | Map route polyline does NOT recompute when AI adds a stop | Bug | Trip Map | P1 — High | OPEN | N/A — open | recap 05-27 #1 | Map draws stale route, visibly skips the new stop. Same 'stale-consumer' family. Scout-first: find polyline coord source + recompute trigger + why Modify-AI save path misses it. ~10-30 line fix.
TM-2 | Map popup shows estimated rate, not actual rate after booking | Bug | Trip Map | P2 — Medium | OPEN | N/A — open | recap 05-27 #2 | Popup reads siteRate w/o the actualRate ?? siteRate fallback wired on Booking page (commit bdb4192). ~5-10 lines in StopPopup. Bundle with TM-3.
TM-3 | 'Book campgrounds' button has no hover state | Bug | Trip Map | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-27 #3 | Cosmetic inconsistency. Add hover: variant matching other action buttons. Bundle with TM-2 as one polish commit.
TM-4 | What is 'Start trip' supposed to do? (product question) | Todo/Scout | Trip Map | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #4 | Flips status ACTIVE, unlocks Mark completed, shows dates. May not earn prominent slot. Scout: every trip.status read, ACTIVE-only behaviors, can status auto-detect from dates. Decide fix/retire/expand after.
TM-5 | Weather sub-tab is non-interactive | Bug/Todo | Trip Map / Weather | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #5 | Tab lists stops+dates but nothing clickable. Scout: scaffolded-but-unwired vs wired-but-no-affordance vs abandoned. Then finish / add affordance / remove tab.
AUDIT-1 | Systematic 'fields we capture vs fields we display' audit | Todo/Audit | Whole app | P1 — High | OPEN | N/A — open | recap 05-27 cross-cutting | Same stale-consumer bug shape hit 6x in 9 days. Own session. Walk every page, list field consumers, check each reads canonical source not stale/parallel field. Known clusters: siteRate/actualRate, campgroundName/candidates, locationName/lat-lng re-geocode, trip totals vs per-stop sums, AI-written fields user can override w/o recompute.
PW-1 | Two cosmetic dead feature-gates (rigCompatibilityFilter, aiPlannerUnlimited naming) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Wire to a route or delete from both FEATURE_GATES tables. Marginal.
PW-2 | Extract TRIAL_DURATION_MS constant (7-day literal duplicated) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | 7*24*60*60*1000 copy-pasted in 2 places. Drift risk, not a bug.
PW-3 | Two parallel FEATURE_GATES tables hand-synced (server + client) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Extract a shared module. Drift risk, not a bug.
AI-1 | Meter the AI for free/trial users (usage count + free limit) | Todo/Feature | AI | P4 — Post-launch | OPEN | N/A — open | recap 05-23 / memory | AI currently hard-gated (expired = no AI). Softer metered model is the fallback if hard gate hurts conversion. Best designed against real AIUsageLog data. Deferred.
EV-1 | Email verification | Todo/Feature | Auth | P1 — High | OPEN — confirm | Yes — confirm status & placement | memory / RR22 backlog | Previously flagged 'essential for real customers,' scoped & deferred. CONFIRM whether you still consider this launch-critical — it may belong at P0. Verify current state in code.
IOS-1 | iOS Safari zoom-stuck bug | Bug | Mobile/UI | P1 — High | DONE (06-02) | Verify on phone (fresh bundle) | memory / RR22 backlog + recap 06-02 evening | iOS Safari/Chrome auto-zoomed on input focus (text ballooned, Send pushed off-screen, never reset). Root cause took 3 passes: (1) a global input,textarea,select{font-size:16px} guard already existed in index.css but was DEAD — it sat in @layer components and lost to text-sm. (2) Moved it OUTSIDE @layer on the theory unlayered beats layered — did nothing, because Tailwind v3.4.19 FLATTENS @layer at build time (compiled CSS has zero native @layer), so the guard was just a (0,0,1) type selector losing to text-sm/.input (0,1,0) on plain specificity → stayed 14px → iOS zoomed. (3) FIX (commit b9f0225 -> merged 5dd984c): added !important to the coarse-pointer guard so it beats the utility classes regardless of specificity, still scoped to @media (pointer: coarse) so desktop keeps 14px. PROVEN in compiled bundle: @media (pointer: coarse){input,textarea,select{font-size:16px!important}}. Verified working on device. KEY LEARNING: under Tailwind v3, unlayered CSS does NOT beat utility classes (no native layers emitted); a global rule that must beat a utility needs !important or specificity >=(0,1,0). Also verify the COMPILED bundle, not just source.
OHV-POC | OHV Destinations real data POC (directions / pass / fee) | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Page still has no real functionality beyond resource links (metadata was hardcoded). Recreation.gov scout was in progress. Build real directions/pass/fee once scout evaluated.
OHV-TRIP | OHV add-to-trip | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Let users add an OHV destination into a trip. Deferred feature.
BOOK-WAVE | Full booking modal wave (confirmation #, site #, hookup, rate, gate code, notes, edit/cancel, conflict detection) | Todo/Feature | Booking | P4 — Post-launch | OPEN | N/A — open | memory | Larger booking feature set. Post-launch.
OHV-LAZY | Code-split OhvDestinationsPage with lazy() | Perf | OHV/Bundle | P4 — Post-launch | OPEN (logged #15) | N/A — logged | this session 06-02 / LAUNCH_STATUS #15 | First-app-load only; per-visit load already fixed (GPS maximumAge + coarse OHV cache key). Low priority.
OHV-RETAIN | Client-side OHV result retention for instant return-visits | Perf | OHV | P4 — Post-launch | OPEN (logged #16) | N/A — logged | this session 06-02 / LAUNCH_STATUS #16 | Cache last GPS + last result so back-nav is instant. Nice-to-have, not a bug.
OHV-CHECK | OHV link-checker — ACTIVATION | Todo/Ops | OHV | P4 — Post-launch | OPEN (logged #17) | N/A — logged | this session 06-02 / LAUNCH_STATUS #17 | Three-state checker BUILT+merged (OK/DEAD/REVIEW, WAF allowlist, emails on DEAD/REVIEW). To activate: (1) confirm OhvLinkCheck table migrated; (2) wire monthly cron like trial-end email cron; (3) smoke-test w/ a known 404. First run will email a REVIEW list — expected; tune allowlist.
PROD-1 | One-trip migration (dev DB → prod DB), re-pointed to prod user | Todo/Ops | Database/Deploy | P1 — High | OPEN | N/A — open | recap 06-02 | Move ONE specific trip from local dev to production, re-point to prod user. Schema-dependency scout FIRST (Trip→stops→candidates/POIs/bookings/party, insertion order, unique-constraint collisions, non-trip-owned refs like Rig). Uses Render External DB URL. PowerShell/psql gotchas apply. NOT started.
PROD-2 | Full feature test pass on live Render site | Todo/Test | Whole app | P1 — High | OPEN | N/A — open | recap 06-02 | Plan full trip on live site, hit paywall, run Stripe TEST payment, download PDF, verify Modify-AI (LB-3) and aiConversation (LB-6) in real prod env. First real-environment regression check.
PROD-3 | Point roamready.ai at the client (GoDaddy DNS → Render) | Todo/Ops | Deploy/DNS | P2 — Medium | OPEN | N/A — open | recap 06-02 | Phase 3. Domain owned at GoDaddy. Currently on onrender.com URLs. Update GoDaddy DNS to Render. Will affect CLIENT_URL, GOOGLE_CALLBACK_URL, Google Cloud authorized URIs once cut over.
PROD-4 | Wire AWS S3 (3 credential vars) — unblocks journal photo upload | Todo/Ops | Storage/Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Only AWS_REGION set in prod; 3 S3 credential vars omitted. Journal photo upload fails until wired. Known, non-blocking.
PROD-5 | Stripe live flip | Todo/Ops | Payments/Deploy | P4 — Post-launch | OPEN — deferred | N/A — open | recap 06-02 | Deferred until business bank account exists (LLC already exists). Then: activate Stripe (tax ID+bank+gov ID), recreate 4 founder price IDs in LIVE mode, stand up prod webhook, swap 6 env vars test→live. ~1hr contained session.
PROD-6 | Render auto-deploy webhook flaky — check GitHub webhook health | Bug/Ops | Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Auto-deploy missed pushes twice on 06-02. Workaround: Manual Deploy → Deploy latest commit if no deploy within ~1 min. Check GitHub→Render webhook health.
DISC-1 | Schema changes MUST go through migrate dev, NEVER db push | Discipline | Database | P1 — High | ACTIVE RULE | N/A — rule | recap 06-02 | LOAD-BEARING now that prod is live. stayActivities crash + OhvLinkCheck table were both db-push drift (in dev, absent in prod, no migration). Any uncommitted-migration schema change silently breaks prod and surfaces as a Sentry email.
HOME-MODAL | First-trip home-address capture (SaveHomeAddressModal) — opt-in to save trip start as home | Feature | Trips/Profile | P1 — High | DONE (06-02) | Verify in browser | recap 06-02 | SHIPPED client-only (modal + SessionPage wiring). Scout found the full home-address persistence layer already existed (User has all 8 home fields, profile edits them, AI pre-fills from them). Only gap was the opt-in modal at first trip. Fires when !user.homeLocation, saves only on active opt-in, per-trip override never overwrites saved home. Both builds green, merged. NOTE: currently saves city-only — see PROF-2.
PROF-1 | Profile home-address field renders empty despite populated DB data | Bug | Profile/UI | P2 — Medium | DONE (06-02) | Verify cold-load in browser | recap 06-02 | Stale-consumer bug (AUDIT-1 family). The visible address <input> was uncontrolled (defaultValue) + unregistered, so reset(user) hydration only fed the hidden registered fields (saves always worked, box stayed blank). Fix: controlled off watch(homeAddress), keeps input unregistered so Google Autocomplete keeps its ref. 1 file, +10/-1. Both builds green, merged. Confirmed only other defaultValue= hit (MembershipsPage:191) is NOT the same defect.
AI-MESA-1 | AI announces phantom home city for no-home users (Mesa → Roswell) | Bug | AI | P1 — High | DONE (06-02) | Verify w/ fresh no-home session | recap 06-02 | Two-part root cause, fixed across two commits. (1) Prompt had hardcoded real-city examples (Mesa, Austin/TX) in HOME-position; model borrowed them when [CITY] was unfillable. Fix: de-seeded all home-position examples to [HomeCity]/[HomeState] placeholders, preserved JSON structure (LB-3 modify prompt untouched + verified). (2) Deeper cause: userProfile drops undefined home keys via JSON.stringify, so model could not SEE home was empty and defaulted to the confident assert template. Fix: inject explicit noHomeDirective sentence in chatWithAI when !homeCity && !homeLocation (covers all 3 planning callers), + patched services/ai.ts:96 else-ask branch. When home exists, directive is empty string → momann path byte-identical (no regression). Prompt/service-only, no schema. VERIFY: fresh session, no-home user should ASK where starting from, not invent a city.
PROF-2 | SaveHomeAddressModal captures city-only, not a full structured address | Bug | Trips/Profile | P2 — Medium | OPEN — design done, build AM | N/A — open | recap 06-02 + mockup | Modal is a pure confirm dialog (no input); on opt-in SessionPage saves 3 city-level fields (homeLocation="Mesa, AZ", homeCity, homeState) and relies on getMe geocode backfill — which resolves the CITY CENTROID, not the real street address. Thin/half-useless home record. FIX (mockup approved 06-02): embed Google Places Autocomplete inside the modal, pre-seeded with trip start city; GATE "Save as my home address" so it only enables after a real place is SELECTED (populates all 8 fields); change modal contract onDone(bool) -> onDone(bool, address?{8 fields}); SessionPage sends full 8-field object to updateMe (server already accepts it). RECOMMENDED: extract shared client/src/components/ui/AddressAutocomplete.tsx (loader + Autocomplete + onPlaceChanged 8-field parser) — must NOT assume react-hook-form; returns parsed obj via onPlace callback. Ship modal on it first, migrate ProfilePage as follow-up. "Not now" = skip saving, city still used for planning (two clean paths, no muddy city-centroid middle). FIDDLY Google Places integration — do with fresh head (InfoWindow-saga lesson). Bundle near AUDIT-1.
AI-SURPRISE-1 | Surprise-trip rule misfires on named-destination trips (asks scope question) | Bug | AI | P1 — High | DONE (06-02) | Verify both paths in fresh session | recap 06-02 evening + scout | Planner asked a weekend/about-a-week/stay-regional-or-go-farther scope question for "Create me a trip from Fargo to Del Rio" — a fully-specified ~1,500mi cross-country trip. Root cause (scouted): that scripted question is STEP 1 of the Surprise-trip rule in services/ai.ts; model wrongly entered the surprise branch because the rule trigger has a loose model-judged catch-all ("any message indicating they want YOU to select where to go") and nothing hard-stopped it when a destination was already named. Scope question fires as FIRST response with NO distance precondition; the real distance reasoning (DRIVE-TIME CONSTRAINT) lives downstream in the build branch and never ran. FIX (prompt-only, +3/-1, commit 90be198 -> merged 6761fe6): prepended a PRECEDENCE guard to the top of the Surprise-trip rule — applies ONLY when no destination named; any "from X to Y"/"trip to Y"/"going to Y" pattern hard-disqualifies the surprise branch, routes straight to NAMED DESTINATION RULE. Catch-all trigger left intact so genuine "surprise me / you pick" still asks STEP 1. No server logic/schema/controller change. Server tsc green. VERIFY (restart backend + fresh browser session): (1) Fargo->Del Rio plans directly, NO scope question; (2) "surprise trip, you pick where" STILL asks the scope question (real surprise flow not broken).
MOBILE-CHAT-OVERFLOW | Chat bubbles could overflow horizontally on mobile (long tokens / no break-words) | Bug | Mobile/UI | P3 — Low | DONE (06-02) | Verify on phone | recap 06-02 evening (found while chasing IOS-1) | Found while debugging the IOS-1 zoom (initially mis-read as a horizontal page-shift). The in-session message bubble <p> (SessionPage.tsx) had whitespace-pre-wrap but no break-words, so a long unbreakable token (URL/long word) could overflow its max-w-[80%] box; overflow leaked through the message list (overflow-y-auto -> overflow-x:visible) into the overflow-hidden chat column. FIX (commit a92f1f9 -> merged 48e18b3, +2/-2): added break-words to the bubble <p> (source fix, wraps long tokens) + min-w-0 to the message-list flex container (guard, can never establish min-content wider than column). Avoided a blunt overflow-x:hidden (would clip tokens mid-word). NOTE: this was correct hygiene but NOT the cause of the reported zoom — that was IOS-1 (font-size). Client tsc && vite build green.
AUTH-RIG-1 | Home rig-context row blank on first login/signup until manual refresh | Bug | Auth/Profile | P1 — High | DONE (06-02) | Verify fresh Incognito login | recap 06-02 evening (found in prod-style fresh-login test) | On fresh login the Home screen (SessionPage empty-state) showed NO rig row (rig pill + "2 adults, pets" + hookup + "Planning for your ... — tap the rig to switch"); a manual browser refresh made it appear. Root cause (scouted end-to-end): the login AND signup endpoints return a SLIM user (no rigs, no travelProfile); the FULL user only comes from /users/me via authStore rehydrateUser(), which runs once on App boot — and on fresh login that boot effect already fired and no-opd BEFORE the token existed (it gates on token). So post-login the store held the slim user, Home never re-fetched, and the rig rows conditions were all falsy -> whole row hidden. Refresh works because App remounts with the token now present -> getMe -> setUser(full). Same stale-consumer FAMILY but the flavor is incomplete-data-shape-after-auth, not a re-render miss. FIX (client-only, 2 files +14/-2, commit 70cfc82 -> merged bddd626): await rehydrateUser() right after setToken+setUser in BOTH the login (LoginPage) and signup (SignupPage) success handlers, so the store holds the full /users/me user before navigating to Home. setToken runs first so the token gate passes; rehydrateUser swallows its own errors so a getMe hiccup never bounces the user to login (stays logged in w/ slim user = current behavior, not worse). NO server payload/schema change (deliberately chose client enrich over fattening the login endpoint — avoids an extra join on every login + Tier-1 schema churn). Mirrors AuthCallbackPage (OAuth) which already did getMe post-auth. Client tsc && vite build green. KEY LEARNING: slim-vs-full user payload shape at the auth boundary — any consumer reading rigs/travelProfile/parties straight off the post-login store will be empty until a refresh; enrich at the auth boundary, not per-consumer.
AUTH-RIG-1 | Home rig-context row blank on first login/signup until manual refresh | Bug | Auth/Profile | P1 — High | DONE (06-02) | Verify fresh Incognito login (no refresh) | recap 06-02 evening | On fresh login the Home screen (SessionPage empty-state) showed the greeting + trip box + in-progress trips but NOT the rig context row (rig pill, "2 adults, pets", hookup, "Planning for your <rig> — tap the rig to switch"); a manual browser refresh made it appear. Root cause (scouted end-to-end): the login AND signup endpoints return a SLIM user object (no rigs, no travelProfile); the FULL user only comes from /users/me via authStore rehydrateUser(), which runs once on App boot with empty deps — and on fresh login that boot effect already fired and no-opd BEFORE the token existed (rehydrateUser early-returns without a token). So post-login the store held the slim user, the Home screen never re-fetched, and every rig-row condition was falsy -> whole row hidden. Refresh "fixed" it because App remounts with the token now present -> getMe -> setUser(full). NOT a Zustand re-render issue (selectors re-render fine) — the full data simply never arrived post-auth. FIX (client-only, 2 files +14/-2, commit 70cfc82 -> merged bddd626): await rehydrateUser() after setToken/setUser in BOTH the login (LoginPage) and signup (SignupPage) success handlers, so the store holds rigs+travelProfile before navigating to Home. Chose client enrich over fattening the login payload (avoids touching Tier-1 auth endpoint + Zod schema + an extra DB join on every login). Safe: setToken runs first so rehydrateUsers token gate passes; rehydrateUser swallows its own errors so await never bounces the user to login on a getMe hiccup; no-rig users land cleanly (row stays hidden, no error). Mirrors AuthCallbackPage (OAuth) which already did getMe. Client tsc && vite build green. KEY LEARNING: slim-vs-full user payload shape at the auth boundary — any consumer reading rigs/travelProfile straight from the post-login store will be empty until a refresh; enrich at the auth boundary, not per-component.
HOME-MOBILE-1 | Home empty-state mobile polish: open-at-top, trips hint, placeholder clipping, post-login scroll race | Bug/Polish | Mobile/UI | P2 — Medium | DONE (06-02) | Verified on device | recap 06-02 evening | Four related Home empty-state (SessionPage) mobile issues, shipped across 3 commits. (1) OPEN-AT-TOP: app used BrowserRouter with no scroll reset, so navigating to Home carried the prior page scrollTop over -> greeting clipped. Fix: new global <ScrollToTop> (useLocation + useLayoutEffect window.scrollTo(0,0) on [pathname]) inside BrowserRouter above Routes (commit 433a1d9 -> ee13d2f). (2) TRIPS HINT: anchoring at top pushes in-progress trips below fold; added muted non-CTA cue at bottom of empty-state column gated on existing showContinueStrip, labeled with live planningTrips.length (commit 9f7b5cd -> 8a871d3). (3) CLIPPED PLACEHOLDER: ChatInput hero textarea rows=1 + fieldSizing:content sizes to empty VALUE not placeholder, so the 2-line placeholder clipped (worsened by the iOS 16px guard wrapping sooner). Fix: minHeight 3.5rem floor (kept fieldSizing/maxHeight so it still grows; no rows=2; copy unchanged) (commit 9f7b5cd). (4) POST-LOGIN SCROLL RACE: greeting still clipped on the post-login landing ONLY. Root cause: global ScrollToTop fires its one pathname-reset while SessionPage is still in its if(hydrating) SPINNER (short page, scroll trivially 0); a tick later hydrating clears, the tall empty-state mounts, browser scroll-anchoring bumps the greeting above the fold, and ScrollToTop never re-fires. From-Dashboard worked because warm data collapses spinner->content into ~the reset frame; post-login is COLD (awaited getMe + fresh-session POST + session fetch) so the gap is wide. NOTE: today AUTH-RIG-1 added an awaited rehydrateUser() to login, which WIDENED the cold path and is what exposed this race. Fix: SessionPage-local useLayoutEffect window.scrollTo(0,0) guarded on the hydrating->ready edge (dep [hydrating], !hydrating), re-applying the reset at the moment real content first paints; useLayoutEffect = before paint = no jump (commit eb61a4d -> 33a7748). Safe for active chat: window reset != the internal overflow-y-auto message-list scroll (bottomRef), different containers. All client tsc && vite build green. KEY LEARNING: a global pathname-keyed scroll reset MISSES content that mounts after an async hydrating gate; pages with a hydrating spinner need a LOCAL re-reset on the ready edge. Also: stale-bundle on the phone (restart Vite + hard-clear) masked test results repeatedly tonight — always confirm fresh bundle before judging a mobile fix.
SCROLL-BEHAVIOR-1 | Conversation over-scroll (top/controls clipped) + shared scroll-reset hook | Bug/Refactor | Mobile/UI | P2 — Medium | DONE (06-02) — Pattern-1 rollout PENDING | Verified short+long convo on device | recap 06-02 evening (app-wide scroll audit) | Reported: in the active conversation view, an AI reply scrolled the top of the page (incl. the New trip / Cancel this plan controls) off-screen even when the exchange already fit. App-wide scroll audit found this is a CLASS of bug with two patterns. PATTERN 2 (over-scroll on content change): SessionPage bottomRef.scrollIntoView (and ModifyTripPanel) used default block:start, which scrolls ALL scrollable ancestors incl. the window on mobile (dvh > visual viewport), carrying the non-sticky header off the top even when nothing needed scrolling. FIX (commit 32ad9df -> merged 8c2097d): block:nearest on both call sites — no-ops when the latest message is already visible (short exchange stays put) but still scrolls minimum to reveal the newest message in long convos (scroll-to-latest preserved). TripBookingPage scrollToStop left alone (intentional deep-link nav). PATTERN 1 (pre-scroll on arrival): the global ScrollToTop fires window.scrollTo(0,0) on [pathname] only, so it MISSES content that mounts after an async hydrating/loading gate (the cold post-login clip — see HOME-MOBILE-1). Audit found ~15 pages with a short-loader->tall-content gate that lack a local ready-edge reset (Dashboard, TripSummary, TripJournal, PackingList, SharedTrip, EditRig, TravelParty, OHV/Van/CarCamping/Roadmap/Maintenance, admin). Established the canonical fix: new hook client/src/hooks/useScrollResetOnReady.ts (useLayoutEffect(()=>{ if(ready) window.scrollTo(0,0) },[ready])); refactored SessionPage onto useScrollResetOnReady(!hydrating) — behavior-identical, no runtime change (commit 8e1fdd6 -> merged aaa75fe). Both client tsc && vite build green. PENDING (held deliberately, fresh-head pass): roll useScrollResetOnReady(!loading) out to the ~15 candidate pages — one line per page, mechanical, but deserves its own focused test sweep; mostly PREVENTIVE (not all candidates will reproduce — needs scroll-anchoring to inject above the fold). KEY LEARNING: a global pathname-keyed scroll reset misses post-hydration content; any page with a loading spinner before tall content needs a local ready-edge reset — now centralized in useScrollResetOnReady so it is not sprinkled/drifting.
DATE-ANCHOR-1 | Trips ignore user departure date; every itinerary anchors to today | Bug | AI/Trip pipeline | P1 — High | DONE (06-02) | Verified specific + vague-month in fresh session | recap 06-02 evening (gated audit + build) | SYSTEMIC: every trip anchored its itinerary to TODAY regardless of the date the user gave (confirmed across multiple users/trips incl. ones with explicit dates). Example: a September trip rendered Day 1 = Jun 4 (build day); season survived only in the trip NAME ("...Fall Adventure"). Root cause (gated scout, root cause (a) = never captured): the itinerary JSON schema the AI emits had NO date field, so a stated date had nowhere structured to land; promote wrote no Trip.startDate; server recomputeStopDates fell back through trip.startDate ?? firstDatedStop.arrivalDate ?? new Date() -> today, and back-filled startDate + every stop arrivalDate to today. The DISPLAY was innocent (correctly read the stored dates, which were today). KEY AUDIT FINDING: the whole server side was already wired right — PlanningSessionPromoteSchema already accepted startDate, promoteSession spreads ...data, recomputeStopDates anchors on startDate, and the map-page shiftDates picker already re-anchors all stops. The pipeline just never RECEIVED a date. FIX (gated 2-phase, +12 across 2 files, commit 5c400b7 -> merged 00b59d7): (1) services/ai.ts — added top-level startDate (ISO yyyy-mm-dd) to the itinerary JSON schema; added a DEPARTURE DATE RULE: specific date -> resolve+emit; vague month/season -> propose FIRST TUESDAY of that month (best midweek RV travel: lighter weekend traffic, easier campground availability) and ASK to confirm, emitting NO <itinerary> that turn (mirrors surprise-rule STEP 1 so the build does not trip early); no date -> omit. Also injected "Today is <ISO date>." into the system prompt so the AI resolves the correct YEAR (LLM date-guessing is unreliable — this was the gap that would have silently broken vague-month + specific-date year resolution). (2) SessionPage.tsx buildItinerary — added startDate: itinerary.startDate ?? null to the promote payload (the single client wiring line). No server/schema change needed; no backfill of existing trips (decided: leave them, fix new only); display ?? new Date() fallback left intact. Server tsc + client tsc/vite build green. DESIGN DECISIONS: vague month -> first Tuesday + confirm; editable post-build via existing map-page date picker; existing wrong-dated trips left as-is. KEY LEARNING: a feature can look like a 4-layer rebuild but be a capture-only gap — audit-first (gated) revealed the server was already ready and the real fix was 1 schema field + 1 prompt rule + 1 client line. Also: any AI feature that must reason about dates needs today injected into the prompt — never trust the model to know the current date/year.
AI-MESA-2 | Planner invents phantom origin city for no-home user on PROD ("...home address in Fargo") despite no-home directive being live | Bug | AI | P1 — High | DONE (06-04) — verified on PROD | Verified on live PROD, fresh session | recap 06-04 (gated DB+code scout) | REGRESSION introduced by AI-SURPRISE-1 (6761fe6). On PROD, no-home user momann sent "create me a trip to cincinnati" and the planner FIRST reply asserted "I will use your home address in Fargo as the starting point." Gated diagnosis ruled out: (a) stale deploy — backend roamready-api confirmed on 00b59d7, fix code live; (b) stored data — ALL momann home fields NULL on prod DB, no Fargo stored; (c) seeded history — session had exactly 2 messages, Fargo originated in the assistant reply only. ROOT CAUSE (code scout): chatWithAI correctly injects the noHomeDirective for null-home users (gate is correct), BUT the prompt ALSO contained the AI-SURPRISE-1 example "Create me a trip from Fargo to Del Rio" in the ORIGIN slot — structurally matching the user message. Classic instruction-vs-example conflict: the concrete origin-city example overrode the abstract "do not borrow a starting city" directive. AI-SURPRISE-1 had planted its own repro phrase as the canonical example a few hours after AI-MESA-1 de-seeded city examples, silently violating the de-seed invariant. FIX (prompt-only, +3/-3 in server/src/services/ai.ts, commit 84c105d -> merged 433ffb4): placeholder-ized ORIGIN-position cities in examples while preserving example SHAPE — line ~106 "from Fargo to Del Rio" -> "from [Origin] to [Destination]"; ~118 "leaving from Austin" -> "[Origin]"; ~174 San Jose/Austin/Denver/San Jose,CA->Miami -> [Origin]/[State]/[Destination]. Left untouched: noHomeDirective + gate (correct); destination-position cities (cannot be misborrowed as start; entangled with DATE-ANCHOR-1 JSON example); [HomeCity]/[HomeState]; LB-3 modify prompt; all schema. Client tsc+vite green; ai.ts zero tsc errors (server exit-1 was pre-existing redis.ts/prisma.ts TS2742 junction artifacts). VERIFIED ON PROD after redeploy + fresh session: no-home user now ASKS "Where will you be starting from?" and names no city; AI-SURPRISE-1 both guards still hold (genuine "you pick" still asks scope question; real named from-X-to-Y still plans directly). KEY LESSON: a later prompt fix that ADDS an example can silently violate a de-seed invariant set by an earlier fix. Any future CC prompt that adds/edits example text in ai.ts must end with a grep check that all ORIGIN-position cities are placeholders ([Origin]/[HomeCity]), never real city names.
FT-1 | Full-timer + skip-persistence feature (isFullTimeRVer + dismissedHomePrompt flags, HomeBaseCard mockup-B, Profile toggle, AI home-free ask) | Feature | Trips/Profile/AI | P1 — High | DONE (06-07) — leak re-fixed 06-09 | Verify on phone via tunnel | recap 06-07 | Handles 3 user kinds with no recurring nag: home-base / full-timer / skipped. Schema: 2 booleans on User (isFullTimeRVer, dismissedHomePrompt) @default(false); migration add_fulltimer_dismissed_flags applied to DEV DB (psql-confirmed), pure additive. updateMe whitelist + AI userProfile carry isFullTimeRVer. services/ai.ts directive split: full-timer w/ no captured origin gets a HOME-FREE ask (no home/save wording); no-home non-full-timer keeps existing ask. HomeBaseCard rebuilt to segmented toggle (Save home base / Done); Skip persists dismissedHomePrompt + one-time "add in Profile" line (gate-flip deferred ~2.2s so line shows). Gate: isEmptyState && !homeLocation && !isFullTimeRVer && !dismissedHomePrompt && !homeCardDismissed. Profile toggle w/ mutual exclusivity (check full-timer clears+disables address; pick address unchecks full-timer). Both builds green, pushed. ¦¦ 06-09: a full-timer home-address NAG resurfaced during trip creation. Two fixes this session: (e776b3d) broadened origin extraction to catch 'to Y from X' word order + lowercase origins; (f2bb1ce) gated the save-address template on !isFullTimeRVer in the PROMPT BODY (not just the injected directive) so it cannot leak. NOTE: the 'regression' was actually a STALE BACKEND (dev server running pre-fix code) — restart + fresh session clears it. AI-path: restart backend, test in NEW session.
PROF-3 | Profile full-timer save flashes & does not persist (empty-string into Float? column + silent catch-less failure) | Bug | Profile | P1 — High | DONE (06-07) | Verified save sticks + reload | recap 06-07 | With a saved address, checking "I am a full-time RVer" + Save just flashed, no persist. Root cause (scouted): mutual-exclusivity clear wrote into homeLat/homeLng (Float? cols) -> Prisma rejects ->Float -> whole updateMe throws ATOMICALLY -> isFullTimeRVer never commits; AND onSubmit had try/finally with NO catch -> silent flash. FIX (client-only): clear all 8 home fields to null (not ); added catch + visible red "Could not save changes" error state. Confirmed sticks + survives reload. KEY LEARNING: clear nullable numeric cols to null not ; a catch-less try/finally hides real errors as a no-op flash.
MODAL-RM | Remove redundant post-build SaveHomeAddressModal ("save trip start as home" popup) | Cleanup | Trips | P2 — Medium | DONE (06-07) | Verify build->map, no popup | recap 06-07 | Closes HOME-MODAL (which shipped 06-02) as now-redundant given the home-base card + full-timer flag + deterministic origin capture. Scout confirmed the itinerary build does NOT depend on the modal (it only gated navigation; build/generate already fire before it). Fully removed: import, saveHomePrompt/savingHome state, the trigger block (collapsed to unconditional navigate(.../map)), handleSaveHomeDone, render, and component file (git rm). CC cleaned newly-orphaned imports (usersApi removed, setUser destructure narrowed to user, HomeAddress import removed) — tsc --noUnusedLocals would have failed otherwise. Client build green, pushed. Two harmless stale doc-comments left (types/index.ts startAddress, HomeBaseCard:13). Supersedes PROF-2 (the city-only modal upgrade) — modal is gone, so PROF-2 is MOOT.
MOBILE-CHAT-HDR | Mobile chat header + top of first reply cut off after sending first message (window over-scroll from keyboard lift across empty->active layout swap) | Bug | Mobile/UI | P1 — High | DONE (06-09) | YES — finish via diagnostic capture, then push | recap 06-07 | NOT PUSHED — all uncommitted in working tree (clean revert point). Symptom: after sending the FIRST message, header ("New trip/Cancel this plan" + "Last edited") + top of reply ride off above the viewport. MEASURED (temporary on-screen overlay) the real cause: WINDOW scroll of 110px (scrollY=110, docH 872 > innerH 762, vvTop=0, keyboard closed). dvh wrapper makes the document taller than the visual viewport; tapping the empty-state hero input lifts the keyboard and scrolls the window down; on send the layout swaps but window.scrollY is never reset. FOUR REAL FIXES IN TREE (keep): (1) message-list scroll containment (listRef.scrollTop guarded on overflow, replaces scrollIntoView so it never scrolls the window); (2) scroll-reset useLayoutEffect (prevEmptyRef true->false edge -> scrollTo(0,0)); (3) body-scroll-LOCK useLayoutEffect (overflow:hidden in conversation view, cleanup restores); (4) sticky header (sticky top-0 z-10 bg-white). dvh height (:844) deliberately NOT changed. Both crash dead-ends fixed: hooks placed ABOVE early returns (was "Rendered more hooks than during previous render" — first early return is if(hydrationError) ~:788). Body-lock got it to scrollY=0 / fully visible in one test. REMAINING EDGE CASE: after stripping the diagnostic, a transition-timing case (during the typing-indicator / first paint of the active layout) still clips and does NOT snap back. NEXT (fresh head): restore the diagnostic, capture numbers AT THE BROKEN MOMENT (during typing, not after settle), then ONE measured fix (apply lock/scrollTo earlier on the isEmptyState flip, possibly in the send handler before the swap; dvh-height rework is last resort). KEY LEARNING: MEASURE before fixing — 6 rounds on theory, solved instantly once instrumented. ¦¦ 06-09: RESOLVED structurally. The off-screen-input bug was confirmed PRE-EXISTING (git: present at baseline bf89b0a; zero visualViewport handling ever). Root cause: mobile wrapper had min-height not definite height -> list never bounded -> input rode off-screen. FIX (mobile-only, desktop untouched): frozen header fixed top-0 / md:sticky + shell pt-[3.75rem] (d815916); pinned input fixed above nav + wrapper min-h->h definite (e534fda); messages rest-at-bottom via inner flex justify-end (2829b28). Earlier rest-at-bottom-via-scroll attempt (bae95cc) pushed input off-screen and was REVERTED (e15875f). Diagnostics removed. No visualViewport needed (measured occlusion negative/visible). NOT PUSHED yet at recap time.
DISC-2 | Diagnostic-overlay-first when a UI cause is unknown after >1 failed fix | Discipline | Whole app / UI | P1 — High | ACTIVE RULE | N/A — rule | recap 06-07 | New working rule from the mobile-chat saga. When a layout/scroll/render bug survives a couple of theory-based fixes, STOP guessing — add a temporary on-screen diagnostic overlay (fixed-position, prints live values like scrollY/innerH/docH/visualViewport/element rect.top), reproduce, read REAL numbers at the BROKEN moment, then make exactly one measured fix. Strip the diagnostic after. Mirrors DISC-1 in spirit: instrument-and-measure beats repeated blind edits.
NGROK-1 | ngrok HTTPS tunnel for real-device phone testing of DEV | Ops/Tooling | Dev/Tooling | P2 — Medium | DONE (06-07) — working | N/A — setup | recap 06-07 | Phone could not log in to dev (OAuth callback redirected to localhost = ERR_CONNECTION_FAILED; mobile browsers also refuse session storage over plain http on a LAN IP). FIX = HTTPS tunnel. ngrok installed via DIRECT .exe download to C:\Users\aylie (npm install was broken/silent — Windows flakiness); run as .\ngrok.exe. Free STATIC domain handling-jackal-omit.ngrok-free.dev (registered once, stable). Google Cloud (roamready-493621) OAuth client: added redirect URI https://handling-jackal-omit.ngrok-free.dev/api/v1/auth/google/callback AND JS origin https://handling-jackal-omit.ngrok-free.dev (origins field = domain only, no path). Dev .env (DEV-ONLY, do NOT push): GOOGLE_CALLBACK_URL + CLIENT_URL -> tunnel; vite.config.ts allowedHosts:[tunnel] (kept host:true + /api proxy). No server code changed. Run: .\ngrok.exe http --domain=handling-jackal-omit.ngrok-free.dev 3000 (own window). Phone: run backend+Vite+ngrok, load the https tunnel URL, click thru one-time interstitial — OAuth + email/password both work, sessions stick. NOTE: desktop OAuth now also wants the tunnel URL (dev .env points there). Free static domain = no re-register between sessions.
OAUTH-LAN | Host-adaptive dev OAuth over raw LAN IP (no tunnel) — scoped, NOT built | Todo/Ops | Auth/Deploy | P3 — Low | OPEN — scoped, deferred (tunnel made it unnecessary) | N/A — scoped | recap 06-07 | Fully scoped but NOT built. Would make dev OAuth work from BOTH localhost and the LAN IP without a tunnel by deriving callbackURL + final-redirect host from x-forwarded-host WHEN NODE_ENV!=="production", keeping GOOGLE_CALLBACK_URL/CLIENT_URL authoritative in PROD (prod callback arrives via Render rewrite, so x-forwarded-host is the API host there — must NOT derive). Also needs LAN origin allowed in dev CORS + the LAN-IP redirect URIs registered in Google Cloud. Superseded for now by NGROK-1 (cleaner, also fixes the mobile insecure-http session problem the LAN-IP fix would NOT). Keep only if you want tunnel-free phone testing.
ONBOARD-HOME | Capture home base + full-timer in the /onboarding flow, then suppress HomeBaseCard for onboarded users | Todo/Feature | Onboarding/Trips | P2 — Medium | OPEN — scoped idea | N/A — scout | recap 06-07 | Your idea, flagged as the better capture point than the post-load card. Add home address + a "full-time RVer" option as a step in /onboarding (Vehicle->Rig->Style->...->Done). Once captured there, the HomeBaseCard becomes FALLBACK-ONLY (already naturally suppressed by its gate: !homeLocation && !isFullTimeRVer && !dismissedHomePrompt). Its own scoped build with a scout — adds a step/fields to the onboarding flow. Not started.
WMK-1 | Recreate RoamReady.ai watermark/wordmark as a clean SVG (current looks washed-out/pixelated) | Todo/Design | Branding/UI | P3 — Low | OPEN — scout drafted, not run | N/A — scout | recap 06-07 | Watermark looks washed-out/pixelated like a raster scaled up. RECOMMENDED: rebuild as an SVG WORDMARK (vector, razor-sharp at any size, tiny) and use it at low opacity for the watermark — one source, two uses, never blurry. The image scout (find roamready*.png/svg assets in client/public + client/src/assets, the header sunset/road icon, exact brand hexes RV Blue #1F6F8B / Sunset Gold #F7A829 / D1 gradient) was DRAFTED but never run (CC ran the OAuth scout instead). CAVEAT: text wordmark is straightforward to rebuild; the sunset/road ICON is hard to match exactly unless an existing SVG of it is found.
TEST-ACCTS | Recreate special-state dev test accounts (wiped by the 06-07 DB reset) | Todo/Ops | Dev/Data | P3 — Low | OPEN | N/A — as needed | recap 06-07 | The dev DB reset wiped all test accounts: momann@gmail.com (owner isOwner=true paywall bypass, 2021 Thor Magnitude BH35), momannexpired (expired Pro trial for paywall testing), Cindy@roamready.ai (Free trial), bmolini (verified-inbox), hometest (null-home). Tables intact, rows gone. PROD untouched. For full-timer testing a plain no-home signup suffices; the owner-bypass + expired-trial states need manual recreation (set flags in DB) when those paths need testing again.
JBANNER-1 | Journal banner States/Trips toggle + shared AllTripsMap extraction | Feature | Journal/Maps | P2 — Medium | DONE (06-09) | Verify on device | recap 06-09 | Added a States¦Trips segmented toggle to the Journal banner — flips one fixed-size box between the states choropleth and an inline all-trips map. Extracted shared AllTripsMap component (5abdaf2); JournalMapPage now a thin wrapper; TripMapPage untouched. AllTripsMap is React.lazy + only mounts in Trips mode (States-only users load NO Google Maps bundle). Commits: 5abdaf2 extract, c9aa405 toggle, 8cde9f9 fixed-size box, a846dd9 header rename 'States visited & trips taken' + removed redundant journal pins from states map, 6c2ff05 banner Trips map self-sufficient (own dropdown+routes toggle, 'View full map' link removed). NOT PUSHED at recap.
AI-ORIGIN-1 | Trip-creation origin extraction missed reversed word order + lowercase origins | Bug | AI | P1 — High | DONE (06-09) | Verify in NEW session after backend restart | recap 06-09 | User typed 'Create a trip to New Orleans from san jose' -> AI ignored 'from san jose' (asked for origin anyway) AND nagged about home address. Root cause: extractFromXtoY (controllers/ai.ts) only matched 'from X to Y' with UPPERCASE origin -> capturedOrigin null -> fell through to ask+home-nag. FIX (e776b3d): broadened to both word orders ('from X to Y' AND 'to Y from X') + lowercase origins (normalizeOriginCase), with conservative STOP-word guards (rejects 'from bad to worse', 'from work', 'from dawn to dusk' via proper-noun-signal requirement). Tested: captures correctly, idioms reject. AI-path: restart backend + new session.
AI-FT-LEAK-1 | Full-timer home-address save template leaked despite suppression directive | Bug | AI | P1 — High | DONE (06-09) | Verify in NEW session after backend restart | recap 06-09 | Full-timer (isFullTimeRVer=true, no home) still got 'I don't have a home address saved... I'll help you save it'. DB confirmed flag stored true, so the AI received it — but the no-home save-address TEMPLATE was physically present in the prompt body, so the model grabbed it despite the full-timer directive. FIX (f2bb1ce): gated the save-address template on !isFullTimeRVer in the prompt body itself (not just the injected directive). Same family as AI-MESA-1/AI-MESA-2 (instruction-vs-example/template leak). The 'reappearance' on 06-09 was a STALE BACKEND, not a real regression. AI-path gate applies.
VEH-PICKER-1 | Mobile vehicle-confirmation modal buried under itinerary bottom sheet | Bug | Mobile/UI | P2 — Medium | DONE (06-09) | Verified on phone | recap 06-09 | On phone, tapping 'Build full itinerary' opened ConfirmVehiclesModal (z-50) but left the itinerary BottomSheet (z-81) open on top, covering the vehicle picker. Root cause: onBuildItineraryClick called setConfirmVehiclesOpen(true) WITHOUT setSheetOpen(false). FIX (bf89b0a): added setSheetOpen(false) after the guard so the sheet closes when building starts — sequencing, NOT z-index (scout confirmed z-index bump = wrong, leaves two stacked overlays). Mobile-only (desktop Build is in-flow sidebar). Confirmed working.
CHAT-DEADSPACE-1 | Mobile chat dead-space (triple bottom-nav reservation) + height-chain | Bug | Mobile/UI | P2 — Medium | DONE (06-09) | Verified via on-screen diagnostic | recap 06-09 | Measured (DIAG overlay): bottom-nav clearance reserved ~3x (main pb-32 128px + wrapper -8rem 128px + input +4rem ~64px) for a ~56px nav -> dead space + a 422px page-scroll on keyboard focus. FIX (06e9592): reconciled to ONE reservation (wrapper min-h-full, input pb trimmed) -> killed the 422px keyboard page-scroll. Then height-chain fix (6291f67 -> later 13.25rem in d815916): gave the wrapper a definite height so it fills <main> (Delta/GAP became constant regardless of conversation length). Part of the broader MOBILE-CHAT-HDR resolution. Measure-first discipline (DISC-2). NOT PUSHED at recap.
CHAT-PUSH | Push the 06-09 batch (chat layout + journal banner + AI fixes + vehicle picker) to prod | Todo/Ops | Deploy | P1 — High | OPEN | N/A — confirm landed | recap 06-09 | Whole 06-09 session is local-only at recap time (user was saving/pushing at the end). No migrations in the batch = low-risk. After push, confirm Render deployed (PROD-6: auto-deploy flaky, manual Deploy if no build within ~1 min). Verify chat layout on prod (hard-refresh the phone — cached CSS/JS can mask). Commits incl: 5abdaf2 c9aa405 8cde9f9 a846dd9 6c2ff05 (journal), e776b3d f2bb1ce (AI), bf89b0a (vehicle), 06e9592 6291f67 d815916 e534fda 2829b28 (chat), e15875f (revert), plus diag-removal commits.
CHAT-RESTBOTTOM | Chat rest-at-bottom — superseded/RESOLVED by the pin structure | Note | Mobile/UI | P3 — Low | RESOLVED (06-09) | N/A | recap 06-09 | Earlier in the session this was PARKED for late June after a scroll-based attempt failed. SUPERSEDED: once the input was pinned (e534fda) and messages wrapped in flex justify-end (2829b28), rest-at-bottom works structurally without any scroll hacking. No longer a separate backlog item. KEY LESSON: the fix was structural (pin input like a chat app), not scroll logic — scroll-based attempts fought the layout.
TRIPS-BOX-TALLER | Make the Trips banner map box slightly taller than the choropleth box | Todo/Polish | Journal/Maps | P3 — Low | OPEN — optional | N/A | recap 06-09 | User wanted the Trips-mode map box a touch taller than the states choropleth box (more room for the map + its controls). Would break the equal-size flip rule (box would change size between States and Trips modes). Small height-value change, never built. Optional polish.

## Legend & How to use
RoamReady — Bug & Todo Tracker
Built ¦ Updated 2026-06-09: marked MOBILE-CHAT-HDR + FT-1 resolved; appended JBANNER-1, AI-ORIGIN-1, AI-FT-LEAK-1, VEH-PICKER-1, CHAT-DEADSPACE-1, CHAT-PUSH, CHAT-RESTBOTTOM, TRIPS-BOX-TALLER from the 06-09 mobile-chat-rebuild + bug-fix session. NOTE: 06-09 batch was local/unpushed at recap — CHAP-PUSH tracks landing it. | 2026-06-02 from LAUNCH_STATUS.md (audit basis 2026-05-28), session recaps 05-23 & 05-27, and this session's OHV work. ¦ Updated 2026-06-02: appended PROD-1..6 + DISC-1 from the production-deployment (Render) session. ¦ Updated 2026-06-02 evening: appended HOME-MODAL, PROF-1, AI-MESA-1 (all DONE, verify in browser) + PROF-2 (design done, build AM).
IMPORTANT — staleness | DONE items come from the 2026-05-28 audit, not a live re-check. Anything with 'Verify vs current code?' = YES should be re-verified against current main before you trust it for launch. This is the stale-April-audit lesson.
Priorities are PROPOSALS | Each priority is Claude's suggestion with rationale in Notes. You own the launch calls — the Priority and Status columns are dropdowns; override freely, then re-sort/filter.
Priority key
P0 — Launch blocker | Must fix before launch. Currently only AI-path items, all marked DONE — re-verify.
P1 — High | Strongly want before launch or right after; real user-facing damage.
P2 — Medium | Should fix; not catastrophic at launch.
P3 — Low / cosmetic | Polish / cleanup; safe to defer.
P4 — Post-launch | Explicitly deferred; logged for later.
Status colors | Green = DONE/VERIFIED · Red = OPEN · Amber = SCOUT needed
Gap to close | This sheet is built from docs + memory, NOT a live repo read. For a fully authoritative version, run a CC scout that dumps all 3 LAUNCH_STATUS.md tables + greps the code for TODO/FIXME, and reconcile against this sheet.