## Bug Tracker
RoamReady.ai - Bug Tracker
End of day: Monday, June 22, 2026 (RR49) - PRODUCTION LIVE - admin moderation and growth suite shipped
ID | Title / Symptom | Severity | Source | Status | Resolution | Key commits
DUP-CINDY | Duplicate Cindy account from email case-sensitivity (cindy@ vs Cindy@) | High | RR48 / launch | Fixed - verified | Scout mapped User FK relations (most Cascade; Feedback SetNull; Notification no-FK). Read-only verify query in Render Shell confirmed lowercase Jun-22 row empty (0 children except 1 PlanningSession/1 AIUsageLog). Deleted by exact CUID cmqpt3xkc001voe2ffjkmklhm inside a transaction (DELETE 1 then COMMIT). Keeper cmpx6fgdi... (Cindy@, Jun 2, real data) untouched. | manual SQL (Render Shell)
BUG-EMAIL-CASE | Email treated case-sensitively - allowed duplicate accounts | High | RR48 / launch | Fixed - verified | Shared normalizeEmail() helper wired into all 6 paths (signup, Google OAuth writes; login, signup dup-check, password-reset, OAuth compare). Then one-shot backfill UPDATE lowercased 2 existing rows (Cindy@ and a real user Mgsmith4x4@). Collision survey returned 0 before backfill. Verified: mis-cased login works on password AND Google. | push (normalizeEmail) + manual backfill SQL
ONRENDER-REDIRECT | onrender client URL did not redirect to roamready.ai; login cookie scoped to apex left users stuck on the onrender host | Medium | RR49 / Benny | Fixed - verified | Render static-site redirect rules cannot be host-scoped (would loop on roamready.ai), so added an exact-match host guard script as first child of <head> in index.html: if hostname === roamready-client.onrender.com, location.replace to roamready.ai preserving path+query+hash. Does not touch /api XHR rewrite. Verified bounce + deep-link. | b71d1df
BILLING-COMP-DISPLAY | Comped user saw Free Plan / Trial / Upgrade on Billing page despite having Pro | Low | RR49 / Benny | Fixed - verified | Root cause: client User type lacked compTier/compExpiresAt, so the page (fed by /auth/me) could not read comp state already present at runtime. Added fields to client type + getStatus; 3-branch display (real sub > valid comp > free). Comp shows Pro (complimentary) + expiry + soft subscribe link; lifetime shows Lifetime with no prompt. Verified on screen. | (in grant-pro + billing commits)

## Launch Status
RoamReady.ai - Launch Status
Source of truth: LAUNCH_STATUS.md ¦ STATUS: PRODUCTION LIVE at https://roamready.ai (RR49)
ID | Item | Status | Severity / Category | Notes
CLEANUP-TESTSUB | Cancel live subscription from real-card test | OPEN | Cleanup / Low | Benny does first thing RR50. Stripe Dashboard (Live mode ON) -> Subscriptions -> the one test sub -> Cancel immediately. Payment already refunded; cancel stops any rebill. Only one live sub exists, so no risk of hitting a real customer.
CLEANUP-JUNK | Archive 7 myproduct $15 junk products in live catalog | OPEN | Cleanup / Low | RR50 dashboard task. Product catalog (Live) -> Archive each (not delete). Checkout unaffected (code uses only the 4 real price IDs). Tidiness only.
FOUNDER-CANCEL-TEST | Runtime-verify founder-rate preservation before cancelling a real founder | OPEN | Gate / Med | Cancel-billing script is built and code-correct, but founder-rate preservation (metadata admin_cancel tag -> webhook skips forfeit) has NOT been watched working at runtime. GATE: non-founder cancels are fine to use; do NOT cancel a real founder-priced account until a test-mode founder subscription has been stood up and the rate confirmed to survive a cancel. (build-green != runtime-correct).
FR-TIER2-ANONYMIZE | Tier 2: one-way anonymize (true data erasure, retain billing shell) | DEFERRED | Post-launch / Legal | Designed + scouted (field map, Stripe-cancel-first ordering, free-text hiding spots incl co-traveler PII and Rig license plates, AdminActionLog). Under CCPA thresholds so not legally required yet. GATE: attorney to set retention periods + bless scrub-vs-keep field list before it runs on a real person. Build script-first, dry-run on a throwaway.
COMP-FILTER-NICETY | Add a Comped option to the Active/Suspended/All filter | DEFERRED | Polish / Low | Comped users are visible in Active/All with the badge, just not filterable-to-only. That filter is the server-side account-status param; a comped filter needs a new server status. Easy add later.
BUG-AI-NODATE-ASK-B | Backend stops silently defaulting null startDate to today in recomputeStopDates | DEFERRED | Post-launch | Carryover. Part A shipped RR48 (opening flow asks+confirms start date).
FR-NIGHTS-BANNER-RESIDUAL | Fire shortfall banner only on post-reconcile residual | DEFERRED | Post-launch | Carryover.
TZ-OFFBYONE | Off-by-one date display in behind-UTC timezones | DEFERRED | Post-launch | Carryover.
MOBILE-CHAT-INPUT | Mobile chat input off-screen on keyboard | DEFERRED | Post-launch | Carryover. Fix = visualViewport listener to lift input above keyboard. Measure-first. Pre-existing, not session-caused.
FR-ROUTE-HWYPREF-1 | Rig-aware prefer major highways / 4-lane routing preference | DEFERRED | Post-launch / Low | Carryover.
FR-SCOPE-HUMOR-1 | Scope guard tone improvement with on-brand dry deflection | DEFERRED | Post-launch / Polish | Carryover. Touches sensitive prompt code; recommended for post-launch A/B test.
LAUNCH-DNS | DNS cutover to roamready.ai | DONE | Launch | RR48. Apex A -> 216.24.57.1; www CNAME -> roamready-client.onrender.com. Email records preserved. SSL issued.
LAUNCH-STRIPE | Stripe test -> live flip | DONE | Launch | RR48. Real-card test: charge -> Pro -> refund. All 4 live pieces verified.
DUP-CINDY | Delete empty Cindy duplicate account | DONE | RR49 | Verified. Deleted by CUID after zero-child verify.
BUG-EMAIL-CASE | Email case-sensitivity normalize + backfill | DONE | RR49 | Verified. normalizeEmail on 6 paths + 2-row backfill.
ONRENDER-REDIRECT | onrender host -> roamready.ai redirect | DONE | RR49 | Verified bounce + deep link. b71d1df.
FR-ACCT-SUSPEND | Reversible account suspend/reactivate + auth-state enforcement + audit log | DONE | RR49 / Admin | Verified in browser. Shared accountLifecycle service (one impl for script + buttons). Auth gates: requireAuth + refresh + Google OAuth all reject deactivated. Self-suspend and owner-suspend guards refuse. History timeline. Migrations add_account_deactivation (deactivatedAt, deactivatedReason, AdminActionLog).
FR-CANCEL-BILLING | Optional Stripe cancel/refund on deactivate (script) with founder-rate preservation | DONE | RR49 / Admin | Built + pushed. SUSPEND default / CANCEL opt-in / --immediate / --refund. Stripe-first then DB; webhook owns downgrade; founder rate preserved via admin_cancel metadata tag. NOTE: see FOUNDER-CANCEL-TEST gate above before cancelling a real founder.
FR-GRANT-PRO | Grant/revoke complimentary Pro (admin) independent of Stripe | DONE | RR49 / Admin | Verified (PDF export works for comped user; revoke clears). Schema add_complimentary_access (compTier/compExpiresAt/compReason/compGrantedBy/compGrantedAt). hasAccess additive comp clause, never touches Stripe fields. 1mo/1yr/lifetime/custom-date. Comped badge + history + honest Billing display.
FR-ADMIN-DELETE-USER | Cascade-aware delete-user in admin panel | DEFERRED | Post-launch | Superseded in practice by suspend (reversible) + Tier 2 anonymize (parked). True hard-delete remains for empties/tests only.

## Features Shipped
Features shipped - RR49 (Monday, June 22, 2026)
Admin moderation + growth tooling, all scouted/built/verified this session
Feature | What it does | Status | Key commits
Email case-normalization | Shared normalizeEmail() on every write + compare path; one-shot backfill of existing mixed-case rows. Root-cause fix for the duplicate-account bug. Mis-cased login now works on password and Google. | Deployed | (normalizeEmail + backfill)
onrender host redirect | index.html host guard bounces the bare onrender URL to roamready.ai (path+query+hash preserved), exact-match so the apex never loops; /api rewrite untouched. | Deployed | b71d1df
Account suspend / reactivate | Reversible account on/off. Blocks login via requireAuth + refresh + Google OAuth (no leak path), hides from active admin lists. Shared accountLifecycle service used by both a CLI script and in-app buttons (one implementation). Self- and owner-suspend guards. Per-account moderation history timeline. AdminActionLog audit. | Deployed | 212909e, f90859e
In-app admin moderation UI | Subscribers page gains per-row Suspend/Reactivate buttons, Active/Suspended/All filter, Suspended badge + reason inline, required-reason confirm dialog, and a generic History modal (renders all action types incl. future ones). | Deployed | f90859e
Cancel-billing + refund (script) | Optional Stripe subscription cancel on deactivate: default at-period-end or --immediate, opt-in --refund with extra confirmation. Stripe-first-then-DB, webhook owns the downgrade, founder rate preserved on admin cancels via metadata tag. Stays script-only (deliberate friction on money). Founder path pending runtime verification. | Deployed | 4edd346
Grant / revoke complimentary Pro | Owner grants Pro with no Stripe charge: 1 month / 1 year / lifetime / custom date + reason. Comps live in separate comp* fields (never pollute revenue or collide with real subs). Comped badge, history, and honest user-facing Billing display (Pro (complimentary) + expiry, soft subscribe link on time-limited, none on lifetime). | Deployed | 65c05da + billing fix

## Backlog & Open Items
Backlog and open items - updated RR49 (June 22, 2026)
Carried + new. RR50 starts with the two Stripe dashboard cleanups.
Priority | Item | Notes
1 - RR50 first | Stripe cleanups (cancel test sub, archive 7 junk products) | Pure Live-dashboard clicking, no code. Benny does cancel-test-sub first thing; both walked click-by-click.
1 - RR50 | A few bugs + full handoff | Benny flagged: tackle a few bugs and do a handoff next session.
2 - Gate | Founder-cancel runtime test | Stand up a test-mode founder subscription and confirm founder rate survives an admin cancel BEFORE cancelling any real founder. Non-founder cancels OK now.
2 - Parked | Tier 2 anonymize (data erasure) | Designed. Attorney to bless retention + field list. Script-first, dry-run on throwaway. Not legally required yet (under CCPA thresholds).
3 - Recommended | Non-founder fresh-account click-through before announcing | Payment path proven; confirm first-time-visitor paywall/pricing display before soft launch to RV communities.
4 - Polish | Comped filter option | Add Comped to the Active/Suspended/All filter (needs a new server status param).
4 - Polish | NIGHTS-PROSE-1 | Model narration can misstate nights vs the correct card. Feed derived totals into the model summary. (Carried.)
Carryover | Open trip/AI items | BUG-AI-NODATE-ASK Part B, FR-NIGHTS-BANNER-RESIDUAL, TZ off-by-one, mobile chat input keyboard, FR-ROUTE-HWYPREF-1, FR-SCOPE-HUMOR-1.
Dev infra note | Prisma tsvector phantom recurs | Every auto-migration re-adds the spurious ALTER TABLE JournalEntry ... DROP DEFAULT on the search tsvector col - strip it before applying. Also: this Prisma version refuses migrate dev/--create-only non-interactively (use migrate diff -> strip -> migrate deploy), and migration folder timestamps must be UTC to sort correctly. Never accept a DB reset.