## Bug Tracker
RoamReady.ai — Bug Tracker
Updated RR55. Open items on top by severity; completed green rows hidden by default.
ID | Title / Symptom | Severity | Source | Status | Resolution / Notes
BUG-ORIGIN-DISAMBIG-REGRESSION | Planner asks "start from home in San Jose, or somewhere else?" even when the origin is explicitly stated in the request (e.g. "create a trip from Denver to Aspen"). Origin (Denver) is in the user message but the disambiguation gate does not read it. Previously fixed - has regressed. | P1 | User test (Benny) - dev RR55 | Done — RR55 | FIXED RR55 + PUSHED. Root cause: AI tag captured too late (after the gate); regex too brittle for messy input. Fix: AI tag = primary origin/dest source captured pre-gate, geocode-validated + anti-fabrication; hard gate keyed on resolved origin not home; catch-all tag strip. All 5 messy-input tests pass on dev; live on prod.
SCOUT-GOOGLE-SEGMENT-AVOID | Verify: can Google Directions reliably route around a SPECIFIC banned segment via waypoints? (the load-bearing unknown that gates the auto-reroute half of the pivot) | P1 | RR55 pivot | Open | FIRST TECHNICAL SCOUT of RR55, before committing to auto-reroute. Google native avoid= only covers highways/tolls/ferries — NOT a specific road/segment. To force a detour around a known no-go (e.g. a banned pass), we must inject a via-waypoint that pushes the route off the banned segment. That trick can be finicky (waypoint placement, snapping, multi-leg). SCOUT GOAL: confirm whether we can reliably force avoidance of a specific segment, and how robust it is. GATING: if reliable -> auto-reroute is viable (ship after warnings). If flaky -> ship WARNING-ONLY (still honest, still valuable) and treat avoidance as best-effort. Either way the warning path does not depend on this. Read-only research/scout; report before building.
BUG-WEATHER-DATE-RANGE | Weather fetch 400s — trips dated 2025 (should be 2026) push Open-Meteo out of allowed range; also needs graceful fail-soft for far-future dates beyond forecast horizon | P1 | RR54 testing | Open | Found RR54 during HERE testing. Open-Meteo forecast API 400s with reason "Parameter 'start_date' is out of allowed range from 2026-03-26 to 2026-07-12" — because trips are being created/stored with 2025 dates (e.g. start_date='2025-07-15') even though the user requested July 2026 and the session/UI shows 2026 (anchor=2026-07-15 in recomputeStopDates). So the WEATHER fetch (getTripWeather → fetchLiveForecast, weatherFetch.ts:77 / trips.ts:3708) sends a year that's outside Open-Meteo's rolling forecast window (~now through ~16 days out, hist+forecast bounded) and every stop's weather fails. Two-layer issue: (1) ROOT: a year is resolving to 2025 somewhere in trip/stop date creation for the weather call (the trip anchor is 2026 but the weather params say 2025 — find where the weather call derives its year; likely a stale 'today'/year default or a created-trip vs requested-date mismatch). (2) RESILIENCE: even once dates are right, Open-Meteo only serves a limited date window — a trip dated beyond the forecast horizon (months out) will ALWAYS 400. Weather fetch must fail-soft GRACEFULLY (skip/placeholder 'forecast not yet available for these dates', not a wall of unhandled axios 400 stack traces in logs). NOTE: does NOT affect routing — routing/restrictions/line all worked in same run; weather is independent. Reproduced repeatedly on NYC→Montauk Jul 2026 trips.
BUG-ROUTE-NOT-RV-SAFE | Directions links + measured drive-times use Google's DEFAULT CAR route — no rig height/length/weight/grade awareness. Live prod handed a 40ft coach the Pinecrest→Zephyr Cove leg over CA-108 Sonora Pass (posted vehicle-length/trailer restrictions, ~26% grades) — a route a big rig cannot legally/safely take. Core product promise (RV-safe routing) was never actually built; only drive-TIME was made honest (Plan-is-Truth), never the ROUTE. AI deliberately removed from route choice (MESA), so nothing in the system checks rig restrictions. | P1 | User test (Cindy/Benny) — prod | Open | THE TOP ITEM ON THE BOARD — above WSL + three-option refusal. Found RR54 on live prod. Root: directionsUrl helper (FEAT-LEG-DIRECTIONS) builds a plain maps/dir/?api=1 link = Google car route; server drive-times (fetchLegDetail/planLegSplits) measure the same car route honestly but it's still a CAR route. Google Directions API has NO true RV/truck mode (no height/length/weight/grade params). FIX (Phase 2, own arc, real cost): integrate a rig-aware routing provider (HERE / PTV / Trimble-MapQuest truck routing) for BOTH the directions links AND the server leg measurement; feed rig dims from the existing Rig profile (RigPage combined-length is already captured, currently DISPLAY-ONLY per RigPage.tsx:91-93). Claude to research current provider options/pricing before Benny picks one. Until then: honest disclaimers hold the line (see BUG-TIPCARD-FALSE-CLAIM). INTERIM STOPGAPS to scope under this item: (a) deterministic per-leg "verify rig restrictions yourself" caveat on every drive leg (server-stamped, true 100%, no AI knowledge needed — do NOT let the AI volunteer pass-specific warnings from memory, reintroduces MESA fabrication risk); (b) rerouting tools (delete stop / add stop along the way / chat modify) already EXIST but are hazard-blind — a user can reroute but the new leg can hit another restricted pass; real safe-reroute needs the provider too. ¦¦ LOCKED ARCHITECTURE (RR54, decided with Benny): HERE replaces Google as the drive-time/route ENGINE inside the existing Plan-is-Truth pipeline — NOT a display-time swap. Flow: (1) AI picks STOPS only (unchanged, never picks roads/never hints HERE — MESA line stays clean); (2) server asks HERE truck/RV routing for the real RV-safe route between consecutive stops, passing rig dims (height/length/weight/grade) from the Rig profile (RigPage combined-length already captured, currently display-only); (3) HERE returns PATH + TIME — both become source of truth: drive time, arrival, AND any required transit overnight are all computed from HERE's safe path BEFORE the user approves the plan; (4) Google displays HERE's path via forced WAYPOINTS extracted from HERE's polyline (geometric hand-off, NOT the AI describing the route to Google — descriptive hand-off = MESA fabrication risk). WHY Option B not A: Benny caught that routing AFTER the plan (Option A: HERE reroutes a finalized plan) makes the plan DISHONEST — approved time/arrival/overnights would disagree with the road actually driven. Plan-is-truth requires HERE feed INTO planning, so the measurement swap (fetchLegDetail/planLegSplits source HERE instead of Google) is the correct shape. Bigger build (touches the core measurement path everything depends on) but the only honest one. PROVIDER = HERE (recommended): real free tier (first 5,000 advanced-routing transactions free, then ~$2.50/1k), pay-as-you-grow, returns leg sections + flexible-polyline matching the existing leg shape. PTV = enterprise/fleet, overkill. Google has NO RV/truck mode. RESIDUAL GAP: HERE nails infrastructure restrictions (bridge/weight/posted truck bans — the Sonora Pass class). RV-specific park-road length limits / scenic-byway bans / seasonal closures are looser (per-park/road, no national rule), so the deterministic server-stamped "verify rig restrictions yourself" caveat STAYS even after HERE — shrinks the gap, doesn't close it 100%. Never let AI volunteer pass-specific warnings from memory. NEEDS FROM BENNY: a HERE account + API key (credential = Benny's hands, not CC). Touches server + client = own focused fresh session, scout-first. ¦¦ RR54 INTEGRATION STATUS: HERE engine LIVE behind flag — measures rig (height/length/weight), catches LEGAL restrictions (proven: NYC→Montauk parkway ban rerouted onto LIE), inserts overnights, flags restriction notices to UI (amber advisory, both panel + prose). Map-waypoint display built (HERE corridor via Google via:true). TUNING: 8→3 waypoints cut most wobble (143→126mi) but residual hook near Yaphank remains — needs Fix B (snap waypoints to road centerline). BLOCKER: Google ROADS API is NOT enabled on the key (403 API_KEY_SERVICE_BLOCKED, project 721991817454) — Benny must enable "Roads API" in Google Cloud console + allow it on the Maps key (paid SKU, low volume = 1 call/route-gen) before Fix B can build. Snap insertion point confirmed: generateRoutes (trips.ts:3263-3269) after sampleCorridorWaypoints. Interim alt if Benny skips paid API: drop to ≤2 waypoints or midpoint-bias sampling (snapping is the clean fix). All HERE work on local main, ahead of origin by 12, UNPUSHED.
FEAT-ROUTING-REQUIRED-DIMS-DISCLAIMER | Make GVWR/length/height required for HERE routing (with type-based fallback ladder) + prominent persistent liability disclaimers on rig form, route view, per-route | P1 | Benny decision (RR54) | Open | QUEUED for RIGHT AFTER the HERE-Google integration completes (Benny RR54). Three parts: (1) REQUIRED FIELDS: make GVWR + length + height REQUIRED on the rig form when HERE routing active — half-filled rig silently disables the matching restriction class (confirmed: null height = no height checks). Handle EXISTING rigs gracefully (soft-require + "complete your rig for safe routing" nudge, do not break saved rigs). Pairs with the FALLBACK LADDER (decided RR54): user GVWR if set → else conservative type-based max (err HEAVY/safe) → else height/length only. Claude verifies the per-type max weights before hardcoding. (2) PERSISTENT LIABILITY DISCLAIMER (visible, not buried): user verifies clearances, weight limits, AND grade themselves; RoamReady provides a SUGGESTED option that MAY OR MAY NOT be right; no route-fitness guarantee. On rig form + trip/route view. Benny: "they need to take responsibility for themselves so they do not automatically blame us." (3) PER-ROUTE VERIFICATION PROMPT at route generation: "double-check clearances, weight, and grade for these roads before you drive them." MESA/liability principle; makes the existing ToS route-fitness disclaimer VISIBLE at point of use.
FEAT-GRADE-HAZARD-DB | Curated dangerous-pass + restrictions hazard database — now the CORE data layer behind FEAT-HAZARD-DB-ROUTING (was a side-feature, now central after the RR55 pivot) | P1 | Benny (RR54, drove Sonora) | Done — RR55 | SHIPPED RR55. Hazard table + corridor/name match + rig-gating live. 18 restrictions + 11 HIGH grade passes (Sonora etc) seeded. Warnings fire on planning page AND map page (red Rig warning pill). Restrictions live on PROD; grade seed on dev, pending prod seed+push.
BUG-PLAN-ORIGIN-NULL | HOME stop with a non-matching city resolves to NULL coords server-side — possible wrong origin fed to routing (mileage/route correctness, not just cosmetics) | P2 | RR54 logs | Open | Surfaced in RR54 NYC->Montauk logs while Benny's home is San Jose: '[createStop:homeCoords] HOME stop city mismatch — locationName=New York City != homeCity=San Jose -> null coords (will be geocoded by client)' and '[createStop] locationName=New York City resolvedLat=null resolvedLng=null'. The HOME/origin stop came through with NULL server coords and was deferred to client geocoding. EVIDENCE something's off: the in-app run measured 124mi / 2722 polyline pts while a clean isolated point-to-point of the SAME corridor measured 116mi / 2441 pts — more points AND longer in-app, consistent with the routing origin differing from the clean test. WHY IT STILL MATTERS post-pivot: if the origin geocodes WRONG (falls back to the San Jose home, a 0,0, or a different NYC point), that is a CORRECTNESS bug affecting mileage and the computed route regardless of which vendor draws the line — fix before shipping routing. If it turns out the origin is fine and the discrepancy was purely the abandoned HERE polyline, this dies with that approach. A read-only scout was dispatched end of RR54 to determine origin-coordinate-bug vs polyline-concatenation-order. CHECK THE SCOUT RESULT EARLY IN RR55.
FEAT-THREE-OPTION-REFUSAL | [Enhancement] When a trip can't fit requested nights, offer THREE paths not two: (1) add nights, (2) pick closer, (3) NEW: keep the nights & drive longer days (back-solve the required drive cap) | P2 | Benny idea | Open | Benny has 3 drivers, wants the option to keep tight nights by raising the daily drive limit. Recommended approach (Option A): back-solve the drive cap needed to fit requested nights and offer the specific number ('to keep 10 nights I'd stretch your driving to ~8h/day, OK?'). Real (possibly iterative) logic — its own focused build. Build on the now-deterministic minimalTripBudget foundation. Deferred to fresh day. Logged RR52.
DEVENV-WSL-MIGRATIONS | [Dev env] Windows Smart App Control now blocks Prisma's unsigned schema-engine-windows.exe — local `migrate deploy`/`migrate diff` fail (EPERM/spawn). Worked around RR53 via Docker-container psql + manual _prisma_migrations INSERT. Recurs on EVERY future local migration. | P2 | Dev env (RR53) | Open | DURABLE FIX: run Prisma migrations from WSL (Linux schema engine, never subject to Windows SAC; applies + records _prisma_migrations atomically — no manual SQL surgery). Do NOT disable SAC (was irreversible pre-Dec2025; now reversible but global on/off, worse than WSL). prisma generate is NOT blocked (in-process WASM) — only the migrate schema engine. Next-session setup task. Logged RR53.
DEVOPS-SPLIT-GOOGLE-KEYS | Split shared Google Maps key into server-only + browser keys (referrer-restriction on shared key would break all server-side Google calls) | P3 | CC finding (RR54) | Open | RR55 NOTE: the pivot to Google waypoint-avoidance routing leans HARDER on server-side Google Directions calls, so this matters more now (though still pre-launch-hardening priority). ¦¦¦ Hardening (found RR54 during Roads API setup). The Google key is SHARED: GOOGLE_MAPS_API_KEY === VITE_GOOGLE_MAPS_API_KEY (one 39-char value used both server-side AND in the browser). LATENT FOOTGUN: the moment anyone adds an HTTP-referrer restriction to harden the browser-exposed key (standard practice), EVERY server-side Google call (Directions, Geocoding, Roads/snapToRoads) instantly 403s — they send no referrer — and routing silently breaks (snap → permanent unsnapped fallback). FIX: split into TWO keys — (1) a server-only key, unrestricted or IP-restricted to the Render servers, for backend calls; (2) a separate HTTP-referrer-restricted key for the browser (VITE_). Not urgent (shared key works today) but DO before locking down the client key / before launch security hardening. Console-only task for Benny + a .env var split.
DEAD-CREATETRIP-ENDPOINT | createTrip (POST /trips) is a live auth-gated endpoint with NO in-app caller; tripsApi.create is dead client code | P3 | CC audit | Open | Decision for later: either wire a manual 'blank trip' create flow, or retire the endpoint + dead client method. Not urgent. Logged RR52.
MODIFY-CLARIFY-VERBOSE | When user references a stop not on the trip ('go to Boise instead of Salt Lake City' when SLC isn't a stop), AI gives a wordy 'I don't see X' clarifying reply | P3 | User test (Benny) | Open | Not a bug — AI correctly won't guess which stop to swap (guessing = silent wrong-swap risk). Low-pri tone item: could make the clarifying question tighter/less wordy. Do NOT make it guess. Logged RR52.
UX-TRANSIT-NIGHT-INFLATE | [UX] Requested nights + required transit overnights inflate the displayed total (10 nights shows as 12-15n badge); disclosed in honest notes but the badge contradicts what the user typed | P3 | User test (Benny) | Open | Not a bug (Check C — mild overshoot allowed by design; every added overnight is explained in the honest drive-time notes). UX polish: panel could distinguish 'N nights at destinations + M driving nights = total' so the badge doesn't contradict the typed number. Deferred. Logged RR52.
TEST-HARNESS-NOEXIT | [Dev env] CC test runners (extractFromXtoY.test.ts, prebuildBudget.determinism.ts) don't self-terminate on Windows — orphaned tsx/node processes accumulate (24 seen RR53), hold the query-engine DLL handle, and cause EPERM on `prisma generate`. Root cause of the RR53 generate-blocking saga. | P3 | Dev env (RR53) | Open | The determinism harness makes live Google Directions calls and hangs without exiting; unit runners stack up across runs. FIX: add a timeout + explicit process.exit() to the test harnesses so they terminate cleanly. Mitigation meanwhile: kill orphaned node by __tests__ command-line match before `prisma generate`. Logged RR53.
FR-RATE-DECIMAL | Booking rate-per-night: auto-format to decimals (type 5500 → 55.00) | P3 | User req (Benny) | Open | RR53 deferred — parked after time picker + directions. Currency-input formatter on the rate field in ReservationSection. Small, self-contained. Next booking-form item.
BUG-TIPCARD-FALSE-CLAIM | Planning-session tip card (SessionTipCard.tsx) made an explicit FALSE safety claim: "RoamReady knows your rig — we route around low bridges and tight switchbacks automatically." Product does NOT do this (confirmed by in-code admission RigPage.tsx:91-93). Live prod copy was promising a routing-safety capability that doesn't exist + directly contradicted the ToS. | P1 | User test (Benny) — prod | Done | RR54 RESOLVED. One-line copy swap: replaced the false capability tip with an honest knowledge-kind advisory: "Routes don't yet check rig restrictions — always verify height, length, weight, and grade limits for your vehicle before driving." CC routed it to the existing 'knowledge' kind (the suggested 'tip' kind would've failed typecheck — Kind is a closed union try¦capability¦knowledge¦brand). Aligns live product with ToS (TermsOfServicePage.tsx:177-182 already disclaims route fitness). MESA principle: don't let the product imply a safety it can't back. Verified via grep: "switchback"/"low bridge" gone from file. Commit on local main (merge c2ce7e4). PENDING PUSH (client-only, push=prod deploy). Landing-page "rig compatibility" copy left alone — that's campground FIT, not routing safety, a real adjacent feature.
FEAT-ACCOUNT-MENU-EMAIL | [Enhancement] Account dropdown (upper-right name/icon) should show the logged-in user's email so the active test account is identifiable at a glance when switching between many accounts. | P3 | User req (Benny) | Done | RR54 SHIPPED (client-only). Added a 2-line header at the top of the dropdown PANEL (trigger button untouched): full name (text-sm gray-700 font-medium) + muted email (text-xs gray-500, truncate/ellipsis if >192px panel), then a 0.5px divider, then existing Profile/Billing/Sign out unchanged. user.email already on the useAuthStore() user object — pure display, no fetch. AppLayout.tsx +8. CC caught + corrected a git add -A that swept two untracked RR53 docs into the merge (rewound, re-committed client-only, nothing pushed). Merge de50a31 on local main. PENDING PUSH (bundled with BUG-TIPCARD-FALSE-CLAIM — both client-only, one push ships both).
BUG-MODIFY-INTENT-CONFUSION | “Create a stop in [city]” on an open trip is sometimes mistaken for new-trip planning; AI asks planning questions instead of adding the stop | P2 | User test (Benny) | Done | FIXED (prompt-only): added a change-destination path (remove old + add new, carry over nights) + a guard so modify mode never re-asks origin/start-date/total-nights + scoped the clarifying-question line. Tester-confirmed + local-tested ('change destination to Denver' swaps cleanly, no re-interrogation). Local main.
TZ-OFFBYONE | Off-by-one dates on weather day, journal edit prefill, reservations bucketing, admin session inspector | P2 | User test (Benny) | Done | Routed four surfaces through parseTripDate; weather day numeric. Pushed.
BUG-ROUNDTRIP-MODIFY-DROP | Round trip on an already-built trip via modify did not insert the return leg | P1 | Prod behavior | Done | buildModifyInstructions gained a round-trip action. Pushed.
BUG-ROUNDTRIP-PLANNING | Mid-planning “make it a round trip” didn’t rebuild; malformed <modify> tags leaked | P2 | User test (Benny) | Done | Planning re-emits full itinerary inline; stray tags scrubbed; strip regex broadened. Pushed.
BUG-AI-NODATE-ASK-B | recomputeStopDates fabricated + persisted today’s date for dateless trips (silent fake DB write) | P1 | CC audit | Done | Leaves stop dates null when no real anchor. Anchor path byte-identical. Pushed.
BUG-PDF-TOSTRING | Cindy’s PDF crashed on free-text times without a colon (“3pm”) | P1 | Prod user (Cindy) | Done | Finite-check fallback to raw string. DEPLOYED TO PROD (roamready-client).
STORED-NIGHTS-OFFBYONE | Stored Stop.nights one short for stays entered as “N days” via modify (9-day stay stored as 8) | P1 | User test (Benny) | Done | Root: modify prompt said days-minus-1 while planning said days=nights. Aligned both + added date-range rule. Pinecrest row corrected manually + backfill. Pushed. (Fresh-thread test pending.)
ITIN-NIGHTS-MISMATCH | Itinerary stay card showed 3 disagreeing numbers (badge 8 / span 8 / cost 9) for one stop | P1 | User test (Benny) | Done | Display-only fix: badge, date range, day-span all show true booked window (true nights, arrival→checkout). PDF matches. Pushed.
BUG-MODIFY-ADDSTOP-SEQUENCE | Stop added via modify landed in the wrong geographic position (Fort Stockton before Toyahvale) | P2 | User test (Benny) | Done | Server geocodes the new stop + re-slots only it by min-added-detour; origin/finish/booked pinned. Pushed.
BUG-PLAN-BUILD-DIVERGE (Part 1) | Built trip differed from approved plan: phantom transit stop + scrambled nights | P1 | User test (Benny) | Done | Part 1 (build verbatim) + Part 2 (server-sole drive-time check) COMPLETE. See BUG-PLAN-IS-TRUTH-P2. Pushed status: local main.
BUG-LONGLEG-CANT-DELETE | User couldn't delete a transit/overnight stop on a still-over-cap leg — recheck immediately re-inserted it, overriding the user | P1 | User test (Benny) | Done | Design fix: replaced silent enforcement with a confirm modal ('Remove this overnight stop?') showing real merged-leg hours. Confirm = delete + acknowledge leg (suppress re-insert); cancel = restore. Ack persists; resets if leg endpoints change. Local main.
BUG-RECHECK-DELETE-INVISIBLE | Delete on map-page trash-can appeared to skip drive-time recheck (no log, no overnight on a 6.5h merged leg) | P2 | User test (Benny) | Done | Not a bug — recheckLongLegs ran but only logged on insert; 6.5h leg was within the 1h grace (cap 6h tolerates 7h). Fixed by adding full observability logging on every recheck path + per-leg hours. Local main.
BUG-LONGLEG-ACK-NO-SESSION | Keep-long-drive acknowledgment stored in planning session — a session-less Trip would silently drop it (latent, not user-reachable today) | P3 | CC audit | Done | Moved ack to Trip.acknowledgedLongLegs JSONB column (migration 20260625120000, applied). Latent future-proof; every current user trip has a session. Cleaner design, removes session dependency. Local main.
BUG-MODIFY-GHOST-ROUTE | After an AI-modify destination change, the old map route line ('ghost path') stayed drawn until a manual page refresh | P2 | User test (Benny) | Done | Two causes: (1) route polyline dedup key wasn't invalidated on modify apply so it short-circuited the redraw; (2) geocoding effect had no .catch — a failed coord write left geocoding stuck true, permanently gating the route redraw until reload. Fix: invalidate dedup key on onTripUpdated + add .catch resetting geocoding flag. Client-only, local main.
BUG-PLAN-ORIGIN-LOOP | Planning sometimes re-asks for the starting location. Fixed common cases (bare 'X to Y', arrow 'X→Y', abbrev 'KC') but still flaky on run-together phrasings where night-count abuts the date ('3 nights july7') | P2 | User test (Benny) | Done | PARTIAL FIX shipped RR52: extractFromXtoY now handles 'X to Y', 'from X to Y', 'X → Y', abbreviations (KC→Kansas City). REMAINING: phrasings like '...3 nights july7' / '3 nights july2' (no separator between nights and date) still sometimes trigger the origin question. Inconsistent → parser fragile on the string tail. Tomorrow: harden parse for nights/date run-together. Open. ¦¦ RR53 FIX: bare "X to Y" origin capture (anchored to msg start, both-sides proper-noun guard, STOP set extended incl trip/flight/road to kill "Trip to Miami" false positive). 15/15 regression test (extractFromXtoY.test.ts). Commit fe4107e. Tested live. Pushed RR53 batch.
BUG-PLAN-BUILD-DIVERGE (Part 2) | Server now sole transit-stop inserter; honest measured drive-time notes; deterministic over-cap splitting | P1 | Session arc | Done | Whole Plan-is-Truth Part 2 arc. Server measures real Google drive times, inserts overnight transit stops, builds honest grounded notes from measured legHours. AI insertion rule removed. Tested across many live trips RR52. DEPLOYED (auto-deploy fired earlier). Local main has follow-on fixes below.
BUG-MODIFY-ONEWAY-ROUNDTRIP | Converting a round trip to one-way failed: removing return-home KC tripped the 'cannot delete home departure' guard, leaving trip half-modified | P2 | User test (Benny) | Done | Atomic makeOneWay server action: truncates everything after the turnaround (farthest-from-origin via Haversine). Guard now protects only the FIRST stop (departure), not every HOME. New make_one_way modify action wired through prompt+client. Built+merged local main, not yet runtime-retested on a fresh round trip (do tomorrow).
BUG-TITLE-DRIFT | Trip title mismatched destination (showed 'Portland, MO' / 'Indianapolis' instead of real destination) and didn't update on destination change | P2 | Tester FB-MYE1 + Benny | Done | Title now DERIVED from the turnaround (farthest-from-origin destination), flexible during planning, locked at Build, manual rename after. Fixed the round-trip 'picks return-leg city' bug (was showing Indianapolis; now correctly Bangor). Tested working RR52.
BUG-BUDGET-NONDETERMINISTIC | Budget-conflict refusal fired inconsistently for identical input (same trip built twice, refused once) and named a return-leg city, because it computed from the AI's variable per-run build | P1 | User test (Benny) | Done | Root cause: gate computed from AI's variable itinerary. Fix: minimalTripBudget computes conflict from the MINIMAL trip (origin→turnaround→origin), stable across runs. minNeeded=1+coreTransit (×2 round trip). Refusal now deterministic, names the turnaround (Bangor), states the minimum, offers to bump; 'yes bump it' builds at minNeeded. Tested 3× consistent build (10n) + 3× consistent refuse (3n) + one-way lower min (5). Local main.
BUDGET-REFUSAL-MIN-WOBBLE | Budget refusal fires deterministically but the quoted MINIMUM nights number wobbles across runs (e.g. '5-6' vs '9') because the AI paraphrases instead of stating the exact computed minNeeded | P3 | User test (Benny) | Done | The DECISION (refuse) is deterministic and the system HAS the right number (built at 9 when accepted), but the prose sometimes quotes a wrong lower estimate (5-6) instead of the computed minNeeded. Prompt-tightening: force the refusal to state the EXACT computed minNeeded verbatim, not an AI estimate. Same 'server stamps truth, model reports it' principle. Logged RR52. ¦¦ RR53 FIX: verbatim-echo of app-computed minNeeded + HISTORY_CAP defer guard + clause 3 (forbid fabricated miles/hours/driving-days/radius in budget justification; geography OK). Commits 2370553 + ac88959. Tested live AFTER clean restart: "why so many nights?" returns qualitative geography, zero fabricated numbers. Pushed RR53 batch.
BUG-BUDGET-SHAPE-MULTIPLIER | Stated minimum nights swings (e.g. 5→9) for identical trip input across turns because minNeeded's ×2 round-trip multiplier reads trip SHAPE from the AI's per-turn itinerary, which can flip one-way→round-trip between turns | P2 | User test (Benny) | Done | Found RR53. minNeeded = 1 + coreTransit, coreTransit = oneWayTransit ×(round-trip?2:1). Distance is deterministic; the ×2 shape multiplier follows the AI's emitted stops (computeTripShape reads last-stop-returns-to-origin). RR52 BUG-2 fix anchored DISTANCE to the minimal trip but still reads SHAPE + turnaround from AI stops. Fix: derive shape deterministically from the request (return language / explicit round-trip), not from AI's emitted itinerary. NOT caused by RR53 batch (both budget commits are prompt-only). Its own focused build. ¦¦ RR53 RESOLVED by structural pre-build budget fix: trip shape now derived deterministically via server-ported roundTripIntent (not AI per-turn itinerary). minNeeded stable across runs (one-way 4×5, round-trip 7×5). Commit b8c96fa. Pushed origin.
BUG-MILEAGE-OPENING-TURN | Model still volunteers fabricated mileage ("1,600+ miles one-way") on the INITIAL trip-acknowledgment turn; clause 3 (RR53) only covers the budget-justification ("why so many nights?") path | P2 | User test (Benny) | Done | Found RR53. Clause 3 verified working on the budget-justification turn (qualitative geography, no numbers) but the opening "KC to Bangor, 3 nights" acknowledgment turn still fabricates total mileage. Same leak class, adjacent path clause 3 doesn't reach. Recommended fix: lift the no-quantified-mileage/hours prohibition into criticalRulesBlock (high-salience, ALL turns) rather than another co-located clause. Pairs well before FEAT-THREE-OPTION-REFUSAL (keeps its drive-cap math honest). Its own focused build. ¦¦ RR53 RESOLVED by structural fix: app owns budget minimum pre-build (deterministic <destination> capture + parser primary). Model never states mileage/hours/days/nights — canonical suffix rule covers all turns; interim OPENING FLOW timing clause + BUDGET MINIMUM hedging DELETED/superseded. Tested 6/6 incl both-gates coexist. Commit b8c96fa. Pushed origin.
BUG-TRIP-MAPPINS-MX | Foreign map-pin bug, 2nd instance: a MEXICAN stop drops its pin in central US (Colorado fallback) — same root as the RR46/47 Vancouver→Colorado bug. The RR47 Canada fix was country-specific and left the body alive; Mexico (and any non-US/CA country) re-triggered it. | P2 | User test (Benny) | Done | RR53 RESOLVED with the GENERAL fix (find the body, not the heads). TripMapPage.tsx geocode previously forced "USA" + US componentRestrictions on every non-Canadian stop → foreign cities resolved to a US fallback coord. Fix: force US for {2-letter US state OR full US-state name OR blank}, force CA for CA provinces, UNRESTRICTED for any genuinely-foreign present state (Google resolves the country) — no per-country enumeration, cures the whole class. Hardening commit added full US-state-NAMES (data stores mixed "AZ" + "Arizona" formats) which also closed the "Georgia" US-state-vs-country hole. Commits 2e7aece (general) + b4b909c (hardening). Pushed origin, verified on prod (Mexican stop now lands in Mexico). NOTE: pre-existing bad rows (wrong-but-present coords) do NOT auto-heal — geocoder only re-resolves null coords; scoped NULL-and-re-geocode repair needed for any already-saved bad trip (Docker-psql local / Render Shell prod). Data finding: locationState stored inconsistently (2-letter AND full name) — audit elsewhere for read assumptions.
BUG-TRIP-SHAPE-ASSUME | Planner ASSUMES round-trip when shape was not stated. User: "plan a trip to Rocky point mexico from mesa arizona" (one-directional, no round-trip language). AI correctly ASKED one-way-vs-round-trip; user answered only date+nights ("july 1st for 6 days"), leaving shape unanswered — AI then built Mesa→Puerto Peñasco→Mesa (added a return-home leg the user never requested, prose said "and back"). | P2 | User test (Benny) | Done | Found RR53 on prod. Decision LOCKED: planner must NOT assume trip shape when unstated — build the literal one-way reading, user adds return via modify if wanted (lean: option 1; option 2 = re-ask/block-build still open). Root to scout: build-path shape default vs the server-ported roundTripIntent recognizer (tonight's budget fix) — if build defaults round-trip while budget uses roundTripIntent, they DISAGREE; cleanest fix may be making the build path respect the same recognizer (one source of truth for shape). roundTripIntent on this phrasing should return ONE-WAY (no "and back"/"return"/"round trip" language). Specific failure: an explicitly-asked-but-unanswered shape question resolves to round-trip — likely a hardcoded round-trip default. Scout queued. ¦¦ RR53 RESOLVED (find the body): build path rubber-stamped the model's round-trip on ambiguous input while budget path used hasRoundTripIntent (split-brain). Fix: aligned stripUnrequestedReturnLeg to strip-unless-positive-round-trip-intent → build==budget==prompt one-way default on the shared recognizer. 21/21 regression both directions. Pushed + verified prod.
FEAT-BOOKED-DEEPLINK | "Booked" status badge deep-links to its reservation (opens expanded) | P3 | User req (Benny) | Done | RR53 SHIPPED. Booked badge (stops-list pill + map popup) deep-links to /trips/:id/booking?stopId=; on-load handler now also opens the target Edit panel expanded (autoOpenEdit prop + one-shot ref guard so close stays closed; captured-once deepLinkStopId so in-page nav never re-opens). Commits 4eafff7 + e6775da. Pushed + verified prod.
BUG-PDF-TOSTRING | PDF render crashed on free-text check-in/out times ("3pm" no colon → NaN → toString threw, killed whole @react-pdf render). Cindy-reported prod. | P1 | Cindy (prod) | Done | RR53 RESOLVED at source via the time picker. Free-text time field was the single producer of malformed values; rest of system already uses canonical "HH:MM". Replaced with 3-dropdown picker emitting "HH:MM" — malformed input now impossible. Legacy rows lazy-self-heal on next Save; PDF Number.isFinite band-aid kept as defense-in-depth. Commit 7f909a5. Pushed, PDF verified clean.
FR-TIME-INPUT-PICKER | Time picker for booking check-in/out (replace free text) | P2 | Roadmap | Done | RR53 SHIPPED (same commit as BUG-PDF-TOSTRING cure). 3 dropdowns/field (hr, min 00/15/30/45, AM/PM), default PM-in/AM-out, stored "HH:MM", legacy on-load parse + self-heal. Commit 7f909a5.
FEAT-LEG-DIRECTIONS | Google Maps directions link per leg on map + itinerary pages | P3 | User req (Benny) | Done | RR53 BUILT (testing). Shared directionsUrl helper (maps/dir/?api=1, coords-preferred + City,State fallback). Map: per-stop-row "Directions to <next>" + popup, last omitted, stopPropagation guard. Itinerary: "Directions" on each DRIVE leg. New tab, MapPin. Commit 8c332b6. On local main at log time. ¦¦ REFINED RR53: two origins per leg ("from my location" omits origin→GPS · "from previous stop"); booked stops route to the campground NAME not the city (destinationForStop, path A, no fetch). RE-ANCHOR FIX: links now route TO each stop (not the next) — start stop has no link, each stop links to itself with prior stop as "from previous"; itinerary DRIVE rows were already correct (untouched), only map page fixed. Pushed + verified prod.
BUG-BOOKED-ADDR-HIDDEN | Booked stop hid the campground street address (collapsed booked row AND the edit/update panel both dropped it; unbooked cards showed it). User needs the address to confirm directions land on the right place. | P2 | User test (Benny) | Done | RR53 RESOLVED. BookedRowCard (collapsed) + the Edit expansion (ReservationSection panel) never rendered cg.address though cg (bookedCg lookup) was in scope. Added cg.address line to BOTH states, same field/format/guard as the unbooked RecommendedCampgroundCard. Pushed + verified prod (shows collapsed + expanded).

## Features & Roadmap
RoamReady.ai — Features & Roadmap
Updated RR55. Open/upcoming on top by priority; shipped = green.
ID | Feature | Priority | Status | Notes
FEAT-HAZARD-DB-ROUTING | Owned hazard database + honest planning-time warnings + steer Google to route around known no-go segments (the RR55 architecture) | P1 | TOP PRIORITY — Open | THE NEW CORE PATH (RR55 pivot, replaces FEAT-RV-SAFE-ROUTING). Three layers: (1) OWN a curated hazard database — grades (West 29 / East 19 passes, tiered 6/9/12%) + Restrictions (20: length/height/width/weight/tunnel/propane/vehicle-type bans). Built RR54, lives in the Grade Hazards (West/East) + Restrictions tabs of this file and in standalone RoamReady_Grade_Hazards_West.xlsx. (2) FIRE HONEST WARNINGS during trip planning when a route crosses a known hazard (the pop-up-during-planning mechanism). ANY restriction that could affect the rig surfaces a notice; hard bans vs advisories worded differently. (3) STEER GOOGLE to route around known no-go segments via forced via-waypoints — Google then computes AND renders its own clean line, dissolving the map-line rendering problem that killed the HERE approach. ¦¦ LOAD-BEARING UNKNOWN to scout FIRST: can Google Directions reliably avoid a SPECIFIC segment via waypoints? Native avoid= only does highways/tolls/ferries; segment avoidance needs the via-waypoint trick, which can be finicky. Verify reliability before promising auto-reroute. ¦¦ SEQUENCING (recommended): ship WARNING-ONLY first (honest value, no reroute dependency — already more than most RV tools), add auto-reroute second. ¦¦ BUILD-FIRST ANCHORS (highest confidence, facts w/ official sources): the legal length bans that exceed a 42-ft coach — Going-to-the-Sun 21ft, Independence Pass 35ft, Smugglers Notch 40ft (fine ->$10k Jul 1 2026), Beartooth 40ft, Tail of the Dragon 30ft — plus propane tunnel bans (Baltimore, Boston Harbor, NYC East River/Hudson tunnels, apply regardless of length). ¦¦ DATA HYGIENE: Confidence column is load-bearing. Blog/forum/law-firm sources = good for DISCOVERY, NOT authoritative for numbers. Verify Med/Low-Med rows vs DOT / NPS / Mountain Directory before live warnings. Mountain Directory (R&R Publishing) = definitive grade ref, paid ebooks; facts aren't copyrightable (Feist) so verify-in-our-own-words is clean, but don't copy prose/maps/whole compilation; human-in-the-loop (Benny reads, Claude cross-checks); IP-attorney consult before shipping a paid feature built partly on it. GAP: low-clearance BRIDGES + weight-limited bridges not yet gathered (all free/official sources). ¦¦ Leans harder on Google — see DEVOPS-SPLIT-GOOGLE-KEYS (now more important). HERE demoted: at most a detection/drive-time input, not the router.
FEAT-REROUTE-OPTIONS | Hazard reroute (Version A): when a hazard warns, offer Find a safer route - compute 2-3 real Google alternates between the affected stops, check each against the hazard DB, show clear options as a LIST with trade-offs (extra miles, hazards avoided), user picks one, insert a waypoint stop on the chosen safe road so Google redraws cleanly. Honest when no clear alternate exists. | P1 | In progress - RR55 | Builds on FEAT-HAZARD-DB-ROUTING. Reliable mechanism: tell Google to go THROUGH a curated waypoint (not AVOID a segment). Reroute = add-a-stop on safer road, plan changes honestly. Load-bearing scout: is Google alternate-routes reliable enough to surface genuinely different routes.
FEAT-REROUTE-MAP-LINES | Hazard reroute (Version B, enhancement): draw the 2-3 alternate routes directly on the MAP as colored, clickable polylines simultaneously - pick one on the map, others clear, chosen becomes the route. Visual upgrade to FEAT-REROUTE-OPTIONS Version A. | P3 | Deferred | Future enhancement after Version A ships. NOTE: multi-polyline map rendering is the same code territory as the abandoned HERE line / scribble - build with care, not casually. Only after A proves the feature is worth it.
FR-HAZARD-WARN-VERBOSITY | Hazard warning prose is wordy and duplicated: the full DANGER text prints in the AI chat reply (sometimes twice) AND in the sidebar advisory AND the map pill. Polish: warning detail lives in ONE place (the structured advisory/pill); AI prose acknowledges the hazard in ONE short conversational sentence pointing to it, not the full verbatim block, never repeated. | P3 | Deferred | Cosmetic - warning works, just verbose+repeats. Touches services/ai.ts buildViolationAdvisory + the planner prompt (sensitive code). Do as its own small focused build, NOT bundled with reroute. Single-source-of-truth for warning display.
FEAT-RV-SAFE-ROUTING | Real rig-aware routing — height/length/weight/grade-restricted routes for both the directions links and the server drive-time measurement | P1 | SUPERSEDED by FEAT-HAZARD-DB-ROUTING | RR55 SUPERSEDED: the HERE-as-route-engine plan is abandoned (HERE rerouting unproven; map line never converged). Replaced by FEAT-HAZARD-DB-ROUTING (own hazard DB + honest warnings + Google waypoint-avoidance). Vendor research BELOW retained for reference — still useful if we ever revisit an external router, and the grade-DB conclusion still holds. ¦¦¦ The core product promise, never actually built. Google Directions has no RV/truck mode. Integrate a rig-aware provider (HERE / PTV / Trimble-MapQuest truck routing — Claude to research current options + pricing before Benny picks). Feed rig dims from the Rig profile (already captured, currently display-only). Own focused arc, real cost. Tracks against BUG-ROUTE-NOT-RV-SAFE. Until shipped, honest disclaimers hold the line. Interim stopgap to scope: deterministic per-leg "verify rig restrictions yourself" caveat (server-stamped, never AI-volunteered pass warnings). ¦¦ LOCKED RR54: HERE replaces Google as the drive-time/route engine INSIDE Plan-is-Truth (path+time+overnight all from HERE's RV-safe route, before approval) — not a display swap. AI stays stops-only; Google displays HERE's path via waypoints. Option A (reroute after planning) ruled out as dishonest. Provider = HERE (free tier, ~$2.50/1k). Honest per-leg caveat stays for the park/byway residual gap. ¦¦ RR54 SIDE NOTE (Benny): evaluate Rand McNally RoadIQ as an ALTERNATIVE or COMPLEMENT to HERE for RV routing — Rand McNally has deep RV/truck routing heritage (the RV GPS market, trucker atlas). Worth comparing on: rig-dimension routing quality, GRADE/steep-pass awareness (HERE gap — see FEAT-GRADE-HAZARD-DB), API availability/pricing, coverage. Could be HERE-or-RoadIQ, or HERE-plus-RoadIQ for grade. Park until HERE is battle-tested in real use; do not switch mid-stream. Logged for future evaluation. ¦¦ RR54 RoadIQ FINDING (researched): Rand McNally Road IQ has the BEST RV/truck pedigree + most likely GRADE/steep-pass awareness (their atlas heritage marks grades — the exact HERE gap). BUT it is B2B/ENTERPRISE, not a self-serve dev API: reaches developers only via Platform Science fleet ecosystem partnership; pricing is "Get Pricing" quote-only (almost certainly enterprise minimums + sales cycle); historic API (IntelliRoute) targeted carrier TMS integrations. NOT a realistic near-term swap/add for a solo pre-revenue founder — opposite friction from HERE (no self-serve key, no published price, sales-gated). VERDICT: not now. Only worth a sales conversation LATER, and ONLY for grade data, if grade-aware routing becomes critical enough to justify an enterprise relationship. For the grade gap NOW, the curated dangerous-pass DB (FEAT-GRADE-HAZARD-DB) is the cheaper/realistic path — no vendor, catches Sonora today. ¦¦ RR54 PTV EVALUATION (researched): PTV Logistics (PTV Developer / xServer) is a 40-yr European truck-routing specialist. UNLIKE Rand, it appears SELF-SERVE — developer.myptv.com portal, OpenAPI/REST, free test tier, integratable like HERE was. Truck routing factors size/weight/access-restrictions/toll/rest-times/emissions; deep truck-specific restriction data. TRADEOFFS vs HERE: (+) more accessible than Rand, mature truck data; (-) TWO UNCONFIRMED blockers for us: (1) GRADE — their materials emphasize restrictions/toll/emissions/rest-times but do NOT clearly advertise grade/gradient, so it may NOT solve the Sonora gap either (verify before assuming); (2) US COVERAGE — PTV is EU-centric (tolls across 35 EU countries), US restriction-data depth unverified for a US RV app. Production pricing not public (free test only). VERDICT: more realistic than Rand, but NOT an obvious upgrade over HERE unless US coverage is confirmed strong AND it does grade. Its extra features (EU toll, rest-times, emissions) are fleet-logistics-oriented, low value for a consumer RV-trip planner. If we ever re-evaluate the routing vendor, test PTV in parallel with HERE on US routes; but the curated grade-DB (FEAT-GRADE-HAZARD-DB) remains the right fix for the grade gap regardless of which routing vendor we use. Three vendors now logged: HERE (current, no grade), PTV (self-serve, grade unconfirmed, EU-strong), Rand/RoadIQ (best US/grade pedigree, enterprise-only).
FEAT-MARKET-RIG-AWARE-ROUTING | Advertise rig-aware routing as a selling point (capability-named, disclaimer-paired, no over-claim) | P3 | Deferred | FUTURE / low-priority (Benny RR54 — revisit once HERE routing is proven in real use and we like it). Make rig-aware routing a SELLING POINT. RULES for how to claim it (RR54): (1) market the CAPABILITY not the vendor — "rig-aware routing / we factor in your RV height, length & weight", NOT "Powered by HERE" (consumers do not care which engine + locks us to a swappable vendor). (2) Do NOT over-claim — "rig-aware route guidance" / "routes built for your rig, not a sedan" is defensible; "RV-SAFE routing" / "route around every hazard" recreates the BUG-TIPCARD-FALSE-CLAIM liability. HERE catches LEGAL/posted restrictions, not grade safety or every park-road limit, and can return flagged-but-violating routes. (3) MUST ship paired with the liability disclaimer (FEAT-ROUTING-REQUIRED-DIMS-DISCLAIMER) — "we give rig-aware guidance" + "you verify clearance/weight/grade yourself" are two sides of one coin. Copy in LandingPage.tsx (existing rig-compat bullets there = campground FIT, separate). Park until the engine is battle-tested.
FR-WINBACK | Cancelled-customer export for win-back | P3 | Deferred | Gated on FR-MARKETING-OPTIN (no opt-in basis today).
FR-RIG-SPEC-AUTOFILL | Pick RV make/model/year → autofill specs | P3 | Deferred | Hybrid recommended: curated common-rig set + per-class defaults + manual override. No clean free RV spec DB exists; build curated, grow over time. ¦¦ RR54 update: decided shape = CURATED common-rig picker (~100-200 popular rigs, hand-verified specs) → autofills length/height/GVWR/fuel/MPG/tank, user CONFIRMS/corrects. NOT a universal "type any vehicle, pull everything" search — no clean/free RV spec DB exists, and auto-pulled GVWR that is wrong UNDER-states weight = the dangerous routing direction. Degrade gracefully: not on list → manual + type-based fallback estimate. The fallback ladder (FEAT-ROUTING-REQUIRED-DIMS-DISCLAIMER) already solves "HERE fires on incomplete data" without any dataset, so autofill is convenience-only. DEFER until core routing engine + disclaimers + map-waypoint display are all shipped to prod — do not pull focus from finishing the engine.
FR-ROUTE-HWYPREF-1 | Rig-aware “prefer major highways / 4-lane” routing preference | P3 | Deferred | Post-launch, low severity.
FR-SCOPE-HUMOR-1 | Scope-guard tone improvement with on-brand deflection | P3 | Deferred | A/B test before shipping.
FR-FEEDBACK-NOTIFY | 5th dev@ alert on feedback submission | P3 | Deferred | Scoped, not built.
JOURNAL-LOCATION | Optional place picker on freeform journal entries (pin stopless entries) | P3 | Deferred | Reuse AddressAutocomplete in AddEntryModal; columns exist from step 7; needs scout.
MOBILE-CHAT-INPUT | Chat input off-screen when keyboard opens (mobile) | P3 | Deferred | Pre-existing (baseline bf89b0a). Fix = visualViewport listener to lift input. Measure-first. Not pushed.
PLAN-IS-TRUTH-PART2 | Real Google drive-time check DURING planning — transit stops appear in the approved plan + AI explains them honestly | — | Shipped | RR52 COMPLETE. Server measures real Google drive times during planning + is sole transit-stop inserter; AI stopped fabricating compliance; honest grounded notes (planning + modify); every stop-mutation path funnels through recheckLongLegs; keep-long-drive confirm modal; ack on Trip column. Built + merged local main. NOT pushed/deployed.
FR-MARKETING-OPTIN | Marketing opt-in popup after signup | P2 | Shipped | RR53 SHIPPED + DEPLOYED. Opt-in modal at onboarding (unchecked default, Option A: Save records checkbox state — no unaffirmed consent; warm copy, no "marketing" in user-facing text). marketingConsent + marketingConsentAt columns (migration 20260626120000, applied local via Docker-psql workaround + prod via Render auto-deploy). PATCH /users/me/marketing-consent (exempt from verified-email gate — fires pre-verification). Profile toggle (in-app opt-out). Owner-gated /admin/marketing-subscribers list + CSV (both client OwnerRoute + server requireOwner). UNSUBSCRIBE email-link not built — required when campaign-sending starts (FR-WINBACK era). Pushed + live.
FR-TIME-INPUT-PICKER | Scrolling time picker (AM/PM) replacing free-text time field | P3 | Shipped | Root-cause cure for the PDF time crash. Standardized input.
RIG-CHANGE | Full rig-change feature: trip-page selector + larger-rig warning + per-stop “booked for [rig]” + AI modify action | — | Shipped | All routed through one guarded swap path. Migration: 7 bookedForRig* cols. Dev-tested. Pushed, not yet deployed to prod.
STOP-GEO-RESLOT | Geo-reslot modify-added stops + booked-stop date-shift modal + originalBookedDate record | — | Shipped | Server geocode + min-detour reslot; center-screen modal; backfill done. Pushed.
STAY-CARD-TRUE-WINDOW | Itinerary stay card shows true booked window (nights + arrival→checkout); PDF matches | — | Shipped | Display-only (Option 1). Pushed.
NIGHTS-CONVERSION | Align modify days→nights with planning + explicit date-range rule | — | Shipped | Pushed. Fresh-thread test pending.
KEEP-LONG-DRIVE | User opt-in to drive an over-cap leg: confirm modal on overnight delete, ack persists, no nag | — | Shipped | Reused ConfirmModal. 'Remove this overnight stop?' wording, danger button. Ack on Trip.acknowledgedLongLegs (migration applied). Local main, not pushed.

## Launch Status
RoamReady.ai — Launch Status
Snapshot of LAUNCH_STATUS.md (repo root = source of truth). Updated RR55.
Item | Status | Category | Notes
RV-safe routing (core promise) — RR55 pivot | WARNING LAYER LIVE — reroute next | Launch-critical | RR55: hazard DB + warnings SHIPPED. Owned hazard database, rig-gated warnings on planning + map pages. Restrictions live on PROD. Reroute (Find a safer route) is the next build - scout pending.
RR54 client fixes (honest tip-card + account-menu email) | COMMITTED, PENDING PUSH | Deploy pending | Both client-only, on local main (ahead of origin by 2). One save-progress.bat push ships both → deploys roamready-client only (no server, no migration). The tip-card fix should go tonight — pulls the false RV-safe-routing claim off live prod.
Site live at roamready.ai | LIVE | Launch | Real Stripe payments, DNS cutover complete, Render deployed.
PDF time-crash fix | DEPLOYED | Prod fix | Live on roamready-client (Cindy’s PDF works).
RR51 batch (rig, stop-sequence, nights, stay-card) | PUSHED, NOT DEPLOYED | Deploy pending | On GitHub. Deploy needs BOTH roamready-api (server) and roamready-client (client). Deliberate step.
Plan-is-Truth Part 1 | PUSHED, NOT DEPLOYED | Deploy pending | Built + merged to local main and pushed to origin. Not deployed to prod. Drive-time net OFF until Part 2.
Plan-is-Truth Part 2 | DEPLOYED | Push pending | RR53: structural pre-build budget fix (app owns minimum, deterministic shape) shipped + pushed; prod migrations current (45 found, up to date).
Marketing opt-in (FR-MARKETING-OPTIN) | DEPLOYED | Feature | RR53. Consent capture + modal + admin subscriber list. Schema migration 20260626120000 applied to prod (Render auto-deploy on push). Live on roamready.ai.
HERE routing stack (detection + advisory UI + GVWR + abandoned line) | PUSHED — dormant (flags off) | Deploy/decision pending | RR55: HERE stack pushed to prod, line dormant behind VITE_USE_HERE_ROUTING (absent on prod client = off). Detection separable, off by default. Decision resolved - leave dormant, superseded by hazard DB.

## Grade Hazards (West)
ID | Pass / Road | Route | State | Region | Peak Grade | Severity Tier | Length/Vehicle Limit | Confidence | Warning Message (draft) | Source(s)
GH-W-001 | Sonora Pass | CA-108 | CA | Sierra Nevada | ~26% | 3 - DANGEROUS | Vehicles >25 ft & trailers NOT recommended | High (grade widely cited 26%; verify coords) | DANGER: Sonora Pass (CA-108) reaches ~26% grade with tight switchbacks. NOT recommended for vehicles over 25 ft. Your rig should avoid this pass — seek an alternate route. | rvlife.com; sierramountainpasses.com; matadornetwork; komoot
GH-W-002 | Ebbetts Pass | CA-4 | CA | Sierra Nevada | ~23-25% | 3 - DANGEROUS | <2 lanes wide in places; 28 ft+ alt-route signs | High | DANGER: Ebbetts Pass (CA-4) hits ~23-25% grade, is under 2 lanes wide in spots with hairpins. Signs advise vehicles over 28 ft find an alternate route. Avoid in a large rig. | rvlife.com; escapeforum; komoot; sierramountainpasses
GH-W-003 | Tioga Pass | CA-120 | CA | Sierra Nevada | Steep but more evenly graded | 2 - CAUTION | Open seasonally (Yosemite) | Med (grade % not pinned — verify) | CAUTION: Tioga Pass (CA-120) is a high, steep Sierra crossing. More evenly graded than Sonora/Ebbetts but still demands low gear and engine braking. Seasonal closure Nov-May. | sierramountainpasses; matadornetwork
GH-W-004 | CA-3 Callahan to Trinity River | CA-3 | CA | Klamath/Trinity | 7%+ | 2 - CAUTION | No shoulder, several-hundred-ft drop-offs | Low-Med (anecdotal 7%+; verify) | CAUTION: CA-3 between Callahan and the Trinity River is steep (7%+), twisting, with no shoulder and big drop-offs. Demanding for a large rig. | rvlife.com (user report)
GH-W-005 | Tehachapi Pass | CA-58 | CA | S. Sierra/Tehachapi | Long sustained grade (~4,000 ft summit) | 2 - CAUTION | Very heavy truck traffic | Low-Med (grade % not pinned) | CAUTION: CA-58 over Tehachapi has a long sustained ascent/descent and heavy truck traffic. Use low gear; watch brake temps on the long downgrade. | tripadvisor; rvlife
GH-W-006 | Million Dollar Hwy / Red Mountain Pass | US-550 | CO | San Juan Mtns | ~8-9% | 2 - CAUTION | No guardrails; ~40 accidents/7 deaths a year | High (8-9% well documented) | CAUTION: US-550 (Million Dollar Highway / Red Mountain Pass) runs ~8-9% with sheer drop-offs and NO guardrails. Narrow and notoriously dangerous. Drive northbound to stay off the cliff edge; use engine braking. | uncovercolorado; denvergazette; kekbfm; interstatesignways
GH-W-007 | Independence Pass | CO-82 | CO | Sawatch Range | 6.5% | 3 - DANGEROUS (length) | NO vehicles over 35 ft — strictly prohibited | High (35-ft limit confirmed multiple) | DANGER: Independence Pass (CO-82) bans ALL vehicles over 35 ft. Your coach exceeds this limit — do NOT take this pass. Narrow, one-lane sections with steep drop-offs. | dangerousroads.org; denvergazette; rectorlawfirm
GH-W-008 | Pikes Peak Highway | Pikes Peak Hwy | CO | Front Range | 12%+ | 3 - DANGEROUS | Toll road; summit 14,115 ft | Med (12%+ cited; verify segment) | DANGER: Pikes Peak Highway has sections over 12% grade climbing to 14,115 ft. Severe brake-overheating risk on descent. Not advised for a large motorhome. | kekbfm (12%+ running slope)
GH-W-009 | Grand Mesa Scenic Byway | CO-65 | CO | Grand Mesa | 10-12% | 3 - DANGEROUS | Cedaredge to summit segment | Med (10-12% cited; verify) | DANGER: Grand Mesa Byway (CO-65) reaches 10-12% between Cedaredge and the summit — among the steepest paved grades on the Western Slope. Large rigs should reconsider. | kekbfm
GH-W-010 | Slumgullion Pass | CO-149 | CO | San Juan/Rio Grande | ~9.5% | 2 - CAUTION | CO steepest paved road | High (9.5% widely cited) | CAUTION: Slumgullion Pass (CO-149) is ~9.5% — Colorado’s steepest paved road. Sustained grade; use low gear and watch brake heat. | matadornetwork; kekbfm
GH-W-011 | Wolf Creek Pass | US-160 | CO | San Juan Mtns | ~6.8-7% | 2 - CAUTION | Summit 10,857 ft; runaway ramps | Med (verify exact %) | CAUTION: Wolf Creek Pass (US-160) is a long ~7% grade with runaway truck ramps and frequent winter hazards. Low gear and engine braking on the descent. | denvergazette; metierlaw (verify %)
GH-W-012 | Vail Pass | I-70 | CO | Gore Range | ~7% | 2 - CAUTION | Interstate; ski traffic, weather | Med | CAUTION: Vail Pass (I-70) runs up to ~7% at 10,666 ft. An interstate but still a real grade — heavy weather and ski traffic add risk. Use engine braking. | denvergazette
GH-W-013 | Loveland Pass | US-6 | CO | Front Range | ~6.7% | 2 - CAUTION | 11,990 ft; hazmat detour route, no guardrails | Med (verify %) | CAUTION: Loveland Pass (US-6) climbs to 11,990 ft with sharp curves and little guardrail; it is the detour when Eisenhower Tunnel closes. High-profile vehicles like RVs need real caution. | metierlaw
GH-W-014 | US-14 Bighorn / Granite Pass | US-14 | WY | Bighorn Mtns | avg ~10%, peak ~13.5% | 3 - DANGEROUS | Summit 9,430 ft; semis avoid | High (10%/13.5% cited multiple) | DANGER: US-14 over the Bighorns averages ~10% and peaks near 13.5% — semis avoid it entirely. Severe for a large RV. Strongly consider an alternate route. | matadornetwork; rvlife
GH-W-015 | Teton Pass | WY-22 | WY | Teton Range | 10% | 3 - DANGEROUS | 10% both sides; 60,000 lb weight limit; trailers banned in winter | High (10%/60k lb from Mountain Directory) | DANGER: Teton Pass (WY-22) is a sustained 10% grade on BOTH sides (eases to 6-7% lower down), peaks 8,429 ft, with a posted 60,000 lb weight limit and runaway ramps that require crossing oncoming traffic. Trailers banned in winter. Demanding/dangerous for a heavy coach — the Hwy 26/89 via Alpine is the safer alternate. | mountaindirectory; bookoutdoors; arrowtruck
GH-W-016 | I-84 Cabbage Hill / Emigrant Hill | I-84 | OR | Blue Mtns | 6% | 2 - CAUTION (deadly) | Gains 2,000 ft in 6 mi; sharp turns | High (6% confirmed; ODOT project) | CAUTION: I-84 Cabbage Hill gains 2,000 ft in 6 miles at 6%. An Oregon highway patrol officer reported a motorhome a WEEK burns climbing it in summer. Manage engine/transmission heat carefully both directions. | theashlandchronicle; mountaindirectory
GH-W-017 | UT-143 | UT-143 | UT | Dixie NF / Cedar Breaks | 13%+ | 3 - DANGEROUS | Large trucks avoid (brake-fire risk) | High (13%+ cited) | DANGER: UT-143 reaches over 13% climbing toward the ski resort; trucks avoid it to keep brakes from catching fire. Not advised for a large motorhome. | matadornetwork
GH-W-018 | UT-12 (Boulder Mtn / Hogback) | UT-12 | UT | Dixie NF / Escalante | Steep + hairpins, narrow Hogback | 2 - CAUTION | Narrow spine ("Hogback") w/ drop-offs both sides | Low-Med (grade % not pinned) | CAUTION: UT-12 is hairpin-heavy with the narrow "Hogback" section dropping off both sides. Doable but white-knuckle with a trailer/large rig — UT-24 is the calmer alternate. | rvlife (user reports)
GH-W-019 | Moki Dugway | UT-261 | UT | Cedar Mesa | ~10%+ gravel switchbacks | 3 - DANGEROUS | Unpaved graded switchbacks; large rigs avoid | High (well-known hazard) | DANGER: Moki Dugway (UT-261) is a series of steep UNPAVED switchbacks carved into a cliff. Large RVs and trailers should not attempt it — use the paved alternate. | rvlife (multiple reports)
GH-W-020 | US-89 Yarnell Hill | US-89 | AZ | Weaver Mtns | Steep switchbacks | 2 - CAUTION | "Large rigs not allowed" sign now posted | Med (grade % not pinned) | CAUTION: US-89 over Yarnell Hill (Prescott Valley toward Congress) has tight switchbacks; signage now warns large rigs. Many RVers route around via Phoenix. | rvtravel.com
GH-W-021 | Apache Trail | AZ-88 | AZ | Superstition Mtns | N/A (dirt, 1-lane) | 3 - DANGEROUS | Gravel/dirt, sometimes one lane | High (well-known no-go) | DANGER: AZ-88 (Apache Trail) between Tortilla Flat and Roosevelt Lake is winding gravel/dirt, sometimes a single lane. Do NOT attempt in a big rig. | rvlife; rvtravel
GH-W-022 | US-2 Stevens Pass | US-2 | WA | Cascades | Long steep grade (~6%+) | 2 - CAUTION | Winding 2-lane; limited pullouts | Low-Med (verify %) | CAUTION: US-2 over Stevens Pass has a long steep grade and winding 2-lane sections with few pullouts. I-90 is the lower-stress alternate for large rigs. | escapeforum; rvlife (user reports)
GH-W-023 | Beartooth Highway | US-212 | WY/MT | Beartooth Mtns | Steep + switchbacks | 3 - DANGEROUS (length) | Vehicles over 40 ft PROHIBITED (posted) | High (40-ft ban + RVer accounts) | DANGER: Beartooth Highway (US-212) posts a 40-ft vehicle prohibition — your 42-ft coach is over the limit. Relentless switchbacks and steep grades to ~10,947 ft; an RVer reported a 6-hour descent and a $900 brake job. Do NOT take this in a big rig. Stunning, but make it a towed-vehicle day trip. | rvlife.com; bookoutdoors; irv2
GH-W-024 | Cajon Pass | I-15 | CA | San Bernardino Mtns | 6% for ~4 mi (southbound) | 2 - CAUTION | 12-mi downgrade; truck speed 45; runaway ramp | High (6% from Mountain Directory) | CAUTION: Cajon Pass (I-15 south of Victorville) descends ~6% with a 12-mile downgrade, 45 mph truck limit, and a runaway ramp. Heavy truck traffic. Low gear and engine braking — watch brake temps the whole way down. | mountaindirectory
GH-W-025 | Baker Grade | I-15 | CA | Mojave Desert | Long sustained grade | 2 - CAUTION | Long descent toward NV; brake-fade risk | Med (length-driven; verify %) | CAUTION: The Baker Grade (I-15 near Baker, toward the NV line) is a long sustained downgrade where buses and trucks are known to lose brakes. Not super steep but LONG — the danger is brake fade from length. Keep speed down, use engine braking. | truckersreport; mountaindirectory (verify %)
GH-W-026 | In-Ko-Pah Grade | I-8 | CA | Jacumba Mtns | Steep + long (eastbound) | 2 - CAUTION | Long steep descent San Diego toward Yuma | Med (verify %) | CAUTION: I-8 east of San Diego (In-Ko-Pah / Mountain Springs grade toward the desert) is steep AND long on the eastbound descent. Brake-fade risk from sustained length. Low gear, engine braking, watch temps. | truckersreport (verify %)
GH-W-027 | Lewiston Grade | US-95 | ID | Lewiston / Clearwater | ~7% (old grade steeper) | 2 - CAUTION | Long descent into Lewiston; runaway ramp | Med (7% cited; verify) | CAUTION: The Lewiston Grade (US-95 into Lewiston, ID) is a long ~7% descent with a runaway truck ramp at the bottom. Manage brake heat on the way down; the old grade is steeper still and best avoided. | truckersreport; idahoitd (verify %)
GH-W-028 | Snowy Range Scenic Byway | WY-130 | WY | Medicine Bow Mtns | ~7% with sharp curves | 2 - CAUTION | High alpine; seasonal closure | Med (7% from RVer; verify) | CAUTION: WY-130 (Snowy Range Scenic Byway) runs ~7% with sharp 25 mph curves that force heavy braking even at moderate grade, climbing above 10,000 ft. Seasonal. Low gear and patience on the descent. | cheaprvliving (RVer report)
GH-W-029 | CA-49 (Sierra foothills) | CA-49 | CA | Sierra foothills | Steep, twisting, brake-cooking | 2 - CAUTION | Narrow, winding gold-country route | Low-Med (anecdotal; verify %) | CAUTION: CA-49 through the Sierra foothills is steep, narrow, and relentlessly twisting — RVers report cooked brakes and white-knuckle descents in 40-ft motorhomes. Verify a calmer alternate before routing a big rig here. | rvlife.com (multiple RVer reports)

## Grade Hazards (East)
ID | Pass / Road | Route | State | Region | Peak Grade | Severity Tier | Length/Vehicle Limit | Confidence | Warning Message (draft) | Source(s)
GH-E-001 | Smugglers’ Notch | VT-108 | VT | Green Mtns | Steep + single-lane hairpins | 3 - DANGEROUS (length) | Single vehicles >40 ft PROHIBITED by law (23 VSA §1006b) | High (statute confirmed) | DANGER: Smugglers’ Notch (VT-108) legally bans single vehicles over 40 ft. Your 42-ft coach is PROHIBITED — do NOT take this road. Single-lane hairpins around boulders; trucks get stuck yearly. As of July 1, 2026 the fine rises to $10,000 (up to $20,000 if stuck). Seasonal closure mid-Oct to mid-May. Use the Rte 15 / Rte 100 detour. | vtrans.vermont.gov; legislature.vermont.gov; rideapart; vermontbiz
GH-E-002 | Tail of the Dragon | US-129 | TN/NC | Smoky Mtns | Steep + 318 curves in 11 mi | 3 - DANGEROUS (length) | Signs restrict vehicles over 30 ft; 30 mph limit | High (well documented) | DANGER: Tail of the Dragon (US-129) at Deals Gap has 318 curves in 11 miles with signs restricting vehicles over 30 ft. A notorious motorcycle/sports-car road — do NOT drive a large RV or towed setup here. Use I-40 / Foothills Parkway instead. | rvlife.com; upack; wkfirm; outsideonline
GH-E-003 | US-441 Newfound Gap | US-441 | TN/NC | Great Smoky Mtns NP | Sustained mountain grade | 2 - CAUTION | Through GSMNP; scenic but demanding | Med (grade % not pinned) | CAUTION: US-441 (Newfound Gap Rd) from Cherokee NC to Gatlinburg TN climbs through the Smokies with sustained grades and curves. Doable but demanding in a large motorhome — low gear and engine braking; many RVers route around. | rvlife.com (user reports)
GH-E-004 | Clingmans Dome Road | Clingmans Dome Rd | TN/NC | Great Smoky Mtns NP | Steep incline + sharp curves | 2 - CAUTION | Dead-end spur to highest point in GSMNP | Med (grade % not pinned) | CAUTION: Clingmans Dome Road is a steep, narrow, sharply-curving spur to the highest point in the Smokies. Tight for a large rig; consider leaving the coach below and taking the towed vehicle. | wkfirm; queenerlaw; borenandboyd
GH-E-005 | Monteagle Mountain | I-24 | TN | Cumberland Plateau | 6% for ~3 mi (eastbound) | 2 - CAUTION | Brake-check stops; reduced truck speed limit | High (6%/3mi from trucker source) | CAUTION: Monteagle Mountain (I-24) is 6% for ~3 miles eastbound — one of the steepest grades on the Interstate system, with brake-check stops and reduced truck speed limits. Use low gear and engine braking; watch brake temps. | overdriveonline (Killer Hills); borenandboyd
GH-E-006 | Fancy Gap | I-77 | VA | Blue Ridge | ~7% for ~7 mi | 2 - CAUTION | NC weigh scales at the bottom | High (7%/7mi from trucker source) | CAUTION: Fancy Gap (I-77) just past the NC line is a long ~7% grade for about 7 miles — long, steep, and curvy downhill. Notorious for fog and pile-ups. Low gear, engine braking, watch brake temps the whole way down. | overdriveonline (Killer Hills)
GH-E-007 | Black Mountain | I-40 | NC | Blue Ridge | 4-5% (long sustained) | 1 - HEADS UP | Brake-check stops; reduced truck speed limit | High (4-5% from trucker source) | HEADS UP: Black Mountain (I-40, Old Fort grade) is a long sustained 4-5% — not the steepest, but the length cooks brakes. Brake-check stops and reduced truck speed limits. Descend in low gear with engine braking. | overdriveonline (Killer Hills)
GH-E-008 | PA-487 Red Rock Mountain | PA-487 | PA | Allegheny / Ricketts Glen | 12.5%, peak ~14.5% | 3 - DANGEROUS | Steep switchbacks near Ricketts Glen SP | High (12.5%/14.5% cited) | DANGER: PA-487 south of Ricketts Glen reaches 12.5% with a steepest pitch near 14.5% — one of the steepest grades in the East. Treacherous switchbacks. Large rigs should seek an alternate route. | matadornetwork
GH-E-009 | US-33 Shenandoah Mtn / Seneca Rocks | US-33 | WV | Allegheny Mtns | West side ~9% (4.5 mi); east ~8% (2.5 mi) | 3 - DANGEROUS | Two-lane both sides; 25 mph curves | High (9%/8% from trucker source) | DANGER: US-33 over the WV mountains runs ~9% for 4.5 miles on the west side and ~8% for 2.5 miles on the east, with continuous sharp curves and 25 mph hairpins. Steep two-lane with little margin — demanding/dangerous for a large coach. | trucksontriangles; ids-water
GH-E-011 | Kancamagus Highway | NH-112 | NH | White Mtns | Sustained ~ steep mountain grade | 2 - CAUTION | Scenic byway; no services 35 mi; steep near pass | Med (grade % not pinned) | CAUTION: The Kancamagus Highway (NH-112) climbs to ~2,855 ft with sustained grades and curves through the White Mountains, no services for ~35 miles. Manageable for many RVs with care, but use low gear on the descent and watch brake heat. | tripadvisor (verify grade %)
GH-E-012 | Mount Washington Auto Road | Mt Washington Auto Rd | NH | White Mtns | avg ~12% (private toll) | 3 - DANGEROUS | Private toll road; trailers/large RVs prohibited | High (avg 12% well documented) | DANGER: The Mount Washington Auto Road averages ~12% over 7.6 miles to the summit (6,288 ft), with no guardrails and extreme weather. Trailers and large RVs are prohibited. Do NOT take a big coach — not a through route anyway. | widely documented (verify specifics)
GH-E-013 | WV Route 50 (Mt Storm–Gormania) | WV/US-50 | WV | Allegheny Mtns | Steep, winding, drop-offs | 2 - CAUTION | Narrow, mountainous east of Clarksburg | Low-Med (grade % not pinned) | CAUTION: US-50 between Mt. Storm and Gormania, WV is steep, winding, and narrow with drop-offs — hard work even in a car. Consider the I-68/I-79 route instead in a large rig. | rvlife.com (user reports)
GH-E-014 | Sandstone Mountain | I-64 | WV | Allegheny Mtns | 7% for 7 mi (eastbound) | 2 - CAUTION | 2 escape ramps; auto truck-weigh speed advisory | High (7%/7mi, Wikipedia/WVDOT) | CAUTION: I-64 eastbound at Sandstone Mountain, WV is a 7% grade for 7 miles — escape ramps used so often the state installed an automatic truck-weighing speed-advisory system. Long and steep; low gear and engine braking the whole way, watch brake temps. | en.wikipedia I-64 WV; truckersreport; crashforensics
GH-E-015 | Big Savage Mountain | I-68 | MD | Allegheny Mtns | 6% for ~13 mi | 2 - CAUTION | One of the longest grades in the East | High (6%/13mi from trucker sources) | CAUTION: I-68 in western Maryland (Big Savage / Cumberland area) runs 6% for about 13 miles — one of the LONGEST sustained grades in the East. The danger is length, not steepness: brakes fade over 13 miles. Keep speed down, engine brake, consider the toll-road alternate. | mountaindirectory; truckersreport
GH-E-016 | NC-181 Blue Ridge descent | NC-181 | NC | Blue Ridge | 6-10% for 11 mi (much 8-9%) | 3 - DANGEROUS | Long, varies 6-10% | High (Mountain Directory East) | DANGER: NC-181 where it crosses the Blue Ridge Parkway has an 11-mile southbound descent varying 6-10%, much of it 8-9%. Just as hazardous as Western grades. Long gear-down descent — large rigs should consider an alternate. | mountaindirectory
GH-E-017 | Sams Gap | I-26 | NC/TN | Blue Ridge | Long steep descent (WB) | 2 - CAUTION | Long brake-cooking descent NC into TN | Med (length-driven; verify %) | CAUTION: I-26 westbound from NC into TN (Sams Gap) is a long, steep descent truckers single out as a brake-burner. Length is the hazard. Low gear, engine braking, keep speed down. | truckersreport (verify %)
GH-E-018 | US-64 Ocoee Gorge | US-64 | TN/NC | Cherokee NF | Steep + switchbacks | 2 - CAUTION | Narrow, winding along Ocoee River | Low-Med (grade % not pinned) | CAUTION: US-64 from Cleveland TN to Franklin NC along the Ocoee River is steep, narrow, and switchback-heavy with "oncoming traffic may cross center line" signs — white-knuckle for a 35 ft+ motorhome towing. Verify a calmer alternate. | rvlife.com (user reports)
GH-E-019 | PA-125 | PA-125 | PA | Appalachians | Steep grade (large vehicles avoid) | 2 - CAUTION | 18-mi section; large vehicles advised to avoid | Med (Mountain Directory East) | CAUTION: PA-125 between Shamokin and Good Spring is an 18-mile section the Mountain Directory flags for large vehicles to avoid — steep with sustained grade. Seek an alternate in a big rig. | mountaindirectory
GH-E-020 | TX-170 "Big Hill" | TX-170 / FM 170 | TX | Big Bend | 15% | 3 - DANGEROUS | Cliffside curve at bottom of long steep hill | High (15% widely cited) | DANGER: TX-170 (FM 170) in Big Bend reaches a 15% grade — "the Big Hill" — with a cliffside curve at the bottom. Warning signs ~40 mi out. Low gear, engine braking, manual trailer braking required. Demanding/dangerous for a large rig; no easy alternate. | rvtravel.com; matadornetwork

## Restrictions
ID | Road / Feature | Route | State | Restriction Type | Limit | Affects 42-ft coach? | Confidence | Warning Message (draft) | Source(s)
RS-001 | Going-to-the-Sun Road | GTSR | MT | Length + Width/Height | Over 21 ft long (incl bumpers), 8 ft wide (incl mirrors), or 10 ft tall PROHIBITED at Logan Pass | YES - banned | High (NPS official) | RESTRICTED: Going-to-the-Sun Road (Glacier NP) bans vehicles over 21 ft long, 10 ft wide (incl mirrors), or 10 ft tall. Your 42-ft coach is PROHIBITED. Park the rig and take the shuttle or a smaller vehicle. | coach-net; rvlife; NPS
RS-002 | Smugglers’ Notch | VT-108 | VT | Length (legal) | Single vehicles over 40 ft PROHIBITED (23 VSA §1006b) | YES - banned | High (statute) | RESTRICTED: Smugglers’ Notch (VT-108) legally bans single vehicles over 40 ft. Your 42-ft coach is PROHIBITED — fine rises to $10,000 on July 1, 2026. Use the Rte 15 / Rte 100 detour. | legislature.vermont.gov; vtrans
RS-003 | Tail of the Dragon | US-129 | TN/NC | Length | Signs restrict vehicles over 30 ft | YES - restricted | High | RESTRICTED: Tail of the Dragon (US-129) posts restrictions for vehicles over 30 ft — 318 curves in 11 miles. Your coach should not attempt it. Use I-40 / Foothills Parkway. | rvlife; upack
RS-004 | Independence Pass | CO-82 | CO | Length | No vehicles over 35 ft | YES - banned | High | RESTRICTED: Independence Pass (CO-82) bans all vehicles over 35 ft. Your 42-ft coach is PROHIBITED. Narrows to ~11 ft wide in spots. Use US-24 / I-70 alternate. | dangerousroads; familyroadtrip
RS-005 | Beartooth Highway | US-212 | WY/MT | Length | Vehicles over 40 ft prohibited (posted) | YES - banned | High | RESTRICTED: Beartooth Highway (US-212) posts a 40-ft vehicle limit. Your 42-ft coach is over it. Make it a towed-vehicle day trip instead. | rvlife; bookoutdoors
RS-006 | Needles Highway | SD-87 | SD | Width/Tunnel | Narrow tunnels (~8 ft wide / ~11-12 ft high); RVs discouraged | YES - cannot fit | High (well documented) | RESTRICTED: Needles Highway (SD-87, Custer SP) has rock tunnels as narrow as ~8 ft and low clearance — RVs of any length are discouraged and large coaches physically cannot fit. Take a smaller vehicle. | rvlife (verify tunnel dims)
RS-007 | Iron Mountain Road | US-16A | SD | Width/Tunnel | Narrow tunnels (~ low clearance, pigtail bridges) | YES - cannot fit | Med (verify dims) | RESTRICTED: Iron Mountain Road (US-16A, Black Hills) has narrow tunnels and tight pigtail bridges sized for cars — large RVs cannot pass. Verify tunnel dimensions; take the towed vehicle. | general Black Hills refs (verify)
RS-008 | Mount Washington Auto Road | Auto Rd | NH | Vehicle type | Trailers and large RVs prohibited (private toll) | YES - prohibited | High | RESTRICTED: The Mount Washington Auto Road bans trailers and large RVs (avg ~12% to 6,288 ft, no guardrails). Not a through route. Do not take the coach. | widely documented (verify)
RS-009 | Cherohala Skyway | TN-165/NC-143 | TN/NC | Advisory | Steep, high, limited services; large rigs cautioned | Likely - caution | Low-Med | ADVISORY: Cherohala Skyway is a high, steep, remote byway with limited services; doable for some RVs with care but large coaches should plan fuel/brakes and verify. Not a hard ban. | general refs (verify)
RS-010 | Whiteface Mountain Veterans Memorial Hwy | NY-431 | NY | Advisory/Toll | Steep toll road to summit; large RVs cautioned | Likely - caution | Low-Med | ADVISORY: NY-431 up Whiteface Mountain is a steep dead-end toll road to the summit; large RVs should reconsider. Verify before driving. | general refs (verify)
RS-011 | Natchez Trace Parkway | Natchez Trace | MS/AL/TN | Length / vehicle type | Trailers limited to 32 ft; commercial vehicles prohibited | Possibly (verify motorhome rule) | High (32-ft trailer limit) | RESTRICTED: The Natchez Trace Parkway limits trailers to 32 ft and bans commercial vehicles. Verify motorhome length rules for your route before driving. | coach-net
RS-012 | NJ Garden State Parkway | GSP | NJ | Length | Maximum vehicle length 55 ft | No (42 ft OK) - but verify | High | INFO: NJ Garden State Parkway has a 55-ft max length. Your 42-ft coach is under it, but the southern parkway has low inner/outer-lane clearances — stay in the correct lanes. | coach-net
RS-013 | Taconic State Parkway | Taconic | NY | Vehicle type / height | Motorhomes AND trailers prohibited; ~9 ft low bridges | YES - prohibited | High | RESTRICTED: The Taconic State Parkway prohibits motorhomes and trailers, with bridges as low as ~9 ft. Do NOT route your coach here — use I-84/I-87 instead. | godownsize; rvforum; coach-net
RS-014 | Merritt / Wilbur Cross Pkwy | CT-15 | CT | Height / vehicle type | RVs over 8 ft tall not allowed; trailers prohibited | YES - prohibited | High | RESTRICTED: CT’s Merritt and Wilbur Cross Parkways bar RVs over 8 ft tall and prohibit trailers (old, low stone overpasses). Your coach cannot use these — take I-95 or I-91. | godownsize; coach-net; rvforum
RS-015 | NYC Parkways (Hutchinson, Saw Mill, etc.) | Various | NY | Vehicle type / height | No commercial vehicles/trucks; low parkway bridges | YES - prohibited | High | RESTRICTED: Downstate NY parkways (Hutchinson River, Saw Mill, etc.) ban commercial vehicles/trucks and have very low bridges. Keep your coach on the interstates through the NYC area. | nyc.gov; rvforum
RS-016 | Baltimore Harbor & Ft McHenry Tunnels | I-895 / I-95 | MD | Propane / width | Propane prohibited; tunnels ~8 ft wide / 13’06” high | YES - propane ban | High (MDTA) | RESTRICTED: The I-95 (Fort McHenry) and I-895 (Harbor) tunnels under Baltimore prohibit propane and are only ~8 ft wide. Your motorhome’s LP tank means you must detour via the Francis Scott Key Bridge / I-695. | rvblogger; godownsize; rvforum
RS-017 | Boston Harbor Tunnels | I-90/I-93 | MA | Propane | Propane prohibited (Sumner, Callahan, Ted Williams, etc.) | YES - propane ban | High | RESTRICTED: All Boston Harbor tunnels (Sumner, Callahan, Ted Williams, Prudential, Dewey Sq) prohibit propane. With an RV LP tank, route around — do not enter these tunnels. | rvblogger; coach-net
RS-018 | NYC East River / Hudson Tunnels | Holland/Lincoln/Bklyn-Battery/Queens-Midtown | NY/NJ | Propane | Propane prohibited; lower-level GWB & Verrazano too | YES - propane ban | High | RESTRICTED: The Holland, Lincoln, Brooklyn-Battery, and Queens-Midtown tunnels (plus lower-level GWB and Verrazano) prohibit propane. With an LP tank, avoid these crossings — use an approved upper-level or bridge route. | rvblogger; coach-net
RS-019 | Cumberland Gap Tunnel | US-25E | KY/TN | Propane / hazmat | LP gas / hazmat restricted | YES - verify | Med | RESTRICTED: The US-25E Cumberland Gap Tunnel between KY and TN restricts LP gas/hazmat. Verify the current rule and alternate before routing your coach through. | rvblogger (verify)
RS-020 | Hampton Roads / Chesapeake Bay Bridge-Tunnels | I-64 / US-13 | VA | Propane (inspection) | LP allowed if tanks shut off + inspected (max two 45-lb / 200 lb) | Allowed w/ shutoff | High | INFO: The Hampton Roads, Chesapeake Bay, and Norfolk-Portsmouth bridge-tunnels ALLOW propane if tanks are shut off and pass inspection (max two 45-lb tanks / 200 lb). Stop at the inspection station; turn LP off. | coach-net; rvblogger