## Tracker
ID | Item | Type | Area | Proposed Priority | Status | Verify vs current code? | Source | Notes / What remains
LB-1 | PDF lazy-loading — @react-pdf/renderer code-split out of main bundle | Perf | Build/Bundle | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #1 | react-pdf lands in own chunk, not index. Closed.
LB-2 | updateTrip footgun — schema permitted raw startDate/endDate/totalNights write | Bug | Trips/Schema | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #2 | Fields removed from TripUpdateSchema; .strict() rejects. Closed.
LB-3 | Modify-AI long-conversation tag-loss — model stops emitting <modify> tags | Bug | AI | P0 — Launch blocker | DONE (audit 05-28) | YES — highest stakes, re-verify | LAUNCH_STATUS.md #3 / recap 05-23 | Was flagged biggest launch risk. Fixed commit b3994ff 05-23 (annotate not strip + retry + amber notice). RE-VERIFY against current ai.ts before launch.
LB-4 | Weather Tab live forecast — forecast_days param + .split() date bug | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #4 | Three sub-fixes in weatherFetch.ts/trips.ts. Closed.
LB-5 | Weather per-stop live→historical fallback for late stops | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #5 | LIVE_WINDOW_END_DAYS=15 + per-stop fitness/modeMatch. Closed.
LB-6 | aiConversation silent 400 — dead client write + stale exclusion query | Bug | AI/Trips | P0 — Launch blocker | DONE (audit 05-28) | YES — AI path, re-verify | LAUNCH_STATUS.md #6 | Dead write removed; surprise-trip exclusion rewired to PlanningSession.messages. RE-VERIFY (AI path, user-visible if regressed).
LB-11 | UTC-midnight arrival timezone artifact in server weather path | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #11 | parseTripDate helper added server-side. Verified in 3 timezones. Closed.
TM-1 | Map route polyline does NOT recompute when AI adds a stop | Bug | Trip Map | P1 — High | DONE (06-10) — confirmed in-app | N/A — open | recap 05-27 #1 | Map draws stale route, visibly skips the new stop. Same 'stale-consumer' family. Scout-first: find polyline coord source + recompute trigger + why Modify-AI save path misses it. ~10-30 line fix. ¦¦ AUDIT 06-10: reactive wiring present — Routes API effect (TripMapPage:902-911) rebuilds polyline on stop-coordinate-key change; ModifyTripPanel onTripUpdated -> setTrip (:2316) re-runs it; path pushed imperatively (:890-897); refetch path added :715. Caveat: new AI stop updates line only after geocode. ONE manual confirm: add stop via Modify-AI on map page, watch line redraw -> then close. ¦¦ 06-10: Benny confirmed manually — added a stop via Modify-AI on the map page, polyline redrew to include it. Closed (last stale P1 from the audit).
TM-2 | Map popup shows estimated rate, not actual rate after booking | Bug | Trip Map | P2 — Medium | DONE (audit 06-10) | N/A — open | recap 05-27 #2 | Popup reads siteRate w/o the actualRate ?? siteRate fallback wired on Booking page (commit bdb4192). ~5-10 lines in StopPopup. Bundle with TM-3. ¦¦ AUDIT 06-10: FIXED — TripMapPage:233 displayRate = actualRate ?? siteRate (cites booking-page pattern, commit bdb4192); all-in total adds actualFees only when actualRate exists (:241). Closed.
TM-3 | 'Book campgrounds' button has no hover state | Bug | Trip Map | P3 — Low / cosmetic | DONE (audit 06-10) | N/A — open | recap 05-27 #3 | Cosmetic inconsistency. Add hover: variant matching other action buttons. Bundle with TM-2 as one polish commit. ¦¦ AUDIT 06-10: FIXED — Book campgrounds CTA (TripMapPage:1881) carries transition-colors + hover:bg-#FAEEDA (gold-outline canonical, from MAP-ACTION follow-up e82c8c8). Closed.
TM-4 | What is 'Start trip' supposed to do? (product question) | Todo/Scout | Trip Map | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #4 | Flips status ACTIVE, unlocks Mark completed, shows dates. May not earn prominent slot. Scout: every trip.status read, ACTIVE-only behaviors, can status auto-detect from dates. Decide fix/retire/expand after.
TM-5 | Weather sub-tab is non-interactive | Bug/Todo | Trip Map / Weather | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #5 | Tab lists stops+dates but nothing clickable. Scout: scaffolded-but-unwired vs wired-but-no-affordance vs abandoned. Then finish / add affordance / remove tab. ¦¦ AUDIT 06-10: confirmed STILL OPEN — SidebarWeatherTab (TripMapPage:368-452) + StopWeatherCard are pure display, zero interactive elements.
AUDIT-1 | Systematic 'fields we capture vs fields we display' audit | Todo/Audit | Whole app | P1 — High | OPEN | N/A — open | recap 05-27 cross-cutting | Same stale-consumer bug shape hit 6x in 9 days. Own session. Walk every page, list field consumers, check each reads canonical source not stale/parallel field. Known clusters: siteRate/actualRate, campgroundName/candidates, locationName/lat-lng re-geocode, trip totals vs per-stop sums, AI-written fields user can override w/o recompute. ¦¦ AUDIT 06-10: confirmed STILL OPEN — needs its own session (suspect list not code-derivable).
PW-1 | Two cosmetic dead feature-gates (rigCompatibilityFilter, aiPlannerUnlimited naming) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Wire to a route or delete from both FEATURE_GATES tables. Marginal. ¦¦ AUDIT 06-10: confirmed — rigCompatibilityFilter in both gate tables, zero requireFeature() callers (every other key used). Wire or delete.
PW-2 | Extract TRIAL_DURATION_MS constant (7-day literal duplicated) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | 7*24*60*60*1000 copy-pasted in 2 places. Drift risk, not a bug. ¦¦ AUDIT 06-10: confirmed — 7-day literal still duplicated at auth.ts:95 + passport.ts:38, no shared constant.
PW-3 | Two parallel FEATURE_GATES tables hand-synced (server + client) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Extract a shared module. Drift risk, not a bug. ¦¦ AUDIT 06-10: confirmed — two hand-synced FEATURE_GATES tables remain (middleware/auth.ts:90 + authStore.ts:43).
AI-1 | Meter the AI for free/trial users (usage count + free limit) | Todo/Feature | AI | P4 — Post-launch | OPEN | N/A — open | recap 05-23 / memory | AI currently hard-gated (expired = no AI). Softer metered model is the fallback if hard gate hurts conversion. Best designed against real AIUsageLog data. Deferred.
EV-1 | Email verification | Todo/Feature | Auth | P1 — High | DONE (audit 06-10) — shipped end-to-end | Yes — confirm status & placement | memory / RR22 backlog | Previously flagged 'essential for real customers,' scoped & deferred. CONFIRM whether you still consider this launch-critical — it may belong at P0. Verify current state in code. ¦¦ AUDIT 06-10: FIXED end-to-end — schema columns emailVerified/Token/SentAt (schema:56-65); send-on-signup (auth.ts:142); verify + resend endpoints w/ 60s limit (emailVerification.ts); client VerifyEmailPage + EmailVerificationGate + VerificationBanner; requireVerifiedEmail across ~14 routers with owner bypass; Google-OAuth users pre-verified (passport.ts:34). Launch-criticality question answered: it is live. Closed.
IOS-1 | iOS Safari zoom-stuck bug | Bug | Mobile/UI | P1 — High | DONE (06-02) | Verify on phone (fresh bundle) | memory / RR22 backlog + recap 06-02 evening | iOS Safari/Chrome auto-zoomed on input focus (text ballooned, Send pushed off-screen, never reset). Root cause took 3 passes: (1) a global input,textarea,select{font-size:16px} guard already existed in index.css but was DEAD — it sat in @layer components and lost to text-sm. (2) Moved it OUTSIDE @layer on the theory unlayered beats layered — did nothing, because Tailwind v3.4.19 FLATTENS @layer at build time (compiled CSS has zero native @layer), so the guard was just a (0,0,1) type selector losing to text-sm/.input (0,1,0) on plain specificity → stayed 14px → iOS zoomed. (3) FIX (commit b9f0225 -> merged 5dd984c): added !important to the coarse-pointer guard so it beats the utility classes regardless of specificity, still scoped to @media (pointer: coarse) so desktop keeps 14px. PROVEN in compiled bundle: @media (pointer: coarse){input,textarea,select{font-size:16px!important}}. Verified working on device. KEY LEARNING: under Tailwind v3, unlayered CSS does NOT beat utility classes (no native layers emitted); a global rule that must beat a utility needs !important or specificity >=(0,1,0). Also verify the COMPILED bundle, not just source.
OHV-POC | OHV Destinations real data POC (directions / pass / fee) | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Page still has no real functionality beyond resource links (metadata was hardcoded). Recreation.gov scout was in progress. Build real directions/pass/fee once scout evaluated.
OHV-TRIP | OHV add-to-trip | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Let users add an OHV destination into a trip. Deferred feature.
BOOK-WAVE | Full booking modal wave (confirmation #, site #, hookup, rate, gate code, notes, edit/cancel, conflict detection) | Todo/Feature | Booking | P4 — Post-launch | OPEN | N/A — open | memory | Larger booking feature set. Post-launch.
OHV-LAZY | Code-split OhvDestinationsPage with lazy() | Perf | OHV/Bundle | P4 — Post-launch | OPEN (logged #15) | N/A — logged | this session 06-02 / LAUNCH_STATUS #15 | First-app-load only; per-visit load already fixed (GPS maximumAge + coarse OHV cache key). Low priority.
OHV-RETAIN | Client-side OHV result retention for instant return-visits | Perf | OHV | P4 — Post-launch | OPEN (logged #16) | N/A — logged | this session 06-02 / LAUNCH_STATUS #16 | Cache last GPS + last result so back-nav is instant. Nice-to-have, not a bug.
OHV-CHECK | OHV link-checker — ACTIVATION | Todo/Ops | OHV | P4 — Post-launch | OPEN (logged #17) | N/A — logged | this session 06-02 / LAUNCH_STATUS #17 | Three-state checker BUILT+merged (OK/DEAD/REVIEW, WAF allowlist, emails on DEAD/REVIEW). To activate: (1) confirm OhvLinkCheck table migrated; (2) wire monthly cron like trial-end email cron; (3) smoke-test w/ a known 404. First run will email a REVIEW list — expected; tune allowlist. ¦¦ AUDIT 06-10: 2 of 3 activation steps DONE — migration applied (in the 33), endpoint /api/v1/internal/cron/ohv-link-check registered + X-Cron-Secret validation + CRON_SECRET present in .env. REMAINING: register the monthly trigger (no scheduler config exists in repo — needs Render Cron Job or external scheduler) + smoke test. Matches LAUNCH_STATUS item 17.
PROD-1 | One-trip migration (dev DB → prod DB), re-pointed to prod user | Todo/Ops | Database/Deploy | P1 — High | OPEN | N/A — open | recap 06-02 | Move ONE specific trip from local dev to production, re-point to prod user. Schema-dependency scout FIRST (Trip→stops→candidates/POIs/bookings/party, insertion order, unique-constraint collisions, non-trip-owned refs like Rig). Uses Render External DB URL. PowerShell/psql gotchas apply. NOT started.
PROD-2 | Full feature test pass on live Render site | Todo/Test | Whole app | P1 — High | OPEN | N/A — open | recap 06-02 | Plan full trip on live site, hit paywall, run Stripe TEST payment, download PDF, verify Modify-AI (LB-3) and aiConversation (LB-6) in real prod env. First real-environment regression check.
PROD-3 | Point roamready.ai at the client (GoDaddy DNS → Render) | Todo/Ops | Deploy/DNS | P2 — Medium | OPEN | N/A — open | recap 06-02 | Phase 3. Domain owned at GoDaddy. Currently on onrender.com URLs. Update GoDaddy DNS to Render. Will affect CLIENT_URL, GOOGLE_CALLBACK_URL, Google Cloud authorized URIs once cut over.
PROD-4 | Wire AWS S3 (3 credential vars) — unblocks journal photo upload | Todo/Ops | Storage/Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Only AWS_REGION set in prod; 3 S3 credential vars omitted. Journal photo upload fails until wired. Known, non-blocking. ¦¦ AUDIT 06-10 nuance: code reads all 4 AWS vars with empty-string fallbacks + runtime 503 only on missing bucket (journal.ts:11-15,300); .env.example documents all 4; startup env validation (index.ts) has ZERO AWS entries unlike Stripe. Mitigated: photo upload hidden for launch (PHOTOS-HIDE) so the path is UI-unreachable. When S3 gets wired, also add the 4 vars to startup validation.
PROD-5 | Stripe live flip | Todo/Ops | Payments/Deploy | P4 — Post-launch | OPEN — deferred | N/A — open | recap 06-02 | Deferred until business bank account exists (LLC already exists). Then: activate Stripe (tax ID+bank+gov ID), recreate 4 founder price IDs in LIVE mode, stand up prod webhook, swap 6 env vars test→live. ~1hr contained session. ¦¦ 06-10: when the live flip happens, run node server/scripts/verify-stripe-prices.js with the LIVE Stripe vars (script reports key mode) — re-verifies all four price IDs + server/client env pairs in seconds (see STRIPE-PRICE-1). ¦¦ 06-10: also resolve FOUNDER-FORFEIT-1 (enforce or legalize founder-rate forfeiture) before/with the live flip. ¦¦ 06-10: live flip checklist also requires creating a LIVE-mode webhook endpoint + setting its signing secret on Render (see PROD-WEBHOOK-1 — test-mode endpoint did not exist either).
PROD-6 | Render auto-deploy webhook flaky — check GitHub webhook health | Bug/Ops | Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Auto-deploy missed pushes twice on 06-02. Workaround: Manual Deploy → Deploy latest commit if no deploy within ~1 min. Check GitHub→Render webhook health.
DISC-1 | Schema changes MUST go through migrate dev, NEVER db push | Discipline | Database | P1 — High | ACTIVE RULE | N/A — rule | recap 06-02 | LOAD-BEARING now that prod is live. stayActivities crash + OhvLinkCheck table were both db-push drift (in dev, absent in prod, no migration). Any uncommitted-migration schema change silently breaks prod and surfaces as a Sentry email. ¦¦ GOTCHA (2nd occurrence 06-10): Prisma differ keeps emitting a phantom ALTER TABLE JournalEntry ALTER COLUMN search DROP DEFAULT against the GENERATED ALWAYS tsvector FTS column; Postgres rejects it. Every new migration must be hand-trimmed to ONLY the intended change (mark failed attempt rolled back, trim, re-apply). Include this warning in any CC prompt that creates a migration.
HOME-MODAL | First-trip home-address capture (SaveHomeAddressModal) — opt-in to save trip start as home | Feature | Trips/Profile | P1 — High | DONE (06-02) | Verify in browser | recap 06-02 | SHIPPED client-only (modal + SessionPage wiring). Scout found the full home-address persistence layer already existed (User has all 8 home fields, profile edits them, AI pre-fills from them). Only gap was the opt-in modal at first trip. Fires when !user.homeLocation, saves only on active opt-in, per-trip override never overwrites saved home. Both builds green, merged. NOTE: currently saves city-only — see PROF-2.
PROF-1 | Profile home-address field renders empty despite populated DB data | Bug | Profile/UI | P2 — Medium | DONE (06-02) | Verify cold-load in browser | recap 06-02 | Stale-consumer bug (AUDIT-1 family). The visible address <input> was uncontrolled (defaultValue) + unregistered, so reset(user) hydration only fed the hidden registered fields (saves always worked, box stayed blank). Fix: controlled off watch(homeAddress), keeps input unregistered so Google Autocomplete keeps its ref. 1 file, +10/-1. Both builds green, merged. Confirmed only other defaultValue= hit (MembershipsPage:191) is NOT the same defect.
AI-MESA-1 | AI announces phantom home city for no-home users (Mesa → Roswell) | Bug | AI | P1 — High | DONE (06-02) | Verify w/ fresh no-home session | recap 06-02 | Two-part root cause, fixed across two commits. (1) Prompt had hardcoded real-city examples (Mesa, Austin/TX) in HOME-position; model borrowed them when [CITY] was unfillable. Fix: de-seeded all home-position examples to [HomeCity]/[HomeState] placeholders, preserved JSON structure (LB-3 modify prompt untouched + verified). (2) Deeper cause: userProfile drops undefined home keys via JSON.stringify, so model could not SEE home was empty and defaulted to the confident assert template. Fix: inject explicit noHomeDirective sentence in chatWithAI when !homeCity && !homeLocation (covers all 3 planning callers), + patched services/ai.ts:96 else-ask branch. When home exists, directive is empty string → momann path byte-identical (no regression). Prompt/service-only, no schema. VERIFY: fresh session, no-home user should ASK where starting from, not invent a city.
PROF-2 | SaveHomeAddressModal captures city-only, not a full structured address | Bug | Trips/Profile | P2 — Medium | OBSOLETE (audit 06-10) | N/A — open | recap 06-02 + mockup | Modal is a pure confirm dialog (no input); on opt-in SessionPage saves 3 city-level fields (homeLocation="Mesa, AZ", homeCity, homeState) and relies on getMe geocode backfill — which resolves the CITY CENTROID, not the real street address. Thin/half-useless home record. FIX (mockup approved 06-02): embed Google Places Autocomplete inside the modal, pre-seeded with trip start city; GATE "Save as my home address" so it only enables after a real place is SELECTED (populates all 8 fields); change modal contract onDone(bool) -> onDone(bool, address?{8 fields}); SessionPage sends full 8-field object to updateMe (server already accepts it). RECOMMENDED: extract shared client/src/components/ui/AddressAutocomplete.tsx (loader + Autocomplete + onPlaceChanged 8-field parser) — must NOT assume react-hook-form; returns parsed obj via onPlace callback. Ship modal on it first, migrate ProfilePage as follow-up. "Not now" = skip saving, city still used for planning (two clean paths, no muddy city-centroid middle). FIDDLY Google Places integration — do with fresh head (InfoWindow-saga lesson). Bundle near AUDIT-1. ¦¦ AUDIT 06-10: OBSOLETE as written — SaveHomeAddressModal file no longer exists (removed by MODAL-RM 06-07); only 2 stale comment refs remain (types/index.ts:237, HomeBaseCard.tsx:13 — see CLEANUP-1). Structured address fields live on User (homeStreet/City/State/Zip/Lat/Lng); capture surface is Profile/HomeBaseCard now (+ ONBOARD-HOME covers future capture). If city-only capture still matters it is a NEW item against the Profile flow. Closed.
AI-SURPRISE-1 | Surprise-trip rule misfires on named-destination trips (asks scope question) | Bug | AI | P1 — High | DONE (06-02) | Verify both paths in fresh session | recap 06-02 evening + scout | Planner asked a weekend/about-a-week/stay-regional-or-go-farther scope question for "Create me a trip from Fargo to Del Rio" — a fully-specified ~1,500mi cross-country trip. Root cause (scouted): that scripted question is STEP 1 of the Surprise-trip rule in services/ai.ts; model wrongly entered the surprise branch because the rule trigger has a loose model-judged catch-all ("any message indicating they want YOU to select where to go") and nothing hard-stopped it when a destination was already named. Scope question fires as FIRST response with NO distance precondition; the real distance reasoning (DRIVE-TIME CONSTRAINT) lives downstream in the build branch and never ran. FIX (prompt-only, +3/-1, commit 90be198 -> merged 6761fe6): prepended a PRECEDENCE guard to the top of the Surprise-trip rule — applies ONLY when no destination named; any "from X to Y"/"trip to Y"/"going to Y" pattern hard-disqualifies the surprise branch, routes straight to NAMED DESTINATION RULE. Catch-all trigger left intact so genuine "surprise me / you pick" still asks STEP 1. No server logic/schema/controller change. Server tsc green. VERIFY (restart backend + fresh browser session): (1) Fargo->Del Rio plans directly, NO scope question; (2) "surprise trip, you pick where" STILL asks the scope question (real surprise flow not broken).
MOBILE-CHAT-OVERFLOW | Chat bubbles could overflow horizontally on mobile (long tokens / no break-words) | Bug | Mobile/UI | P3 — Low | DONE (06-02) | Verify on phone | recap 06-02 evening (found while chasing IOS-1) | Found while debugging the IOS-1 zoom (initially mis-read as a horizontal page-shift). The in-session message bubble <p> (SessionPage.tsx) had whitespace-pre-wrap but no break-words, so a long unbreakable token (URL/long word) could overflow its max-w-[80%] box; overflow leaked through the message list (overflow-y-auto -> overflow-x:visible) into the overflow-hidden chat column. FIX (commit a92f1f9 -> merged 48e18b3, +2/-2): added break-words to the bubble <p> (source fix, wraps long tokens) + min-w-0 to the message-list flex container (guard, can never establish min-content wider than column). Avoided a blunt overflow-x:hidden (would clip tokens mid-word). NOTE: this was correct hygiene but NOT the cause of the reported zoom — that was IOS-1 (font-size). Client tsc && vite build green.
AUTH-RIG-1 | Home rig-context row blank on first login/signup until manual refresh | Bug | Auth/Profile | P1 — High | DONE (06-02) | Verify fresh Incognito login | recap 06-02 evening (found in prod-style fresh-login test) | On fresh login the Home screen (SessionPage empty-state) showed NO rig row (rig pill + "2 adults, pets" + hookup + "Planning for your ... — tap the rig to switch"); a manual browser refresh made it appear. Root cause (scouted end-to-end): the login AND signup endpoints return a SLIM user (no rigs, no travelProfile); the FULL user only comes from /users/me via authStore rehydrateUser(), which runs once on App boot — and on fresh login that boot effect already fired and no-opd BEFORE the token existed (it gates on token). So post-login the store held the slim user, Home never re-fetched, and the rig rows conditions were all falsy -> whole row hidden. Refresh works because App remounts with the token now present -> getMe -> setUser(full). Same stale-consumer FAMILY but the flavor is incomplete-data-shape-after-auth, not a re-render miss. FIX (client-only, 2 files +14/-2, commit 70cfc82 -> merged bddd626): await rehydrateUser() right after setToken+setUser in BOTH the login (LoginPage) and signup (SignupPage) success handlers, so the store holds the full /users/me user before navigating to Home. setToken runs first so the token gate passes; rehydrateUser swallows its own errors so a getMe hiccup never bounces the user to login (stays logged in w/ slim user = current behavior, not worse). NO server payload/schema change (deliberately chose client enrich over fattening the login endpoint — avoids an extra join on every login + Tier-1 schema churn). Mirrors AuthCallbackPage (OAuth) which already did getMe post-auth. Client tsc && vite build green. KEY LEARNING: slim-vs-full user payload shape at the auth boundary — any consumer reading rigs/travelProfile/parties straight off the post-login store will be empty until a refresh; enrich at the auth boundary, not per-consumer.
AUTH-RIG-1 | Home rig-context row blank on first login/signup until manual refresh | Bug | Auth/Profile | P1 — High | DONE (06-02) | Verify fresh Incognito login (no refresh) | recap 06-02 evening | On fresh login the Home screen (SessionPage empty-state) showed the greeting + trip box + in-progress trips but NOT the rig context row (rig pill, "2 adults, pets", hookup, "Planning for your <rig> — tap the rig to switch"); a manual browser refresh made it appear. Root cause (scouted end-to-end): the login AND signup endpoints return a SLIM user object (no rigs, no travelProfile); the FULL user only comes from /users/me via authStore rehydrateUser(), which runs once on App boot with empty deps — and on fresh login that boot effect already fired and no-opd BEFORE the token existed (rehydrateUser early-returns without a token). So post-login the store held the slim user, the Home screen never re-fetched, and every rig-row condition was falsy -> whole row hidden. Refresh "fixed" it because App remounts with the token now present -> getMe -> setUser(full). NOT a Zustand re-render issue (selectors re-render fine) — the full data simply never arrived post-auth. FIX (client-only, 2 files +14/-2, commit 70cfc82 -> merged bddd626): await rehydrateUser() after setToken/setUser in BOTH the login (LoginPage) and signup (SignupPage) success handlers, so the store holds rigs+travelProfile before navigating to Home. Chose client enrich over fattening the login payload (avoids touching Tier-1 auth endpoint + Zod schema + an extra DB join on every login). Safe: setToken runs first so rehydrateUsers token gate passes; rehydrateUser swallows its own errors so await never bounces the user to login on a getMe hiccup; no-rig users land cleanly (row stays hidden, no error). Mirrors AuthCallbackPage (OAuth) which already did getMe. Client tsc && vite build green. KEY LEARNING: slim-vs-full user payload shape at the auth boundary — any consumer reading rigs/travelProfile straight from the post-login store will be empty until a refresh; enrich at the auth boundary, not per-component.
HOME-MOBILE-1 | Home empty-state mobile polish: open-at-top, trips hint, placeholder clipping, post-login scroll race | Bug/Polish | Mobile/UI | P2 — Medium | DONE (06-02) | Verified on device | recap 06-02 evening | Four related Home empty-state (SessionPage) mobile issues, shipped across 3 commits. (1) OPEN-AT-TOP: app used BrowserRouter with no scroll reset, so navigating to Home carried the prior page scrollTop over -> greeting clipped. Fix: new global <ScrollToTop> (useLocation + useLayoutEffect window.scrollTo(0,0) on [pathname]) inside BrowserRouter above Routes (commit 433a1d9 -> ee13d2f). (2) TRIPS HINT: anchoring at top pushes in-progress trips below fold; added muted non-CTA cue at bottom of empty-state column gated on existing showContinueStrip, labeled with live planningTrips.length (commit 9f7b5cd -> 8a871d3). (3) CLIPPED PLACEHOLDER: ChatInput hero textarea rows=1 + fieldSizing:content sizes to empty VALUE not placeholder, so the 2-line placeholder clipped (worsened by the iOS 16px guard wrapping sooner). Fix: minHeight 3.5rem floor (kept fieldSizing/maxHeight so it still grows; no rows=2; copy unchanged) (commit 9f7b5cd). (4) POST-LOGIN SCROLL RACE: greeting still clipped on the post-login landing ONLY. Root cause: global ScrollToTop fires its one pathname-reset while SessionPage is still in its if(hydrating) SPINNER (short page, scroll trivially 0); a tick later hydrating clears, the tall empty-state mounts, browser scroll-anchoring bumps the greeting above the fold, and ScrollToTop never re-fires. From-Dashboard worked because warm data collapses spinner->content into ~the reset frame; post-login is COLD (awaited getMe + fresh-session POST + session fetch) so the gap is wide. NOTE: today AUTH-RIG-1 added an awaited rehydrateUser() to login, which WIDENED the cold path and is what exposed this race. Fix: SessionPage-local useLayoutEffect window.scrollTo(0,0) guarded on the hydrating->ready edge (dep [hydrating], !hydrating), re-applying the reset at the moment real content first paints; useLayoutEffect = before paint = no jump (commit eb61a4d -> 33a7748). Safe for active chat: window reset != the internal overflow-y-auto message-list scroll (bottomRef), different containers. All client tsc && vite build green. KEY LEARNING: a global pathname-keyed scroll reset MISSES content that mounts after an async hydrating gate; pages with a hydrating spinner need a LOCAL re-reset on the ready edge. Also: stale-bundle on the phone (restart Vite + hard-clear) masked test results repeatedly tonight — always confirm fresh bundle before judging a mobile fix.
SCROLL-BEHAVIOR-1 | Conversation over-scroll (top/controls clipped) + shared scroll-reset hook | Bug/Refactor | Mobile/UI | P2 — Medium | DONE (06-02) — rollout confirmed (audit 06-10) | Verified short+long convo on device | recap 06-02 evening (app-wide scroll audit) | Reported: in the active conversation view, an AI reply scrolled the top of the page (incl. the New trip / Cancel this plan controls) off-screen even when the exchange already fit. App-wide scroll audit found this is a CLASS of bug with two patterns. PATTERN 2 (over-scroll on content change): SessionPage bottomRef.scrollIntoView (and ModifyTripPanel) used default block:start, which scrolls ALL scrollable ancestors incl. the window on mobile (dvh > visual viewport), carrying the non-sticky header off the top even when nothing needed scrolling. FIX (commit 32ad9df -> merged 8c2097d): block:nearest on both call sites — no-ops when the latest message is already visible (short exchange stays put) but still scrolls minimum to reveal the newest message in long convos (scroll-to-latest preserved). TripBookingPage scrollToStop left alone (intentional deep-link nav). PATTERN 1 (pre-scroll on arrival): the global ScrollToTop fires window.scrollTo(0,0) on [pathname] only, so it MISSES content that mounts after an async hydrating/loading gate (the cold post-login clip — see HOME-MOBILE-1). Audit found ~15 pages with a short-loader->tall-content gate that lack a local ready-edge reset (Dashboard, TripSummary, TripJournal, PackingList, SharedTrip, EditRig, TravelParty, OHV/Van/CarCamping/Roadmap/Maintenance, admin). Established the canonical fix: new hook client/src/hooks/useScrollResetOnReady.ts (useLayoutEffect(()=>{ if(ready) window.scrollTo(0,0) },[ready])); refactored SessionPage onto useScrollResetOnReady(!hydrating) — behavior-identical, no runtime change (commit 8e1fdd6 -> merged aaa75fe). Both client tsc && vite build green. PENDING (held deliberately, fresh-head pass): roll useScrollResetOnReady(!loading) out to the ~15 candidate pages — one line per page, mechanical, but deserves its own focused test sweep; mostly PREVENTIVE (not all candidates will reproduce — needs scroll-anchoring to inject above the fold). KEY LEARNING: a global pathname-keyed scroll reset misses post-hydration content; any page with a loading spinner before tall content needs a local ready-edge reset — now centralized in useScrollResetOnReady so it is not sprinkled/drifting. ¦¦ AUDIT 06-10: Pattern-1 rollout confirmed on 13 pages (Dashboard, SessionPage, TripSummary, Maintenance, CarCamping, PackingList, SharedTrip, OhvDestinations, Roadmap, VanDestinations, EditRig + hook). TripMapPage (byte-stable rule) and TripBookingPage not using it — acceptable exclusions. Closed.
DATE-ANCHOR-1 | Trips ignore user departure date; every itinerary anchors to today | Bug | AI/Trip pipeline | P1 — High | DONE (06-02) | Verified specific + vague-month in fresh session | recap 06-02 evening (gated audit + build) | SYSTEMIC: every trip anchored its itinerary to TODAY regardless of the date the user gave (confirmed across multiple users/trips incl. ones with explicit dates). Example: a September trip rendered Day 1 = Jun 4 (build day); season survived only in the trip NAME ("...Fall Adventure"). Root cause (gated scout, root cause (a) = never captured): the itinerary JSON schema the AI emits had NO date field, so a stated date had nowhere structured to land; promote wrote no Trip.startDate; server recomputeStopDates fell back through trip.startDate ?? firstDatedStop.arrivalDate ?? new Date() -> today, and back-filled startDate + every stop arrivalDate to today. The DISPLAY was innocent (correctly read the stored dates, which were today). KEY AUDIT FINDING: the whole server side was already wired right — PlanningSessionPromoteSchema already accepted startDate, promoteSession spreads ...data, recomputeStopDates anchors on startDate, and the map-page shiftDates picker already re-anchors all stops. The pipeline just never RECEIVED a date. FIX (gated 2-phase, +12 across 2 files, commit 5c400b7 -> merged 00b59d7): (1) services/ai.ts — added top-level startDate (ISO yyyy-mm-dd) to the itinerary JSON schema; added a DEPARTURE DATE RULE: specific date -> resolve+emit; vague month/season -> propose FIRST TUESDAY of that month (best midweek RV travel: lighter weekend traffic, easier campground availability) and ASK to confirm, emitting NO <itinerary> that turn (mirrors surprise-rule STEP 1 so the build does not trip early); no date -> omit. Also injected "Today is <ISO date>." into the system prompt so the AI resolves the correct YEAR (LLM date-guessing is unreliable — this was the gap that would have silently broken vague-month + specific-date year resolution). (2) SessionPage.tsx buildItinerary — added startDate: itinerary.startDate ?? null to the promote payload (the single client wiring line). No server/schema change needed; no backfill of existing trips (decided: leave them, fix new only); display ?? new Date() fallback left intact. Server tsc + client tsc/vite build green. DESIGN DECISIONS: vague month -> first Tuesday + confirm; editable post-build via existing map-page date picker; existing wrong-dated trips left as-is. KEY LEARNING: a feature can look like a 4-layer rebuild but be a capture-only gap — audit-first (gated) revealed the server was already ready and the real fix was 1 schema field + 1 prompt rule + 1 client line. Also: any AI feature that must reason about dates needs today injected into the prompt — never trust the model to know the current date/year.
AI-MESA-2 | Planner invents phantom origin city for no-home user on PROD ("...home address in Fargo") despite no-home directive being live | Bug | AI | P1 — High | DONE (06-04) — verified on PROD | Verified on live PROD, fresh session | recap 06-04 (gated DB+code scout) | REGRESSION introduced by AI-SURPRISE-1 (6761fe6). On PROD, no-home user momann sent "create me a trip to cincinnati" and the planner FIRST reply asserted "I will use your home address in Fargo as the starting point." Gated diagnosis ruled out: (a) stale deploy — backend roamready-api confirmed on 00b59d7, fix code live; (b) stored data — ALL momann home fields NULL on prod DB, no Fargo stored; (c) seeded history — session had exactly 2 messages, Fargo originated in the assistant reply only. ROOT CAUSE (code scout): chatWithAI correctly injects the noHomeDirective for null-home users (gate is correct), BUT the prompt ALSO contained the AI-SURPRISE-1 example "Create me a trip from Fargo to Del Rio" in the ORIGIN slot — structurally matching the user message. Classic instruction-vs-example conflict: the concrete origin-city example overrode the abstract "do not borrow a starting city" directive. AI-SURPRISE-1 had planted its own repro phrase as the canonical example a few hours after AI-MESA-1 de-seeded city examples, silently violating the de-seed invariant. FIX (prompt-only, +3/-3 in server/src/services/ai.ts, commit 84c105d -> merged 433ffb4): placeholder-ized ORIGIN-position cities in examples while preserving example SHAPE — line ~106 "from Fargo to Del Rio" -> "from [Origin] to [Destination]"; ~118 "leaving from Austin" -> "[Origin]"; ~174 San Jose/Austin/Denver/San Jose,CA->Miami -> [Origin]/[State]/[Destination]. Left untouched: noHomeDirective + gate (correct); destination-position cities (cannot be misborrowed as start; entangled with DATE-ANCHOR-1 JSON example); [HomeCity]/[HomeState]; LB-3 modify prompt; all schema. Client tsc+vite green; ai.ts zero tsc errors (server exit-1 was pre-existing redis.ts/prisma.ts TS2742 junction artifacts). VERIFIED ON PROD after redeploy + fresh session: no-home user now ASKS "Where will you be starting from?" and names no city; AI-SURPRISE-1 both guards still hold (genuine "you pick" still asks scope question; real named from-X-to-Y still plans directly). KEY LESSON: a later prompt fix that ADDS an example can silently violate a de-seed invariant set by an earlier fix. Any future CC prompt that adds/edits example text in ai.ts must end with a grep check that all ORIGIN-position cities are placeholders ([Origin]/[HomeCity]), never real city names.
FT-1 | Full-timer + skip-persistence feature (isFullTimeRVer + dismissedHomePrompt flags, HomeBaseCard mockup-B, Profile toggle, AI home-free ask) | Feature | Trips/Profile/AI | P1 — High | DONE (06-07) — leak re-fixed 06-09 | Verify on phone via tunnel | recap 06-07 | Handles 3 user kinds with no recurring nag: home-base / full-timer / skipped. Schema: 2 booleans on User (isFullTimeRVer, dismissedHomePrompt) @default(false); migration add_fulltimer_dismissed_flags applied to DEV DB (psql-confirmed), pure additive. updateMe whitelist + AI userProfile carry isFullTimeRVer. services/ai.ts directive split: full-timer w/ no captured origin gets a HOME-FREE ask (no home/save wording); no-home non-full-timer keeps existing ask. HomeBaseCard rebuilt to segmented toggle (Save home base / Done); Skip persists dismissedHomePrompt + one-time "add in Profile" line (gate-flip deferred ~2.2s so line shows). Gate: isEmptyState && !homeLocation && !isFullTimeRVer && !dismissedHomePrompt && !homeCardDismissed. Profile toggle w/ mutual exclusivity (check full-timer clears+disables address; pick address unchecks full-timer). Both builds green, pushed. ¦¦ 06-09: a full-timer home-address NAG resurfaced during trip creation. Two fixes this session: (e776b3d) broadened origin extraction to catch 'to Y from X' word order + lowercase origins; (f2bb1ce) gated the save-address template on !isFullTimeRVer in the PROMPT BODY (not just the injected directive) so it cannot leak. NOTE: the 'regression' was actually a STALE BACKEND (dev server running pre-fix code) — restart + fresh session clears it. AI-path: restart backend, test in NEW session.
PROF-3 | Profile full-timer save flashes & does not persist (empty-string into Float? column + silent catch-less failure) | Bug | Profile | P1 — High | DONE (06-07) | Verified save sticks + reload | recap 06-07 | With a saved address, checking "I am a full-time RVer" + Save just flashed, no persist. Root cause (scouted): mutual-exclusivity clear wrote into homeLat/homeLng (Float? cols) -> Prisma rejects ->Float -> whole updateMe throws ATOMICALLY -> isFullTimeRVer never commits; AND onSubmit had try/finally with NO catch -> silent flash. FIX (client-only): clear all 8 home fields to null (not ); added catch + visible red "Could not save changes" error state. Confirmed sticks + survives reload. KEY LEARNING: clear nullable numeric cols to null not ; a catch-less try/finally hides real errors as a no-op flash.
MODAL-RM | Remove redundant post-build SaveHomeAddressModal ("save trip start as home" popup) | Cleanup | Trips | P2 — Medium | DONE (06-07) | Verify build->map, no popup | recap 06-07 | Closes HOME-MODAL (which shipped 06-02) as now-redundant given the home-base card + full-timer flag + deterministic origin capture. Scout confirmed the itinerary build does NOT depend on the modal (it only gated navigation; build/generate already fire before it). Fully removed: import, saveHomePrompt/savingHome state, the trigger block (collapsed to unconditional navigate(.../map)), handleSaveHomeDone, render, and component file (git rm). CC cleaned newly-orphaned imports (usersApi removed, setUser destructure narrowed to user, HomeAddress import removed) — tsc --noUnusedLocals would have failed otherwise. Client build green, pushed. Two harmless stale doc-comments left (types/index.ts startAddress, HomeBaseCard:13). Supersedes PROF-2 (the city-only modal upgrade) — modal is gone, so PROF-2 is MOOT.
MOBILE-CHAT-HDR | Mobile chat header + top of first reply cut off after sending first message (window over-scroll from keyboard lift across empty->active layout swap) | Bug | Mobile/UI | P1 — High | DONE (06-09) | YES — finish via diagnostic capture, then push | recap 06-07 | NOT PUSHED — all uncommitted in working tree (clean revert point). Symptom: after sending the FIRST message, header ("New trip/Cancel this plan" + "Last edited") + top of reply ride off above the viewport. MEASURED (temporary on-screen overlay) the real cause: WINDOW scroll of 110px (scrollY=110, docH 872 > innerH 762, vvTop=0, keyboard closed). dvh wrapper makes the document taller than the visual viewport; tapping the empty-state hero input lifts the keyboard and scrolls the window down; on send the layout swaps but window.scrollY is never reset. FOUR REAL FIXES IN TREE (keep): (1) message-list scroll containment (listRef.scrollTop guarded on overflow, replaces scrollIntoView so it never scrolls the window); (2) scroll-reset useLayoutEffect (prevEmptyRef true->false edge -> scrollTo(0,0)); (3) body-scroll-LOCK useLayoutEffect (overflow:hidden in conversation view, cleanup restores); (4) sticky header (sticky top-0 z-10 bg-white). dvh height (:844) deliberately NOT changed. Both crash dead-ends fixed: hooks placed ABOVE early returns (was "Rendered more hooks than during previous render" — first early return is if(hydrationError) ~:788). Body-lock got it to scrollY=0 / fully visible in one test. REMAINING EDGE CASE: after stripping the diagnostic, a transition-timing case (during the typing-indicator / first paint of the active layout) still clips and does NOT snap back. NEXT (fresh head): restore the diagnostic, capture numbers AT THE BROKEN MOMENT (during typing, not after settle), then ONE measured fix (apply lock/scrollTo earlier on the isEmptyState flip, possibly in the send handler before the swap; dvh-height rework is last resort). KEY LEARNING: MEASURE before fixing — 6 rounds on theory, solved instantly once instrumented. ¦¦ 06-09: RESOLVED structurally. The off-screen-input bug was confirmed PRE-EXISTING (git: present at baseline bf89b0a; zero visualViewport handling ever). Root cause: mobile wrapper had min-height not definite height -> list never bounded -> input rode off-screen. FIX (mobile-only, desktop untouched): frozen header fixed top-0 / md:sticky + shell pt-[3.75rem] (d815916); pinned input fixed above nav + wrapper min-h->h definite (e534fda); messages rest-at-bottom via inner flex justify-end (2829b28). Earlier rest-at-bottom-via-scroll attempt (bae95cc) pushed input off-screen and was REVERTED (e15875f). Diagnostics removed. No visualViewport needed (measured occlusion negative/visible). NOT PUSHED yet at recap time. ¦¦ PUSHED with the 06-09 batch (CHAT-PUSH); RR35 scout confirmed origin/main == main.
DISC-2 | Diagnostic-overlay-first when a UI cause is unknown after >1 failed fix | Discipline | Whole app / UI | P1 — High | ACTIVE RULE | N/A — rule | recap 06-07 | New working rule from the mobile-chat saga. When a layout/scroll/render bug survives a couple of theory-based fixes, STOP guessing — add a temporary on-screen diagnostic overlay (fixed-position, prints live values like scrollY/innerH/docH/visualViewport/element rect.top), reproduce, read REAL numbers at the BROKEN moment, then make exactly one measured fix. Strip the diagnostic after. Mirrors DISC-1 in spirit: instrument-and-measure beats repeated blind edits.
NGROK-1 | ngrok HTTPS tunnel for real-device phone testing of DEV | Ops/Tooling | Dev/Tooling | P2 — Medium | DONE (06-07) — working | N/A — setup | recap 06-07 | Phone could not log in to dev (OAuth callback redirected to localhost = ERR_CONNECTION_FAILED; mobile browsers also refuse session storage over plain http on a LAN IP). FIX = HTTPS tunnel. ngrok installed via DIRECT .exe download to C:\Users\aylie (npm install was broken/silent — Windows flakiness); run as .\ngrok.exe. Free STATIC domain handling-jackal-omit.ngrok-free.dev (registered once, stable). Google Cloud (roamready-493621) OAuth client: added redirect URI https://handling-jackal-omit.ngrok-free.dev/api/v1/auth/google/callback AND JS origin https://handling-jackal-omit.ngrok-free.dev (origins field = domain only, no path). Dev .env (DEV-ONLY, do NOT push): GOOGLE_CALLBACK_URL + CLIENT_URL -> tunnel; vite.config.ts allowedHosts:[tunnel] (kept host:true + /api proxy). No server code changed. Run: .\ngrok.exe http --domain=handling-jackal-omit.ngrok-free.dev 3000 (own window). Phone: run backend+Vite+ngrok, load the https tunnel URL, click thru one-time interstitial — OAuth + email/password both work, sessions stick. NOTE: desktop OAuth now also wants the tunnel URL (dev .env points there). Free static domain = no re-register between sessions.
OAUTH-LAN | Host-adaptive dev OAuth over raw LAN IP (no tunnel) — scoped, NOT built | Todo/Ops | Auth/Deploy | P3 — Low | OPEN — scoped, deferred (tunnel made it unnecessary) | N/A — scoped | recap 06-07 | Fully scoped but NOT built. Would make dev OAuth work from BOTH localhost and the LAN IP without a tunnel by deriving callbackURL + final-redirect host from x-forwarded-host WHEN NODE_ENV!=="production", keeping GOOGLE_CALLBACK_URL/CLIENT_URL authoritative in PROD (prod callback arrives via Render rewrite, so x-forwarded-host is the API host there — must NOT derive). Also needs LAN origin allowed in dev CORS + the LAN-IP redirect URIs registered in Google Cloud. Superseded for now by NGROK-1 (cleaner, also fixes the mobile insecure-http session problem the LAN-IP fix would NOT). Keep only if you want tunnel-free phone testing.
ONBOARD-HOME | Capture home base + full-timer in the /onboarding flow, then suppress HomeBaseCard for onboarded users | Todo/Feature | Onboarding/Trips | P2 — Medium | OPEN — scoped idea | N/A — scout | recap 06-07 | Your idea, flagged as the better capture point than the post-load card. Add home address + a "full-time RVer" option as a step in /onboarding (Vehicle->Rig->Style->...->Done). Once captured there, the HomeBaseCard becomes FALLBACK-ONLY (already naturally suppressed by its gate: !homeLocation && !isFullTimeRVer && !dismissedHomePrompt). Its own scoped build with a scout — adds a step/fields to the onboarding flow. Not started.
WMK-1 | Recreate RoamReady.ai watermark/wordmark as a clean SVG (current looks washed-out/pixelated) | Todo/Design | Branding/UI | P3 — Low | DONE (audit 06-10) | N/A — scout | recap 06-07 | Watermark looks washed-out/pixelated like a raster scaled up. RECOMMENDED: rebuild as an SVG WORDMARK (vector, razor-sharp at any size, tiny) and use it at low opacity for the watermark — one source, two uses, never blurry. The image scout (find roamready*.png/svg assets in client/public + client/src/assets, the header sunset/road icon, exact brand hexes RV Blue #1F6F8B / Sunset Gold #F7A829 / D1 gradient) was DRAFTED but never run (CC ran the OAuth scout instead). CAVEAT: text wordmark is straightforward to rebuild; the sunset/road ICON is hard to match exactly unless an existing SVG of it is found. ¦¦ AUDIT 06-10: FIXED — SessionPage hero renders /roamready-wordmark.svg (SessionPage:996); SVG in client/public (4.5KB, dated 06-08). Two orphan PNGs (roamready-wordmark-transparent.png, -white-bg.png) referenced nowhere — deletable (see CLEANUP-1). Closed.
TEST-ACCTS | Recreate special-state dev test accounts (wiped by the 06-07 DB reset) | Todo/Ops | Dev/Data | P3 — Low | DONE (audit 06-10) — email corrected | N/A — as needed | recap 06-07 | The dev DB reset wiped all test accounts: momann@gmail.com (owner isOwner=true paywall bypass, 2021 Thor Magnitude BH35), momannexpired (expired Pro trial for paywall testing), Cindy@roamready.ai (Free trial), bmolini (verified-inbox), hometest (null-home). Tables intact, rows gone. PROD untouched. For full-timer testing a plain no-home signup suffices; the owner-bypass + expired-trial states need manual recreation (set flags in DB) when those paths need testing again. ¦¦ AUDIT 06-10: dev DB has exactly 3 users — momann@gmail.com (isOwner, founder, trial to 06-15), Cindy@roamready.ai (verified, isOwner, founder), and the expired-trial account at momannexpired@roamready.test (NOT @gmail.com — tracker email was wrong; seeder server/scripts/seed-expired-user.ts; trialEndsAt 2026-05-31, FREE). All states present. Closed. ¦¦ 06-10 late: dev-state tidy queued for next session — momann@gmail.com on dev is founderPricing=false (post-forfeit-test; set-founder.js --grant not yet run) and tier=FREE while Stripe holds an ACTIVE $8.99 test subscription (final checkout webhook missed — tunnel closed). Morning fix: run set-founder grant; reopen tunnel + one clean checkout to square the DB (or cancel the dangling $8.99 test sub in dashboard). Cosmetic dev state only.
JBANNER-1 | Journal banner States/Trips toggle + shared AllTripsMap extraction | Feature | Journal/Maps | P2 — Medium | DONE (06-09) | Verify on device | recap 06-09 | Added a States¦Trips segmented toggle to the Journal banner — flips one fixed-size box between the states choropleth and an inline all-trips map. Extracted shared AllTripsMap component (5abdaf2); JournalMapPage now a thin wrapper; TripMapPage untouched. AllTripsMap is React.lazy + only mounts in Trips mode (States-only users load NO Google Maps bundle). Commits: 5abdaf2 extract, c9aa405 toggle, 8cde9f9 fixed-size box, a846dd9 header rename 'States visited & trips taken' + removed redundant journal pins from states map, 6c2ff05 banner Trips map self-sufficient (own dropdown+routes toggle, 'View full map' link removed). NOT PUSHED at recap.
AI-ORIGIN-1 | Trip-creation origin extraction missed reversed word order + lowercase origins | Bug | AI | P1 — High | DONE (06-09) | Verify in NEW session after backend restart | recap 06-09 | User typed 'Create a trip to New Orleans from san jose' -> AI ignored 'from san jose' (asked for origin anyway) AND nagged about home address. Root cause: extractFromXtoY (controllers/ai.ts) only matched 'from X to Y' with UPPERCASE origin -> capturedOrigin null -> fell through to ask+home-nag. FIX (e776b3d): broadened to both word orders ('from X to Y' AND 'to Y from X') + lowercase origins (normalizeOriginCase), with conservative STOP-word guards (rejects 'from bad to worse', 'from work', 'from dawn to dusk' via proper-noun-signal requirement). Tested: captures correctly, idioms reject. AI-path: restart backend + new session.
AI-FT-LEAK-1 | Full-timer home-address save template leaked despite suppression directive | Bug | AI | P1 — High | DONE (06-09) | Verify in NEW session after backend restart | recap 06-09 | Full-timer (isFullTimeRVer=true, no home) still got 'I don't have a home address saved... I'll help you save it'. DB confirmed flag stored true, so the AI received it — but the no-home save-address TEMPLATE was physically present in the prompt body, so the model grabbed it despite the full-timer directive. FIX (f2bb1ce): gated the save-address template on !isFullTimeRVer in the prompt body itself (not just the injected directive). Same family as AI-MESA-1/AI-MESA-2 (instruction-vs-example/template leak). The 'reappearance' on 06-09 was a STALE BACKEND, not a real regression. AI-path gate applies.
VEH-PICKER-1 | Mobile vehicle-confirmation modal buried under itinerary bottom sheet | Bug | Mobile/UI | P2 — Medium | DONE (06-09) | Verified on phone | recap 06-09 | On phone, tapping 'Build full itinerary' opened ConfirmVehiclesModal (z-50) but left the itinerary BottomSheet (z-81) open on top, covering the vehicle picker. Root cause: onBuildItineraryClick called setConfirmVehiclesOpen(true) WITHOUT setSheetOpen(false). FIX (bf89b0a): added setSheetOpen(false) after the guard so the sheet closes when building starts — sequencing, NOT z-index (scout confirmed z-index bump = wrong, leaves two stacked overlays). Mobile-only (desktop Build is in-flow sidebar). Confirmed working.
CHAT-DEADSPACE-1 | Mobile chat dead-space (triple bottom-nav reservation) + height-chain | Bug | Mobile/UI | P2 — Medium | DONE (06-09) | Verified via on-screen diagnostic | recap 06-09 | Measured (DIAG overlay): bottom-nav clearance reserved ~3x (main pb-32 128px + wrapper -8rem 128px + input +4rem ~64px) for a ~56px nav -> dead space + a 422px page-scroll on keyboard focus. FIX (06e9592): reconciled to ONE reservation (wrapper min-h-full, input pb trimmed) -> killed the 422px keyboard page-scroll. Then height-chain fix (6291f67 -> later 13.25rem in d815916): gave the wrapper a definite height so it fills <main> (Delta/GAP became constant regardless of conversation length). Part of the broader MOBILE-CHAT-HDR resolution. Measure-first discipline (DISC-2). NOT PUSHED at recap.
CHAT-PUSH | Push the 06-09 batch (chat layout + journal banner + AI fixes + vehicle picker) to prod | Todo/Ops | Deploy | P1 — High | DONE (06-09) | N/A — confirm landed | recap 06-09 | Whole 06-09 session is local-only at recap time (user was saving/pushing at the end). No migrations in the batch = low-risk. After push, confirm Render deployed (PROD-6: auto-deploy flaky, manual Deploy if no build within ~1 min). Verify chat layout on prod (hard-refresh the phone — cached CSS/JS can mask). Commits incl: 5abdaf2 c9aa405 8cde9f9 a846dd9 6c2ff05 (journal), e776b3d f2bb1ce (AI), bf89b0a (vehicle), 06e9592 6291f67 d815916 e534fda 2829b28 (chat), e15875f (revert), plus diag-removal commits. ¦¦ 06-09 PM: PUSHED via save-progress.bat. Batch landed on main/origin. Includes the RES-1 key fix (env-side), FUEL-LOG-1 (5205227,a02712e), and RES-2 (4367fab) from the afternoon session. ¦¦ RR35 scout confirmed: origin/main == main @ 0606276, zero unpushed commits — entire 06-09 PM batch (incl. evening wave) is on origin.
CHAT-RESTBOTTOM | Chat rest-at-bottom — superseded/RESOLVED by the pin structure | Note | Mobile/UI | P3 — Low | RESOLVED (06-09) | N/A | recap 06-09 | Earlier in the session this was PARKED for late June after a scroll-based attempt failed. SUPERSEDED: once the input was pinned (e534fda) and messages wrapped in flex justify-end (2829b28), rest-at-bottom works structurally without any scroll hacking. No longer a separate backlog item. KEY LESSON: the fix was structural (pin input like a chat app), not scroll logic — scroll-based attempts fought the layout.
TRIPS-BOX-TALLER | Make the Trips banner map box slightly taller than the choropleth box | Todo/Polish | Journal/Maps | P3 — Low | OPEN — optional | N/A | recap 06-09 | User wanted the Trips-mode map box a touch taller than the states choropleth box (more room for the map + its controls). Would break the equal-size flip rule (box would change size between States and Trips modes). Small height-value change, never built. Optional polish.
RES-1 | Resources "near you" strip returned "No results found nearby" on prod | Bug | Resources | P2 — Medium | DONE (06-09) | Verified on prod | recap 06-09 | An earlier scout found a backslash route-path typo ('\resources') in api.ts:235, but it was ALREADY fixed in current main (path is '/resources', cat -A confirmed LF-only, git unmodified at d3b3b3e). REAL prod cause: the GOOGLE_MAPS_API_KEY VALUE in the roamready-api Render env was WRONG (not missing). googlePlaces.ts returned null -> [] -> empty UI. Render [Places] log showed "Text search failed (HTTP 400): API key not valid / INVALID_ARGUMENT". FIX: corrected the key value in the Render env (no code change). Confirmed working — Resources now returns results. Same prod-env-gap family as PROD-4. KEY: var is GOOGLE_MAPS_API_KEY (not GOOGLE_PLACES_API_KEY). Failure signatures: present-but-wrong key = HTTP 400 "API key not valid"; missing key = console.warn "not set"; API-not-enabled = HTTP 403 REQUEST_DENIED.
FUEL-LOG-1 | Cost breakdown fuel-leg rows overflowed on mobile, pushing Save off-screen so actual fuel could not be logged; rows also looked disjointed when label wrapped | Bug | Trips/Mobile UI | P2 — Medium | DONE (06-09) | Verified on device | recap 06-09 | TripSummaryPage.tsx fuel-leg row (~1763). The Log-actual SAVE PATH was fully wired (saveLegFuel -> updateStop {actualFuel}, Enter/Escape handlers, Stop.actualFuel field + migration 20260524193338) but the Save button was clipped off the right edge on mobile — and the decimal soft keyboard has no Return key, so there was NO way to commit a value. Root cause: the row was a single-line flex with both children flex-shrink-0 and no wrap. FIX (layout/className only; commits 5205227->96b6406 then a02712e->6b0e07b): every fuel-leg row now stacks two-line on mobile (cities+miles on top; cost + action on their own full-width line below, left-aligned) via flex-col + md:flex-row md:justify-between; input w-20 md:w-24; controls flex-wrap so Save/Cancel never clip. Desktop unchanged. No logic/server change. Applies to STATE A (estimate + "+ Log actual") and STATE B (edit mode w/ Save+Cancel).
RES-2 | "Resources near you" results not ranked by distance — far results outranked nearby ones | Bug | Resources | P2 — Medium | DONE (06-09) | Verified on device | recap 06-09 | searchResourcesNearby used Google searchText (relevance-ranked, no rankPreference) with no distance sort, so a ~25mi Cave Creek and ~75mi Payson dump station outranked a 2mi Mesa one (Chevron on Ellsworth Rd). Comparison vs Google Maps "near me" confirmed our RESULTS were good/relevant (Google's extras were mostly sponsors) — the only real gap was ORDERING. FIX (server-only; commit 4367fab->370dc18): added a haversine distance sort in searchResourcesNearby after the result .map(), sorting closest-first to the user GPS; bumped maxResultCount 10->20 then slice top-10 AFTER sorting (so the closest 10 by real distance surface, not Google's relevance top-10); null-coord results sort last via Infinity. Kept searchText + free-text category queries (option b) — switching to searchNearby would break free-text categories like "RV dump station" and risk shared verifyCampground/searchCampgroundsByArea callers. Applies to ALL category chips, not just Dump Stations. DECISION: page design is fine as-is (ranked list, no AI curation needed); AI-over-data summary parked as a post-launch idea. NOTE: sort runs over the <=20 relevance set, so a closer place Google didn't return in those 20 still won't appear — acceptable for this symptom. Backend restart required after deploy (server change).
MAINT-1 | Maintenance log (Resources > Maintenance "Rig service tracker") has no logging/tracking — no flow | Feature | Resources/Maintenance | P2 — Medium | SCOUTED 06-09 — on hold, scope TBD | N/A — scout | recap 06-09 | The Maintenance card under Resources ("Rig service tracker") opens but has no real log/tracker. Benny wants a proper maintenance tracker that FLOWS: record service items, dates, mileage, history, and recurring/upcoming reminders. SCOUT FIRST: inspect the existing Maintenance page (what is built vs stub, any schema/fields/migration, how it ties to the user's rig) before designing. This is a feature build, not a tune. Queued AFTER RES-2. ¦¦ SCOUTED 06-09: feature is NOT a stub — it is built end-to-end. Schema (MaintenanceItem + MaintenanceLog + MaintenanceStatus enum) migrated in base migration 20260407162013. Server: full CRUD at /api/v1/maintenance (getItems, getHistory, createItem[gated], updateItem[gated], logService[gated]) + verifyRigOwnership + computeStatus(OK/DUE_SOON/OVERDUE from rig.currentMiles & dates). Client maintenanceApi has all 5 methods. Page (client/src/pages/MaintenancePage.tsx, /maintenance) is a working tracker: rig selector (multi-rig), Overdue/Due-soon/Up-to-date summary cards, items grouped by status, per-item "Log service" modal (date/mileage/cost/notes). Auto-seeds 12 DEFAULT_RV_MAINTENANCE items on RV rig creation (users.ts:201; non-RV rigs get none). GAPS = UI ONLY (backend complete): (1) getHistory unused -> logged service is invisible (the main "no flow" complaint); (2) createItem has no UI (no "add custom item" button); (3) updateItem has no UI (no edit); (4) empty state dead for non-RV rigs (fixed once add-item exists); (5) DELETE missing UI AND server endpoint (the one genuine net-new backend bit: 1 route + controller method); (6) next-due date/mileage computed but not displayed. Pattern to mirror for add/edit/delete UI = Travel Party (TravelPartyPage.tsx + its routes/controller/schema/api). RECOMMENDED first pass: #1 show history + #2 add-custom-item/empty-state (most "flow" for least risk). ON HOLD — Benny deciding scope (which of the 4: history / add+empty / edit-delete / next-due).
ROADMAP-LOC | Product Roadmap mis-placed in Resources "Tools & guides" row — move to Help | UX/Cleanup | Resources/Navigation | P3 — Low | DONE (06-09) | Verify on dev | recap 06-09 | The /roadmap page is a PUBLIC, data-driven feedback/voting board (Planned/In Progress/Shipped from the Feedback table, with upvote + submit). It is NOT static "company plans" content. Scout confirmed the owner-side counterpart already exists at /admin/feedback, so the public board should stay public — do NOT hide it behind owner gate. Issue was only PLACEMENT: it sat in the Resources "Tools & guides" tile row next to trip utilities (Maintenance, OHV), a category mismatch. DECISION: remove the Product Roadmap tile from ResourcesPage HUB_TILES; surface/keep it on the Help page (where it is already linked). Keep /roadmap public + unchanged; do NOT add to top nav. Resources tools row then = trip tools only. ¦¦ DONE: removed roadmap tile from ResourcesPage HUB_TILES + dropped unused Package import (commit a1ea58e->a3f0b8e); added a dedicated "Product Roadmap" card w/ View link on HelpPage between FAQ and Known issues; centered the two remaining tiles (Maintenance, OHV) via grid-cols-2 sm:max-w-md sm:mx-auto (b093133->14ffed3). /roadmap unchanged + public. Pushed.
ADMIN-GRANT | Admin access: add owner-only Admin link to MOBILE nav + grant isOwner to test accounts | Feature/Ops | Admin/Auth | P2 — Medium | DONE (06-09) | Verify on dev | recap 06-09 | Two parts. (1) CODE — the owner-gated Admin nav link already exists on DESKTOP (AppLayout.tsx ~129, gated user?.isOwner) but is MISSING from the mobile sidebar; add it to the mobile sidebar <nav> (~211-228) after Help, same isOwner guard. Bottom tab bar left alone (fixed 4-item). OwnerRoute (client) + requireOwner (server) already protect /admin. (2) OPS (Benny runs — DB permissions change, not Claude) — grant isOwner=true to momann@gmail.com and Cindy@roamready.ai on the DEV DB (dev@roamready.ai may already be owner — verify). No UI/endpoint sets isOwner; manual UPDATE only. Use list-users.js to verify casing/existence first, then: UPDATE "User" SET "isOwner"=true WHERE lower(email) IN (lower('momann@gmail.com'), lower('Cindy@roamready.ai')); confirm rows changed; users must re-login to pick up the flag. CAUTION: isOwner = full Pro + skips email verification + unlimited AI (paywall bypass). Cindy was a Free-trial test acct — Benny confirmed OK to convert. PROD is a SEPARATE DB — grants do not propagate; do prod deliberately/scoped later. Admin dashboard is REAL (4 live stat cards: users, Pro subs, trips, free users + Feedback/Revenue/Subscribers/Link-Health subpages) — not stubbed. ¦¦ 06-09: CODE DONE. (a) Mobile Admin link added to sidebar after Help, owner-gated, Shield icon, matches sidebar styling (commit e53f9ed->8d9e4ca). Bottom tab bar untouched. (b) Built reusable grant script server/scripts/set-owner.js (commit 96ff813->e0aad87): node set-owner.js <email> <true¦false>, case-insensitive, prints DB host before write (dev vs prod visible), one email/run, no-op guard, before->after + row count. Reviewed/approved, NOT yet run. PENDING (Benny ops): run list-users.js -> set-owner momann@ + Cindy@ true on DEV, verify, log out/in to test; then PROD via PowerShell $env:DATABASE_URL override (Render External DB URL) + new-terminal cleanup after so override does not linger. isOwner = full Pro + skip email verify + unlimited AI. ¦¦ DONE 06-09: granted isOwner=true to momann@ + Cindy@ on PROD via set-owner.js. Connection saga (resolved): Render external DB needs SSL — added opt-in PGSSL env to the script (commit 1297bfb->bab0ca8), ssl{rejectUnauthorized:false} when PGSSL=true. PowerShell run pattern: $env:DATABASE_URL="<render External DB URL>"; $env:PGSSL="true"; node server/scripts/set-owner.js <email> true. GOTCHAS hit: (1) ECONNRESET = SSL not enabled; (2) semicolon-chained $env did not apply PGSSL — set on separate lines + echo to verify; (3) "unparseable host / ENOTFOUND base" = literal <placeholder> pasted instead of real URL; (4) clean up after: Remove-Item Env:\DATABASE_URL + Env:\PGSSL so prod URL does not linger into dev commands. Admin link: desktop showed immediately (code already on prod); MOBILE link required the e53f9ed->8d9e4ca commit to be pushed (git log origin/main..main to check) + Render redeploy (PROD-6 flaky) + phone hard-refresh + fresh login (isOwner read at login). VERIFIED: admin live on prod desktop + mobile for both accounts. NOTE: isOwner = full Pro + skip email verify + unlimited AI on those accounts.
COST-LINK | Make "Est. total" stat link/scroll to the Cost breakdown section on the itinerary page | UX/Polish | Trips/UI | P3 — Low | DONE (06-09) | Verify on dev | recap 06-09 | On TripSummaryPage the top "Est. total" stat ($1,643) is static text while a full Cost breakdown card sits lower on the same page. Make the Est. total tappable to smooth-scroll down to the breakdown. Scout: no existing scroll pattern in the file (the "View weather" links are toggles, not jumps; refs used only for timers). FIX (client-only, no new state): add costBreakdownRef on the Cost breakdown card-lg (~1569); add optional onClick prop to the presentational StatCell (~2020) rendering it as an accessible button when provided + subtle " down-arrow"/hover-underline affordance in #1F6F8B; wire onClick only on the Est. total StatCell (4th, ~1315-1320) to costBreakdownRef.scrollIntoView({behavior smooth, block start}). Other 3 stats stay non-interactive. Label flips to "Actual" when actuals logged — scroll still applies. ¦¦ DONE (commit 33f5e53->db21ae8): added costBreakdownRef on the Cost breakdown card; StatCell got optional onClick -> renders as accessible <button> w/ cursor-pointer, small down-arrow after label, hover:underline on the value (#1F6F8B); wired only on the Est. total cell to scrollIntoView smooth/start. Other 3 stats unchanged (plain div). Works for Est. total + Actual label states. Client-only, no new state. ¦¦ Affordance refined: replaced the bare down-arrow with explicit one-line "Est. total · View breakdown ↓" link (#1F6F8B, hover:underline), shortened on mobile; row alignment preserved. PUSHED to prod, verified working.
JOURNAL-STOPS | Trip Journal should mirror the itinerary stops (stop entries stay in sync with the actual trip stops) | Feature | Journal/Trips | P2 — Medium | DONE (06-09) | N/A — scout | recap 06-09 | Benny: the Trip Journal "Stop entries" should MIRROR the itinerary stops. Right now the journal shows stop entries (e.g. Redding, Sacramento) with Title/Notes/Rating/Actual cost/Add photos/Save — confirm these stay in sync with the actual itinerary stops (added/removed/reordered). SCOUT: how journal stop entries are generated vs the trip stops — snapshotted at journal creation or derived live from trip.stops? What happens when a stop is added/removed/reordered on the itinerary after journal entries exist? Goal: journal stop list always reflects the current itinerary stops. Queue after MAINT-1 (or bundle — both Journal-area). ¦¦ SCOUT FINDING: live-mirroring was ALREADY working (journal page maps over trip.stops on load; add/remove/reorder auto-mirror; no stored snapshot). Only gap = deleted-stop entries silently demote to Freeform as anonymous "Untitled". DONE (commit 0646a66 -> merged 3ff0d3c, 49+/7-, 3 files, NO migration — placeName/state already on JournalEntry): server journal.ts now persists state (+ existing placeName/lat/lng) on per-stop upsert AND on the photo-upload create/update path (null-only backfill, never overwrites). Client EntryCard got opt-in showRemovedStopOrigin prop: orphaned entry (stopId null) with a placeName renders place as heading + muted "from a removed stop · City, ST" label; user-written title still wins; scoped to trip-journal Freeform section only (Dashboard/other EntryCard usages untouched). Live stop-entry list unchanged. Pre-existing orphans have null state until re-saved (shorter label) — expected. Client tsc+vite + server tsc green.
JOURNAL-ROUTESTOP | Add journal-entry area under stops added via "Add stops along the way" on the itinerary | Feature | Journal/Trips | P3 — Low | DONE (06-09) — VERIFIED on prod | N/A — scout | recap 06-09 | Benny: when a user adds a stop via the itinerary "Tell me more about this route / + Add stops along the way" flow (mid-route attractions like Mount Shasta, Castle Crags from the Suggested-along-this-route list), there should ALSO be a place to add a journal entry under that added stop, so route-inserted stops become journalable like the main overnight stops. Related to JOURNAL-STOPS (same data-model question: do route-added stops flow into the journal stop list?). SCOUT alongside JOURNAL-STOPS. Lower priority. ¦¦ BUILT (commit 04f3ac1 -> merged 6547b9a, 8 files +247/-11): added nullable routePoiId String? + @@index to JournalEntry; migration 20260609120000_add_journal_routepoiid created AND APPLIED to dev DB (prisma migrate dev, status "up to date", backend restarted). Stable POI ids minted in addPOI/addPOIWithDetails. TripJournalPage renders nested "Stops along the way" cards per ADDED route POI (not the suggested list) under the arriving stop; upsert keyed on routePoiId via POST /journal/route-poi/:routePoiId (controllers/journal.ts upsertRoutePoiEntry); edit/delete reuse PUT/DELETE /journal/:id; orphaned route entries (POI removed/regenerated) demote to Freeform via placeName. NO Stop-row promotion (date cascade/counts/leg math safe). BUGFIX (commit 57dba5c -> 557724f): crypto.randomUUID() is undefined on insecure origins (plain-HTTP LAN-IP phone testing) -> threw -> "+ Add" route-stop button silently did nothing on phone (worked on localhost). Replaced with makePoiId() helper that falls back to timestamp+random id when crypto.randomUUID unavailable. Client-only, no migration, fresh bundle on phone to pick up. IMPORTANT for ANY future client code: do not call crypto.randomUUID() in paths that run on the LAN-IP phone test setup (HTTP) — use a guarded fallback. Verify on phone: + Add works, route stop shows as journal card, note saves/sticks. ¦¦ VERIFIED (RR35 scout + manual): commits 04f3ac1/6547b9a + 57dba5c/557724f confirmed pushed; prisma migrate status clean (migration in applied set on dev); Render deploy logs confirmed add_journal_routepoiid applied on PROD; Benny spot-checked route-stop journal card add/save on dev + prod. Fully closed.
JOURNAL-EDITDEL | Add Edit + Delete to journal entries (both per-stop entries and freeform entries) | Feature | Journal/Trips | P2 — Medium | DONE (06-09) | N/A — scout | recap 06-09 | Benny wants Edit AND Delete on BOTH kinds of journal entries: (1) per-stop entries (the upsert cards — Redding/Sacramento — edit = change fields + Save; need a Clear/Delete to wipe the entry without deleting the stop) and (2) freeform entries (standalone, incl. orphaned "from a removed stop" entries — need real edit + delete). SCOUT FIRST: check the journal controller/routes (server/src/controllers + routes/journal) for existing update/delete endpoints (journalApi may already have them un-surfaced, like maintenance did); how upsert vs delete is modeled; whether deleting a per-stop entry = delete the JournalEntry row (stop card then shows empty form again) vs a soft clear. Then surface Edit + Delete buttons on EntryCard / stop cards with a confirm on delete. Mirror existing CRUD UI pattern. Related to JOURNAL-STOPS (just shipped) + JOURNAL-ROUTESTOP (in progress). ¦¦ SCOUT: full CRUD already existed server-side (DELETE /journal/:id, PUT /journal/:id, userId-scoped, tripJournal-gated; journalApi.delete/update defined but UNUSED). UI-only surfacing. DONE (commit 347e940 -> merged 7b8aa8a, client-only, 2 files +211/-48): per-stop entries got a confirm-gated Delete button (only when an entry id exists -> journalApi.delete -> form resets to {}; Stop untouched, FK onDelete:SetNull). Freeform entries got opt-in onEdit/onDelete props on shared EntryCard (Pencil/Trash2 icons), wired on BOTH Trip Journal page AND Dashboard Journal tab (JournalTabContent). Edit reuses AddEntryModal w/ optional entry prop (prefill + "Save changes" -> journalApi.update); no second editor. All deletes window.confirm-gated. Per-stop edit was already inline (Save=upsert). NOTE: CC correctly reset the worktree onto local main (3ff0d3c) before building since origin was behind — avoided clobbering the unpushed placeName work.
JOURNAL-PHOTOS-HIDE | Hide journal photo upload for launch (no storage wired — avoid cost/moderation/privacy) | Decision/Cleanup | Journal/Trips | P2 — Medium | DONE (06-09) | Verify on dev | recap 06-09 | DECISION (06-09): hide the "Add photos" affordance in the journal for launch. Rationale: S3 storage was never wired on prod (see PROD-4 — only AWS_REGION set, 3 credential vars omitted), so uploads fail on prod anyway; and we want to avoid storage cost + moderation + privacy (EXIF) surface pre-launch. Evaluated options: (A) HIDE = chosen; (B) wire S3 + 3-photo cap = deferred; (C) link external photos = rejected because share links (Google Photos/Instagram/FB) do NOT yield reliable inline thumbnails (access-gated / hotlink-blocked) — only tappable "view elsewhere" links, which Benny found underwhelming. BUILD: hide/disable "Add photos" on BOTH per-stop entries (StopJournal) and freeform (AddEntryModal/EntryCard) — client-only, keep the photos field/endpoint in code dormant (do not rip out uploadPhotos), just remove the UI affordance so it can be re-enabled later. FUTURE (when storage is turned on): apply a 3-photos-per-stop cap as the guardrail. Bundle this with JOURNAL-EDITDEL (same journal cards). ¦¦ DONE (same commit 347e940 -> 7b8aa8a): removed the "Add photos" button + hidden file input + handleAddPhotosClick/uploadPhotos UI handlers + now-unused useRef/Camera imports from StopJournal (noUnusedLocals on). AddEntryModal/EntryCard never had a photo control. DORMANT/INTACT for re-enable later: journalApi.uploadPhotos (api.ts:258), the server uploadPhotos endpoint, the photos field, and display of EXISTING stored photos (old data not broken). Future: 3-photos-per-stop cap when storage is turned on. Client tsc + vite green.
MAP-BREADCRUMB-CLIP | Trip map page breadcrumb ("Dashboard > <trip name>") clipped/hidden under the frozen header on mobile | Bug | Trips/Mobile UI | P2 — Medium | DONE (06-09) | N/A — scout | recap 06-09 | On mobile the breadcrumb row at the top of the Trip MAP page (TripMapPage) — "Dashboard > Billings to Sedona" — is cut off / half-hidden behind the fixed mobile header (screenshot: text clipped right under the nav bar). Same family as the mobile-chat-header clipping (content riding under the fixed top-0 header). Likely needs the page top to clear the fixed header (pt offset, cf app-shell pt-[3.75rem]) or the breadcrumb to sit below the header band. SCOUT TripMapPage top layout + interaction w/ AppLayout fixed mobile header. NOTE: TripMapPage kept byte-for-byte stable per standing rule — minimal mobile-only change. NO migration. ¦¦ DONE (commit 47c59ce -> merged b6573ff, ONE line): TripMapPage.tsx:1456 wrapper "-mx-4 -my-6" -> "-mx-4 -mb-6 -mt-2 md:-mt-6". Root cause: -my-6 (-24px top) was calibrated to cancel desktop md:pt-6, but mobile main has only pt-2 (8px) so it over-pulled 16px, dragging the breadcrumb under the 56px fixed header. Fix makes the top pull responsive: -mt-2 on mobile (cancels pt-2, breadcrumb flush below header) / md:-mt-6 reproduces exact desktop -24px. Horizontal -mx-4 + bottom -mb-6 full-bleed unchanged. Shell was already correct — fix belonged on the map page wrapper. Respected TripMapPage byte-stable rule (one class string only). Client tsc + vite green.
MAP-LEGEND-FINISH-DUP | Trip map legend shows two "Finish" rows (H Finish + F Finish) — one likely mislabeled (H = Home?) | Bug | Trip Map/UI | P3 — Low | DONE (06-09) — verified pushed | No — confirmed in RR35 scout | recap 06-09 | Map legend (screenshot) lists BOTH "H Finish" (orange) and "F Finish" (gray) — two entries both labeled Finish. Almost certainly a mislabel: H marker is probably HOME not Finish (F = real finish). Check the legend label map in the trip map component. Cosmetic, low priority. Verify what H/F/S markers represent before relabeling. ¦¦ RESOLVED: fix already landed inside the 06-09 PM batch — commit d4653bb (merge db2917e, branch fix/map-legend-single-finish) collapsed the two rows into ONE orange "Finish" row. Found in history by the RR35 post-batch scout (landed between MAP-ACTION-PILLS and HELP-REDESIGN), so it was pushed with the batch. Closed.
JOURNAL-LINK-ITIN | Add a Trip Journal link/button to the itinerary page (TripSummaryPage) | Feature/Nav | Trips/UI | P3 — Low | DONE (06-09) | Verify on dev | recap 06-09 | The itinerary page (TripSummaryPage) top action row has Modify with AI / Share / PDF but NO Trip Journal link, while the Trip MAP page DOES have a "Trip Journal" action (seen in map page action row). Add a Trip Journal link/button to TripSummaryPage so journal is reachable from the itinerary view too (consistent nav across both trip views). Route is /trips/:id/journal. Match the existing action-row button styling on that page. Client-only, no migration. Queue AFTER the crypto.randomUUID POI-id fix lands. ¦¦ DONE (commit 656fef0 -> merged ce8b2a9, +11/-1, client-only): added a Trip Journal <Link to=/trips/:id/journal> to the TripSummaryPage top action row, BookOpen icon (matches Map page Journal action), btn-outline text-sm styling identical to Modify with AI/Share. Row order: Modify with AI -> Trip Journal -> Share -> PDF. Row already had flex-wrap so it wraps on mobile, no overflow. Link/BookOpen imports handled. Client tsc + vite green.
DISC-PRODMIGRATE | Prod auto-runs migrations on deploy (db:migrate:deploy) — no manual prod migration needed | Discipline/Ops | Database/Deploy | P1 — High | ACTIVE RULE / CONFIRMED | N/A — rule | recap 06-09 | CONFIRMED 06-09: Render roamready-api deploy already auto-applies migrations to PROD. Build Command: npm install && npm run db:generate && npm run build. Start Command: npm run db:migrate:deploy = "prisma migrate deploy --schema=../prisma/schema.prisma" (server/package.json) = the production-safe apply-all-pending command (never creates/resets/prompts, no data loss). So: apply a migration to DEV with prisma migrate dev, commit the migration file, push via save-progress.bat -> Render rebuild runs db:migrate:deploy -> applies pending migrations to the PROD DB automatically. Do NOT run prod migrations by hand. AFTER pushing a migration: (1) confirm Render deployed (PROD-6 auto-deploy flaky -> manual Deploy if no build within ~1 min), (2) CHECK DEPLOY LOGS for the migration name applying (e.g. add_journal_routepoiid), (3) test the feature on prod (a successful save proves the column exists). The JOURNAL-ROUTESTOP migration (routePoiId) rides this path on the next push. NOTE: prisma migrate dev locally needs the root .env DATABASE_URL — run from repo ROOT (cd .. out of server) or it errors P1012 "DATABASE_URL not found"; and clear any leftover $env:DATABASE_URL prod override first.
MAP-ACTION-PILLS | Trip Map page top actions (Trip Journal / Packing list / Share / PDF) -> separate pill buttons | UX/Polish | Trip Map/UI | P3 — Low | DONE (06-09) | Verify on dev | recap 06-09 | TripMapPage top action strip had 4 bare floating links (Trip Journal, Packing list, Share, PDF). Benny chose Option B (mockup): each action becomes its OWN separate pill (rounded-full, 0.5px border, px-3.5 py-1.5, text-sm, hover:bg-gray-50), in a flex gap-2 flex-wrap row so they wrap cleanly on mobile. Chose B over A (single segmented bar) for better mobile wrapping + because these are 4 independent actions, not a pick-one toggle. Actions/icons/navigation UNCHANGED — styling only. CAUTION: TripMapPage byte-stable except this directed change — touch only the action-row markup. Client-only, no migration. ¦¦ DONE (commit 77e7f7a -> merged 893f58b, +13/-5, client-only): TripMapPage action-row container -> flex flex-wrap gap-2 py-2 (dropped lg:flex-nowrap); each of the 4 actions -> px-3.5 py-1.5 text-sm bg-white border-gray-200 rounded-full (0.5px inline borderWidth) + hover:bg-gray-50/text-#1F6F8B, whitespace-nowrap flex-shrink-0. All to/onClick/disabled/icons byte-identical (Journal->/trips/:id/journal, Packing->/packing/:id, Share->setShareOpen, PDF->handleExportPdf w/ Generating state). Wraps cleanly on mobile. Only the action row touched (TripMapPage byte-stable rule respected). Client tsc + vite green. ¦¦ FOLLOW-UP (commit e82c8c8 -> merged eaeba85): the standalone gray rounded-full pills were a DEVIATION from the app canonical button system (.btn-outline/.btn-primary defined in index.css; ~80% of trip pages already use it). Scout confirmed TripSummaryPage action row is the reference. CONFORMED the map action row to canonical: Trip Journal/Packing/Share -> "btn-outline text-sm flex items-center gap-1.5" (teal RV Blue #1F6F8B border+text, rounded-lg, #E0F0F4 hover); PDF -> "btn-primary text-sm flex items-center gap-1.5 disabled:opacity-60" (amber) — byte-identical class strings to TripSummaryPage:1299-1317. Map + itinerary action rows now render as the same component. Container kept flex flex-wrap gap-2 (mobile wrap). All to/onClick/disabled/icons byte-stable. KEY LESSON: use the canonical btn-outline/btn-primary classes for action buttons — do not hand-roll inline button styles (causes page-to-page drift). REMAINING canonical-drift to normalize later (separate optional pass, scouted): TripBookingPage:1047 teal rounded-md primary, DashboardPage:211/305 inline-amber CTAs duplicating btn-primary.
HELP-REDESIGN | Help page redesign: branded header + canonical card chrome + clean Known Issues + Submit feedback button | UX/Polish | Help/UI | P2 — Medium | DONE (06-09) | Verify on dev | recap 06-09 | Benny: Help page looks weak. Multi-part redesign (one pass): (1) BRANDED HEADER — replace the weak plain wordmark top with a branded header resembling the home/landing page (logo + D1 sunset gradient hero feel). Scouting landing page first to match real branding; Benny to pick from mocked options. (2) CHROME — conform the 4 inline-styled cards (warm-taupe #E8E4DA border, rounded-lg+p-6 hybrid) to canonical .card-lg (rounded-xl, border-gray-200/50, 0.5px); normalize h1 text-2xl -> text-xl. (3) KNOWN ISSUES — current 2 items are STALE (iOS Safari zoom = IOS-1 DONE 06-02; journal photo uploads = intentionally hidden today via JOURNAL-PHOTOS-HIDE) -> Benny keeping the section and will supply CURRENT issues to populate. (4) SUBMIT FEEDBACK — add the same "Submit feedback" button from the Product Roadmap page under the Help page Roadmap section. CONSTRAINTS: keep content verbatim otherwise, keep FAQ accordion, no color-coded sections (no tinted Known Issues), Sunset Gold only where brand-appropriate (header gradient ok, not a CTA recolor), keep public-route standalone chrome (logged-out users). Content stays, FAQ accordion stays. ¦¦ DONE (HelpPage.tsx, multiple commits 7c02a75/e51e680/e749c5f/dc223f3 -> merged through 0606276): (1) Branded hero (Option 3): "← Home" link top-left authed-only -> centered roamready-icon.png + tri-color RoamReady.ai wordmark (casing FIXED to capital-R) -> 4px var(--rr-sunset-gradient) strip BELOW the masthead -> "Help & Support" h1, no subtitle. Top padding tightened to pt-1. (2) All 4 inline-styled cards -> canonical .card-lg (killed warm-taupe #E8E4DA border); page bg -> shared bg-rr-bg token; h1 normalized. (3) Known Issues -> "all clear" neutral-gray line (no green/tint). (4) Submit feedback button added under Roadmap as btn-outline, mirrors RoadmapPage openFeedbackModal (FeedbackModal mounted app-wide so works on standalone route); "View Product Roadmap ->" link kept. CONTACT BOX: "Get in touch" heading removed; leads with the full restored intro paragraph ("We started RoamReady because trip planning... small team... read every message... reach out anytime") then Email us at support@roamready.ai; redundant duplicate approachable lines eliminated (sentiment appears once). FAQ accordion + footer kept verbatim, standalone public-route chrome kept. No new colors. Client tsc + vite green throughout.
GREET-TZ-1 | Time-of-day greeting inconsistent across pages (Dashboard "Good morning" vs Home "Up late" at 11:41 PM local) | Bug | UI/Cross-page | P3 — Low | DONE (06-10) — push pending (save-progress.bat) | No — verified in build + spot-check | screenshots 06-10 | At 11:41 PM Arizona (MST, UTC-7), prod Dashboard greets "Good morning, Benny" while Home (SessionPage) greets "Up late, Benny?". Same mismatch observed at ~7 PM. 11:41 PM MST = 6:41 AM UTC -> leading theory: one greeting computed from local device time, the other from UTC (server time or getUTCHours), i.e. two separate greeting implementations that drifted (button-drift pattern, but for clocks). RECOMMENDED FIX (pending scout): single shared client-side getGreeting() helper, local device time, one set of hour buckets, consumed by both pages (and any other copies the scout finds). Read-only scout prompt drafted (find both implementations, report time source + buckets + any caching). ¦¦ FIXED (commit adc7f8b -> merge 801a849, 2 files, client-only). Scout REFUTED the UTC theory: DashboardPage.tsx:206 was a HARDCODED "Good morning" string with no time logic at all; SessionPage was already correct (local-time buckets via greeting.ts). Fix: hour boundaries consolidated into one private timeBucket(hour) (5-11 morning / 12-17 afternoon / 18-20 evening / rest late); timePool now a bucket lookup so selectGreeting behavior is observably unchanged; new exported getSalutation() maps the same buckets to plain salutations; Dashboard h1 consumes it (late-night renders "Up late, {firstName}?"). Verified: tsc clean, full build passed, spot-checks 23:41->Up late, 09:00->morning, 13:00->afternoon, 19:00->evening, 04:59->Up late (boundary). Merged to local main --no-ff; NOT pushed at fix time — Benny to hard-refresh check + save-progress.bat. ¦¦ SUPERSEDED BY DESIGN (06-10): Benny decided the Dashboard should not greet at all — header to be replaced with the Resources-style page title (see DASH-HEADER-1). getSalutation to be removed as unused; the timeBucket refactor STAYS (selectGreeting/Home depends on it). The fix itself worked as specced. ¦¦ 06-10: getSalutation removed in DASH-HEADER-1 (b7a5f27) as planned; timeBucket refactor retained and load-bearing for Home.
DASH-HEADER-1 | Dashboard header: remove greeting, use Resources-style page title ("Your trip dashboard" big, no subtitle) | UX | Dashboard/UI | P3 — Low | DONE (06-10) — pushed | No | Benny decision 06-10 | Design decision (screenshots, dev): Dashboard should not greet ("Up late, Benny?" felt wrong there); instead match the Resources page header pattern — big h1 title, exactly the Resources h1 styling. Spec: "Your trip dashboard" as the large title, NO subtitle (trip cards self-explain); remove getSalutation import/usage from DashboardPage AND remove the now-unused getSalutation export from greeting.ts (grep-verify first); KEEP the timeBucket refactor — selectGreeting/Home observably unchanged. Everything else in the header row (Plan a new trip, search, chips, trial banner) untouched. Client-only. CC prompt drafted, awaiting run. ¦¦ FIXED (commit b7a5f27 -> merge c733b3a, 2 files, client-only). DashboardPage:212 now renders h1 "Your trip dashboard" with the exact Resources h1 classes (text-xl font-medium text-gray-900 — happened to match the old greeting h1, so only the text changes visually); greeting h1, subtitle <p>, salutation const, and getSalutation import removed; useAuthStore kept (trial banner still needs user). greeting.ts: getSalutation + SALUTATION_BY_BUCKET removed; timeBucket refactor + POOL_BY_BUCKET kept, selectGreeting (Home) observably unchanged. Verified: pre-delete grep showed only the definition remained; post-merge grep zero matches; full build passed. NOT pushed at fix time — 4 commits ahead of origin (GREET-TZ-1 pair + this pair); Benny to hard-refresh check + save-progress.bat.
AI-HUMOR-1 | Add humor/personality to trip-build experience (loading lines first; AI persona later) | Feature | AI/UX | P4 — Post-launch | OPEN — idea, scope discussed | Yes — scout loading-state sites first | Benny idea 06-10 | Benny: can the AI responses have humor when people build a trip? Discussed three layers by risk: (1) RECOMMENDED FIRST PASS — deterministic micro-copy: rotating hand-written funny loading lines while the itinerary builds (+ empty states, success line), shipped like the Home greeting pools (rotating variants, no AI). Pure client work, zero AI risk, one CC session. (2) LATER, OWN SESSION — short persona section in the conversational planner prompt: warm/wry, max one light line per reply, HARD RULES: never inside JSON output, never about costs/safety/breakdowns/errors, drop humor when user is stressed/reporting a problem. Requires regression spot-checks after (no-home user, reversed origin phrasing, full-timer suppression) since the prompt holds ORIGIN RESOLUTION + SCOPE-1 anchor + FT suppression. (3) NEVER — humor instructions in JSON-generation paths (verify-note failure shape: chatty preamble breaks parsing). Status: idea logged; scout for layer-1 loading-state sites not yet drafted.
PASS-SCROLL-1 | Memberships & Passes: "+" opens add-membership form below the fold with no scroll — looks like a dead button | Bug | Profile/UX | P2 — Medium | DONE (06-10) — verified + pushed | Yes — CC scouts location first | Benny report 06-10 | Clicking the "+" on passes in Memberships & Passes DOES open the add-membership box further down the page, but the page does not scroll, so the click appears to do nothing (invisible-success bug, same family as COST-LINK). FIX SPEC: on add-form open, after render, smooth scrollIntoView (block: center) on the form container + focus the first input; driven from the open-state change (useEffect/ref callback), NO setTimeout guessing; if "+" clicked while already open, re-scroll + refocus (preserve existing toggle semantics); reuse the COST-LINK scroll pattern from TripSummaryPage if reusable. Desktop + mobile. CC prompt drafted (scout locates the component first), awaiting run. ¦¦ FIXED (commit eb5c4fa -> merge dd04b43, MembershipsPage.tsx only, +10/-2). Scout: "+" cards in "Available to add" (MembershipsPage:163) call openAddForm -> setShowForm(true); form renders as the LAST block on the page (below the fold, no scroll/focus). COST-LINK turned out to be a plain inline ref + scrollIntoView (no shared util) — pattern reused. Fix: formRef on the form card-lg container + useEffect keyed on showForm -> scrollIntoView({smooth, center}); no-op on close. DELIBERATE DEVIATIONS: (1) first-input FOCUS skipped — ACCEPTED as the better call (mobile auto-focus pops keyboard mid-scroll; IOS-1 zoom + MOBILE-CHAT-HDR history); (2) re-click while form already open does NOT re-scroll (showForm unchanged). OPEN TEST before closing clean: open form, scroll up, click a DIFFERENT pass "+" — if the form silently updates below the fold with no scroll, original bug recurs; one-line follow-up (key effect on selected pass too, or scroll in openAddForm). Build passed. NOT pushed at fix time. Note: local main had advanced to 42da058 "Progress save" — GREET-TZ-1/DASH-HEADER-1 pairs appear pushed via save-progress between sessions. ¦¦ 06-10: Benny verified in-app (scroll-on-open works, re-click test passed) and pushed via save-progress.bat. Closed.
BILL-FOUNDER-1 | Billing: "Lifetime founder rate" only explains itself on hover (invisible on mobile) — replace with inline anchor pricing (regular rate slashed vs founder rate) | UX | Billing/Conversion | P2 — Medium | DONE (06-10) — verified + pushed | Yes — scout for pricing facts first | Benny idea 06-10 | Two parts. (1) BUG-ish: the founder-rate element relies on hover for its explanation — no hover on mobile, so the best marketing line is invisible. (2) FEATURE: show anchor pricing — regular rate struck through next to the founder rate on BOTH monthly and yearly cards, plus a "Lock in the founder rate forever" one-liner; kill the tooltip. GUARDRAIL: slashed price must be a REAL regular rate defined in code/Stripe and genuinely intended post-founder (no fake reference pricing — trust + FTC). OPEN QUESTION: Benny forgot the regular monthly/yearly rates — scout must report every price the code knows (founder prices + any regular/post-founder rate in client constants, server config, Stripe price IDs, seeds, LAUNCH_STATUS.md). If NO regular rate exists anywhere, Benny picks the number first (typical founder anchors 25-40% off), then implement. Scout prompt drafted, awaiting run. ¦¦ SCOUTED 06-10. PRICING FACTS: founder $7.99/mo, $69.99/yr; REGULAR $8.99/mo, $89.99/yr (in ToS, trial-end email, admin MRR math, STARTUP.md) - anchor numbers are real, anchoring is clean. Yearly is the headline: save $20/yr (~22%); monthly only $1 (~11%). Badge duplicated in PricingPage.tsx:284-297 + PaywallModal.tsx:216-229; native title= tooltip; the cancel-and-rejoin half of the message is hover-only (invisible mobile). PricingPage is ONE Pro card with annual toggle (price line :263-275); regular prices hardcoded TWICE in that file. FIX SPEC (drafted): strikethrough regular before founder price for active interval; "Save $20/yr" chip on annual only; kill title/cursor-help/Info icon; full caveat as always-visible small print ("Locked in while you stay subscribed - cancel and rejoin later and you will pay the regular rate"); consolidate PricingPage regular prices into one constant; mirror in PaywallModal by hand; SKIP useBillingConfig extraction (stays backlog); comment-only fix in founderPricing.ts:1-9 (flag survives cancellation, RATE does not per ToS - current comment contradicts ToS and could mislead a future editor); schema.prisma untouched; non-founder view byte-for-byte unchanged. FOUNDER_CUTOFF_DATE placeholder 2026-12-31 to be set launch+30d on launch day. ¦¦ FIXED (commit 1e1656e -> merge e115ad5, 3 files). PricingPage: REGULAR_PRO_PRICING constant consolidates the twice-hardcoded regular prices (effectiveProPricing else-branch + PLANS spread, displayed values unchanged); founder-only anchor pricing — monthly: struck $8.99 before $7.99/mo; annual: struck $89.99 before "$69.99 billed annually" (big figure stays the $5.83/mo equivalent) + "Save $20/yr" chip reusing the Free-card teal pill tokens (#E0F0F4/#134756, no amber); title=/Info icon/cursor-help removed; full caveat now always-visible small print. PaywallModal: identical treatment via its REGULAR_DISPLAY/FOUNDER_DISPLAY; useBillingConfig extraction untouched (backlog). founderPricing.ts (SERVER config — no client file by that name) comment-only fix distinguishing flag (eligibility, survives cancellation) from rate (forfeited per ToS), honestly noting forfeiture is NOT yet enforced in code -> spawned FOUNDER-FORFEIT-1. Verified: client build + server tsc clean; non-founder DOM identical; chip whitespace-nowrap, line wraps safely on mobile. Benny test: /pricing founder view both toggle states + PaywallModal on momannexpired, then push. ¦¦ 06-10: Benny verified in-app (both toggle states + PaywallModal) and pushed. Closed.
STRIPE-PRICE-1 | Verify Stripe price IDs match displayed prices — diagnostic snapshot shows regular ANNUAL price ID at $69.99 (founder figure) vs displayed $89.99 | Bug? | Billing/Stripe | P1 — High | DONE (06-10) — verified TEST mode; re-verify at live flip | No — Stripe dashboard, not code | BILL-FOUNDER-1 scout 06-10 | stripe-checkout-snippet.txt:188-189 (captured diagnostic) shows STRIPE_PRO_ANNUAL_PRICE_ID at "$69.99 USD/year, active" - the FOUNDER annual figure on the REGULAR annual price ID. If that reflects live Stripe config (not a stale capture), regular annual subscribers would be undercharged $20/yr against the displayed $89.99. ACTION (Benny, manual, ~2 min): open Stripe dashboard and verify all four price IDs - regular monthly $8.99, regular annual $89.99, founder monthly $7.99, founder annual $69.99. Must be confirmed before launch / before the Stripe live flip (PROD-5). Per standing rule, billing/permissions config is Benny-run; Claude does not touch Stripe. ¦¦ RESOLVED via DISC-CCFIRST route: built server/scripts/verify-stripe-prices.js (bd08290 -> merge 24f289a, read-only stripe.prices.retrieve only, exits 1 on failure). Live run (TEST mode): ALL 4 PASS — regular $8.99/mo + $89.99/yr, founder $7.99/mo + $69.99/yr, all usd/active/correct interval, product RoamReady Pro. The $69.99-on-regular-annual reading in security-tests/stripe-checkout-snippet.txt was a STALE CAPTURE; regular annual env var now points to a different price ID at $89.99. Bonus: script FAILs if server STRIPE_*_PRICE_ID and client VITE_STRIPE_* pairs disagree (catches client checking out at a different price than the server guard expects). Command: node server/scripts/verify-stripe-prices.js from repo root. CAVEAT: TEST keys verified — MUST re-run with live keys at the PROD-5 Stripe live flip (reminder added to PROD-5 row). Push pending at close time.
DISC-CCFIRST | CC-first lookup rule: scriptable lookups/verifications go through Claude Code, never manual dashboard hunts | Rule | Workflow | P1 — High | ACTIVE RULE | N/A — rule | Benny directive 06-10 | Born from STRIPE-PRICE-1: Benny spent ~10 min lost in the Stripe dashboard before Claude offered the obvious read-only API script. RULE: if a lookup, verification, or config check CAN be done via a CC script/command (reading env vars, querying APIs with existing keys e.g. Stripe, checking DB/config state), ALWAYS lead with the ready-to-paste CC prompt. Manual dashboard/UI steps only when no scriptable path exists, or for the one residual action a script cannot do (then give an exact click-path for just that screen). Also stored in Claude memory; goes in every recap working-rules section.
FOUNDER-FORFEIT-1 | Founder-rate forfeiture (ToS: cancel-and-rejoin pays regular rate) is NOT enforced in code — returning founders still get founder price IDs | Bug? | Billing/Server | P2 — Medium | DONE (06-10) — VERIFIED on dev; push pending | Yes — scout checkout path after decision | BILL-FOUNDER-1 build 06-10 | Found during BILL-FOUNDER-1: checkout selects founder price IDs off the founderPricing flag ALONE, and the flag survives cancellation — so a founder who cancels and rejoins is still charged $7.99/$69.99, contradicting BOTH the ToS ("billed at the then-current standard rate" on rejoin) AND the new always-visible badge caveat shipped 06-10. The app currently makes a written promise billing does not keep. DECISION (Benny): (1) RECOMMENDED — enforce forfeiture: server-side at checkout-session creation, founder with a previously-cancelled subscription gets REGULAR price IDs (ToS, copy, and billing align; founder urgency stays true); needs a scout of the checkout/session path + how to detect prior cancellation (Stripe subscription history vs local flag demotion). OR (2) be generous on purpose: founders keep the rate even after cancel/rejoin — zero code, but soften the ToS clause AND the badge caveat in PricingPage + PaywallModal to match. Only fires when a founder cancels then rejoins — not blocking current pushes, but MUST be decided before live money (pair with PROD-5). ¦¦ DECISION 06-10: Benny chose option (1) ENFORCE - server charges regular price IDs to founders who previously cancelled; ToS + badge copy stand as written. Read-only scout drafted covering: checkout-session creation + current price-ID selection, founderPricing eligibility semantics, Stripe webhook handlers + schema subscription fields, whether any persisted record of a prior ended PAID subscription exists, and edge facts (expired trial must NOT count as forfeiting; active-subscription checkout paths). Design pick after scout: webhook-set forfeit flag vs Stripe-history check at checkout. ¦¦ SCOUTED 06-10 (key facts): client picks priceId; server only validates against the 4 env IDs + the one founder gate (subscriptions.ts:111-121, flag-only). founderPricing stamped at signup from FOUNDER_CUTOFF_DATE clock (auth.ts:100-116, passport.ts:42-52), never flips, read by PricingPage/PaywallModal/checkout guard//me/cron email. subscription.deleted handler (subscriptions.ts:331) writes tier=FREE + subscriptionId=null, records NO cancellation timestamp; no subscription-history table; strongest implicit prior-payer signal is trialEndsAt=null (only nulled by paid checkout); customerId NOT proof of payment (created on demand pre-session); involuntary churn (payment_failed -> Stripe gives up) emits the same deleted event — distinguishable only via cancellation_details.reason (currently ignored). DESIGN PICKED: demote-the-flag — in the subscription.deleted handler, if founderPricing && cancellation_details.reason === cancellation_requested (VOLUNTARY only), set founderPricing=false + new founderRateForfeitedAt timestamp (one nullable column, migration add_founder_rate_forfeited_at — preserves founder history for support). Everything downstream aligns automatically (display, price-ID selection, guard, emails) — zero checkout/client changes. Timing correct by construction: deleted fires at period end (continuously-active ToS wording); reactivation before period end never triggers. Accepted gap: accounts that paid-and-cancelled BEFORE ship keep the flag (pre-launch = test accounts only). Build prompt drafted incl. migration drill + Stripe CLI/manual test steps. ¦¦ BUILT (commit 7253278 -> merge 1ab77fe, 3 files). schema.prisma: founderRateForfeitedAt DateTime? added + founderPricing comment corrected; migration add_founder_rate_forfeited_at applied to dev (33 migrations, up to date) — NOTE: auto-generated SQL again included the phantom ALTER COLUMN search DROP DEFAULT against the GENERATED tsvector FTS column; failed attempt marked rolled back, migration hand-trimmed to the ADD COLUMN only, re-applied (second occurrence of this pattern). subscriptions.ts:331 deleted-handler: founderPricing=true AND cancellation_details.reason=cancellation_requested -> founderPricing=false + founderRateForfeitedAt=now + log; any other/missing reason keeps the rate; existing writes + grace-period subscriptionEndsAt untouched. No other code — demotion realigns display/price-ID selection/guard//me/cron automatically. LAUNCH_STATUS.md does not track founder pricing (left alone). Server tsc clean (as-any cast pending prisma generate after backend stop). PENDING: Benny pre-test gate (stop backend -> generate -> restart -> Stripe portal-cancel test -> verify DB + /pricing) then push; check Render logs for the migration. ¦¦ VERIFIED 06-10: dashboard Cancel-Immediately fired customer.subscription.deleted -> 200; list-users.js shows momann FREE + founderPricing=false — demotion fired on the voluntary-cancel reason exactly as designed. (First attempt taught the lesson: portal/default cancels are AT PERIOD END and emit only subscription.updated — no deleted event until period end. Immediate cancel required to exercise the handler same-day.) Remaining: founder flag restore on dev via set-founder.js --grant, then push.
CLEANUP-1 | Dead-code micro-sweep: 2 stale SaveHomeAddressModal comment refs + 2 orphan wordmark PNGs | Chore | Client/Hygiene | P3 — Low | OPEN — batch with next client session | No | RR35-AUDIT 06-10 | From the 06-10 audit: (1) stale comment references to the removed SaveHomeAddressModal at types/index.ts:237 and HomeBaseCard.tsx:13; (2) orphan PNGs in client/public (roamready-wordmark-transparent.png, roamready-wordmark-white-bg.png) referenced nowhere since the SVG replaced them. Five-minute deletion pass — fold into the next client-touching CC session rather than its own run.
WEBHOOK-500-1 | customer.subscription.updated webhook handler returns 500 intermittently (matched-user events crash; orphan no-ops 200) | Bug | Billing/Server | P1 — High | DONE (06-10) — VERIFIED on dev; push pending | Yes — scout first | Stripe tunnel log 06-10 | Found during the FOUNDER-FORFEIT-1 dev test. Tunnel log 06-10 01:22:19/:45/:46 shows three customer.subscription.updated events returning 500 while others return 200. Pattern: 500s coincide with events matching the DB user; 200s with orphan subs (findFirst miss -> no-op before the crash point). LEADING THEORY (unconfirmed): Stripe API 2025-03-31+ moved current_period_end from the Subscription object to subscription.items.data[].current_period_end; the updated handler writes subscriptionEndsAt=current_period_end from the OLD location -> undefined -> Invalid Date -> Prisma throw -> 500. CLI shows API version 2026-03-25 (new shape). P1 because prod portal plan-changes arrive as exactly this event, and subscriptionEndsAt drives the paid-through grace period. Scout drafted: handler field reads, stripe pkg + pinned apiVersion, error logging path, and whether checkout.completed/deleted read period fields the same vulnerable way (completed 200d tonight but may have written subscriptionEndsAt silently wrong/null). Also from same log: all of Benny cancels were at-period-end (subscription.updated), zero deleted events — forfeit test redo via dashboard Cancel-Immediately in progress. ¦¦ SCOUTED 06-10, THEORY CONFIRMED: subscriptions.ts:325 reads sub.current_period_end at top level only and writes new Date(cpe*1000) with NO guard, inside if(user) — post-basil payloads (CLI 2026-03-25; any 2025-03-31+ endpoint) carry the field only at sub.items.data[].current_period_end -> undefined -> Invalid Date -> PrismaClientValidationError -> 500 on matched users only (orphans no-op 200). stripe pkg 16.12.0; client pinned apiVersion 2024-06-20 (governs OUTBOUND retrieve calls, NOT webhook payload shape). completed handler is SAFE (retrieves via pinned API + guarded :240-252, degrades to null); deleted handler reads no period fields. Errors logged via errorHandler console.error + Sentry; the :19/:45/:46 clustering = Stripe retries. FIX DRAFTED: dual-shape read (top-level ?? items.data[0]) + completed-style guard, OMIT subscriptionEndsAt when absent (never write null — grace period), warn log; tier write stays; apiVersion pin untouched. VERIFY: restart backend (no migration), resubscribe, updated events during checkout must 200 (they 500d at 01:22:19). PROD CHECK: stripe webhook_endpoints list -> if a prod endpoint pins 2025-03-31+, prod has been 500ing this event already. ¦¦ FIXED (commit fc852b0 -> merge c6dc24c, subscriptions.ts only, +23/-1, updated case only): dual-shape read (top-level ?? items.data[0].current_period_end) with comment that payload shape follows the SENDER api version not our pinned client; subscriptionEndsAt included in the update ONLY when typeof cpe === number && cpe > 0, otherwise field OMITTED (never null — grace period preserved) + warn log; tier write unconditional within if(user); completed/deleted handlers + 2024-06-20 pin untouched. tsc clean. VERIFY PLAN: restart backend -> cancel-immediately (forfeit test) -> resubscribe watching tunnel: updated events that 500d at 01:22:19 must now 200. ¦¦ VERIFIED 06-10: resubscribe checkout run — customer.subscription.updated events returned 200 (same event type that 500d at 01:22:19 pre-fix). Closed pending push.
PROD-WEBHOOK-1 | No Stripe webhook endpoint exists AT ALL — prod cannot receive any Stripe events (subscriptions would never activate on the live site) | Bug | Billing/Prod | P1 — High (launch blocker) | DONE (06-10 late) — pending morning verification | No — confirmed via stripe webhook_endpoints list | CLI check 06-10 | Discovered via stripe webhook_endpoints list (test mode): data is EMPTY — zero dashboard/API-created endpoints. Dev only works because the CLI tunnel forwards events; prod (roamready-api on Render, test-mode keys) has no endpoint and has never received a Stripe event. Consequence: a prod checkout would charge the card but the DB would never flip to PRO (same symptom as tonight closed-tunnel dev test). No damage yet — nobody has subscribed on prod (PROD-2 not run). SEQUENCE: (1) ship WEBHOOK-500-1 fix FIRST — a new endpoint will pin a post-basil API version, the exact shape the unfixed handler 500s on; (2) push/deploy; (3) create the endpoint via CLI (DISC-CCFIRST): stripe webhook_endpoints create --url https://roamready-api-klx5.onrender.com/api/v1/subscriptions/webhook with enabled_events checkout.session.completed, customer.subscription.updated, customer.subscription.deleted, invoice.payment_failed — creation response includes the whsec signing secret (only shown once); (4) put that secret in STRIPE_WEBHOOK_SECRET on Render roamready-api env (env save triggers restart); (5) verify with a prod test checkout during PROD-2. NOTE: dev .env keeps the CLI listen secret; prod gets the endpoint secret — different values is correct. At the PROD-5 live flip, a LIVE-mode endpoint must be created the same way (added to PROD-5 checklist). ¦¦ 06-10 late: Benny executed steps A-D — pushed, Render deploy, endpoint created via CLI (4 events), whsec set as STRIPE_WEBHOOK_SECRET on Render roamready-api. Morning RR36 scout verifies: endpoint list shows 1 correct endpoint, push status, prod migration. First real prod event lands during the PROD-2 test checkout.

## Legend & How to use
RoamReady — Bug & Todo Tracker
¦ Updated 2026-06-09 PM: appended RES-1, FUEL-LOG-1, RES-2 (all DONE this afternoon) and MAINT-1 (OPEN — scout next). Marked CHAT-PUSH DONE (batch pushed). Claude now owns/maintains this tracker file directly (Benny does not edit it). ¦ Updated 2026-06-09 PM (2): added ROADMAP-LOC (move roadmap tile -> Help) and ADMIN-GRANT (mobile admin link + grant isOwner to momann/Cindy on dev). Both in progress. ¦ Updated 2026-06-09 PM (3): closed ADMIN-GRANT (admin live on prod desktop+mobile, momann+Cindy owners); added COST-LINK (in progress), JOURNAL-STOPS + JOURNAL-ROUTESTOP (queued, scout next). MAINT-1 still pending scout. ¦ Updated 2026-06-10: RR35 post-batch verification ALL GREEN — full 06-09 PM batch pushed (origin==main @ 0606276), all key commits present, prisma dev clean (32 migrations, up to date), add_journal_routepoiid confirmed applied on PROD (Render deploy logs), app spot-checks passed (RES-2 distance ranking, route-stop journal save, journal edit/delete, Help redesign + feedback modal). MAP-LEGEND-FINISH-DUP found already fixed in history (d4653bb/db2917e) -> marked DONE. JOURNAL-ROUTESTOP fully verified on prod. MAINT-1 scope decision pending. ¦ Updated 2026-06-10 (2): added GREET-TZ-1 (greeting timezone mismatch Dashboard vs Home, scout drafted). ¦ Updated 2026-06-10 (3): GREET-TZ-1 fixed + merged (adc7f8b/801a849) — Dashboard greeting now shares Home hour buckets via exported getSalutation(); push pending. ¦ Updated 2026-06-10 (4): added DASH-HEADER-1 (replace Dashboard greeting with Resources-style title; supersedes the visible part of GREET-TZ-1, timeBucket refactor retained). ¦ Updated 2026-06-10 (5): DASH-HEADER-1 DONE (b7a5f27/c733b3a, push pending — 4 commits queued incl. GREET-TZ-1 pair); added AI-HUMOR-1 (P4 idea: humor in trip-build, deterministic loading-lines first). ¦ Updated 2026-06-10 (6): added PASS-SCROLL-1 (passes "+" opens form below fold without scrolling; scroll+focus fix drafted). ¦ Updated 2026-06-10 (7): PASS-SCROLL-1 fixed (eb5c4fa/dd04b43) — scroll-on-open shipped, focus deliberately skipped (iOS keyboard history); one re-click-different-pass test pending before clean close. GREET/DASH-HEADER pairs appear pushed (main advanced via Progress save). ¦ Updated 2026-06-10 (8): PASS-SCROLL-1 verified + pushed — closed. DASH-HEADER-1/GREET-TZ-1 confirmed pushed. ¦ Updated 2026-06-10 (9): added BILL-FOUNDER-1 (hover-only founder rate -> inline anchor pricing; scout drafted to pull real regular-rate numbers first). ¦ Updated 2026-06-10 (10): BILL-FOUNDER-1 scouted (founder $7.99/$69.99 vs regular $8.99/$89.99; fix prompt drafted - strikethrough anchor + Save $20/yr chip + visible caveat). Added STRIPE-PRICE-1 (P1: regular annual price ID may be set to $69.99 - Benny to verify all four price IDs in Stripe dashboard before launch). ¦ Updated 2026-06-10 (11): added DISC-CCFIRST ACTIVE RULE (scriptable lookups go through CC, not dashboards — born from the Stripe price-ID hunt). ¦ Updated 2026-06-10 (12): STRIPE-PRICE-1 CLOSED — all 4 prices PASS in TEST mode via new verify-stripe-prices.js (bd08290/24f289a); $69.99 reading was a stale capture. Live re-run reminder wired into PROD-5. ¦ Updated 2026-06-10 (13): BILL-FOUNDER-1 DONE (1e1656e/e115ad5 — anchor pricing + visible caveat, test/push pending). Added FOUNDER-FORFEIT-1 (P2: ToS forfeiture not enforced in checkout — enforce or soften copy; decide before live money, paired with PROD-5). ¦ Updated 2026-06-10 (14): BILL-FOUNDER-1 verified + pushed - closed. FOUNDER-FORFEIT-1 decided: ENFORCE forfeiture; scout drafted. ¦ Updated 2026-06-10 (15): FOUNDER-FORFEIT-1 scouted + designed (webhook flag demotion, voluntary-cancel only, founderRateForfeitedAt migration); build prompt drafted. ¦ Updated 2026-06-10 (16): FOUNDER-FORFEIT-1 BUILT (7253278/1ab77fe) — webhook flag demotion + founderRateForfeitedAt migration; pre-test gate + push pending. Phantom tsvector migration trim logged as standing gotcha on DISC-1 (2nd occurrence). RR35-AUDIT scout queued next in CC. ¦ Updated 2026-06-10 (17): RR35-AUDIT reconciled — CLOSED: EV-1 (P1, email verification shipped end-to-end), TM-2, TM-3, WMK-1, PROF-2 (obsolete), SCROLL-BEHAVIOR-1 rollout, TEST-ACCTS (email corrected to momannexpired@roamready.test). TM-1 LIKELY FIXED pending one manual confirm. Confirmed open: TM-5, AUDIT-1, PW-1/2/3, PROD-4 (nuanced). OHV-CHECK 2/3 done (trigger registration remains). Added CLEANUP-1 (stale comments + orphan PNGs). ¦ Updated 2026-06-10 (18): TM-1 confirmed in-app and CLOSED. ¦ Updated 2026-06-10 (19): added WEBHOOK-500-1 (P1 — subscription.updated handler 500s on matched users; suspected current_period_end API-shape change; scout drafted). Forfeit test pending redo via Cancel-Immediately (period-end cancels emitted no deleted events). ¦ Updated 2026-06-10 (20): WEBHOOK-500-1 root-caused (unguarded top-level current_period_end read vs post-basil payload shape); fix prompt drafted; prod webhook-endpoint api_version check queued. ¦ Updated 2026-06-10 (21): added PROD-WEBHOOK-1 (P1 LAUNCH BLOCKER — zero Stripe webhook endpoints exist; prod deaf to all billing events; endpoint creation sequenced after WEBHOOK-500-1 fix ships). PROD-5 checklist gains live-mode endpoint step. ¦ Updated 2026-06-10 (22): WEBHOOK-500-1 fixed (fc852b0/c6dc24c, dual-shape guarded read); combined verify pass queued (forfeit cancel-immediately + resubscribe 200s + set-founder restore) then push + prod endpoint creation. ¦ Updated 2026-06-10 (23): FOUNDER-FORFEIT-1 VERIFIED on dev (FREE + founder=false after immediate cancel) — closed pending push. WEBHOOK-500-1 resubscribe verify next. ¦ Updated 2026-06-10 (24): WEBHOOK-500-1 VERIFIED (updated events 200 on resubscribe) — closed pending push. ¦ Updated 2026-06-10 (25): dev test-account tidy noted on TEST-ACCTS (founder grant pending + DB/Stripe sub mismatch from closed-tunnel checkout). Prod endpoint creation steps A-D in flight. ¦ Updated 2026-06-10 (26): END OF DAY — PROD-WEBHOOK-1 executed (endpoint + secret on Render), pending morning verification. Recap roamready-recap-2026-06-10.docx delivered with RR36 verify scout + handoff.
Built ¦ Updated 2026-06-09: marked MOBILE-CHAT-HDR + FT-1 resolved; appended JBANNER-1, AI-ORIGIN-1, AI-FT-LEAK-1, VEH-PICKER-1, CHAT-DEADSPACE-1, CHAT-PUSH, CHAT-RESTBOTTOM, TRIPS-BOX-TALLER from the 06-09 mobile-chat-rebuild + bug-fix session. NOTE: 06-09 batch was local/unpushed at recap — CHAP-PUSH tracks landing it. | 2026-06-02 from LAUNCH_STATUS.md (audit basis 2026-05-28), session recaps 05-23 & 05-27, and this session's OHV work. ¦ Updated 2026-06-02: appended PROD-1..6 + DISC-1 from the production-deployment (Render) session. ¦ Updated 2026-06-02 evening: appended HOME-MODAL, PROF-1, AI-MESA-1 (all DONE, verify in browser) + PROF-2 (design done, build AM).
IMPORTANT — staleness | DONE items come from the 2026-05-28 audit, not a live re-check. Anything with 'Verify vs current code?' = YES should be re-verified against current main before you trust it for launch. This is the stale-April-audit lesson.
Priorities are PROPOSALS | Each priority is Claude's suggestion with rationale in Notes. You own the launch calls — the Priority and Status columns are dropdowns; override freely, then re-sort/filter.
Priority key
P0 — Launch blocker | Must fix before launch. Currently only AI-path items, all marked DONE — re-verify.
P1 — High | Strongly want before launch or right after; real user-facing damage.
P2 — Medium | Should fix; not catastrophic at launch.
P3 — Low / cosmetic | Polish / cleanup; safe to defer.
P4 — Post-launch | Explicitly deferred; logged for later.
Status colors | Green = DONE/VERIFIED · Red = OPEN · Amber = SCOUT needed
Gap to close | This sheet is built from docs + memory, NOT a live repo read. For a fully authoritative version, run a CC scout that dumps all 3 LAUNCH_STATUS.md tables + greps the code for TODO/FIXME, and reconcile against this sheet.