## Bug Tracker
RoamReady.ai — Bug Tracker
Updated mid-RR53 (marketing opt-in, budget fix, Mexico map-pin, trip-shape, booked-deeplink, time picker/PDF crash, leg directions + refinement, booked address). Claude owns this file. Open on top; completed (green) hidden.
ID | Title / Symptom | Severity | Source | Status | Resolution / Notes
BUG-MODIFY-INTENT-CONFUSION | “Create a stop in [city]” on an open trip is sometimes mistaken for new-trip planning; AI asks planning questions instead of adding the stop | P2 | User test (Benny) | Done | FIXED (prompt-only): added a change-destination path (remove old + add new, carry over nights) + a guard so modify mode never re-asks origin/start-date/total-nights + scoped the clarifying-question line. Tester-confirmed + local-tested ('change destination to Denver' swaps cleanly, no re-interrogation). Local main.
TZ-OFFBYONE | Off-by-one dates on weather day, journal edit prefill, reservations bucketing, admin session inspector | P2 | User test (Benny) | Done | Routed four surfaces through parseTripDate; weather day numeric. Pushed.
BUG-ROUNDTRIP-MODIFY-DROP | Round trip on an already-built trip via modify did not insert the return leg | P1 | Prod behavior | Done | buildModifyInstructions gained a round-trip action. Pushed.
BUG-ROUNDTRIP-PLANNING | Mid-planning “make it a round trip” didn’t rebuild; malformed <modify> tags leaked | P2 | User test (Benny) | Done | Planning re-emits full itinerary inline; stray tags scrubbed; strip regex broadened. Pushed.
BUG-AI-NODATE-ASK-B | recomputeStopDates fabricated + persisted today’s date for dateless trips (silent fake DB write) | P1 | CC audit | Done | Leaves stop dates null when no real anchor. Anchor path byte-identical. Pushed.
BUG-PDF-TOSTRING | Cindy’s PDF crashed on free-text times without a colon (“3pm”) | P1 | Prod user (Cindy) | Done | Finite-check fallback to raw string. DEPLOYED TO PROD (roamready-client).
STORED-NIGHTS-OFFBYONE | Stored Stop.nights one short for stays entered as “N days” via modify (9-day stay stored as 8) | P1 | User test (Benny) | Done | Root: modify prompt said days-minus-1 while planning said days=nights. Aligned both + added date-range rule. Pinecrest row corrected manually + backfill. Pushed. (Fresh-thread test pending.)
ITIN-NIGHTS-MISMATCH | Itinerary stay card showed 3 disagreeing numbers (badge 8 / span 8 / cost 9) for one stop | P1 | User test (Benny) | Done | Display-only fix: badge, date range, day-span all show true booked window (true nights, arrival→checkout). PDF matches. Pushed.
BUG-MODIFY-ADDSTOP-SEQUENCE | Stop added via modify landed in the wrong geographic position (Fort Stockton before Toyahvale) | P2 | User test (Benny) | Done | Server geocodes the new stop + re-slots only it by min-added-detour; origin/finish/booked pinned. Pushed.
BUG-PLAN-BUILD-DIVERGE (Part 1) | Built trip differed from approved plan: phantom transit stop + scrambled nights | P1 | User test (Benny) | Done | Part 1 (build verbatim) + Part 2 (server-sole drive-time check) COMPLETE. See BUG-PLAN-IS-TRUTH-P2. Pushed status: local main.
BUG-LONGLEG-CANT-DELETE | User couldn't delete a transit/overnight stop on a still-over-cap leg — recheck immediately re-inserted it, overriding the user | P1 | User test (Benny) | Done | Design fix: replaced silent enforcement with a confirm modal ('Remove this overnight stop?') showing real merged-leg hours. Confirm = delete + acknowledge leg (suppress re-insert); cancel = restore. Ack persists; resets if leg endpoints change. Local main.
BUG-RECHECK-DELETE-INVISIBLE | Delete on map-page trash-can appeared to skip drive-time recheck (no log, no overnight on a 6.5h merged leg) | P2 | User test (Benny) | Done | Not a bug — recheckLongLegs ran but only logged on insert; 6.5h leg was within the 1h grace (cap 6h tolerates 7h). Fixed by adding full observability logging on every recheck path + per-leg hours. Local main.
BUG-LONGLEG-ACK-NO-SESSION | Keep-long-drive acknowledgment stored in planning session — a session-less Trip would silently drop it (latent, not user-reachable today) | P3 | CC audit | Done | Moved ack to Trip.acknowledgedLongLegs JSONB column (migration 20260625120000, applied). Latent future-proof; every current user trip has a session. Cleaner design, removes session dependency. Local main.
DEAD-CREATETRIP-ENDPOINT | createTrip (POST /trips) is a live auth-gated endpoint with NO in-app caller; tripsApi.create is dead client code | P3 | CC audit | Open | Decision for later: either wire a manual 'blank trip' create flow, or retire the endpoint + dead client method. Not urgent. Logged RR52.
BUG-MODIFY-GHOST-ROUTE | After an AI-modify destination change, the old map route line ('ghost path') stayed drawn until a manual page refresh | P2 | User test (Benny) | Done | Two causes: (1) route polyline dedup key wasn't invalidated on modify apply so it short-circuited the redraw; (2) geocoding effect had no .catch — a failed coord write left geocoding stuck true, permanently gating the route redraw until reload. Fix: invalidate dedup key on onTripUpdated + add .catch resetting geocoding flag. Client-only, local main.
MODIFY-CLARIFY-VERBOSE | When user references a stop not on the trip ('go to Boise instead of Salt Lake City' when SLC isn't a stop), AI gives a wordy 'I don't see X' clarifying reply | P3 | User test (Benny) | Open | Not a bug — AI correctly won't guess which stop to swap (guessing = silent wrong-swap risk). Low-pri tone item: could make the clarifying question tighter/less wordy. Do NOT make it guess. Logged RR52.
BUG-PLAN-ORIGIN-LOOP | Planning sometimes re-asks for the starting location. Fixed common cases (bare 'X to Y', arrow 'X→Y', abbrev 'KC') but still flaky on run-together phrasings where night-count abuts the date ('3 nights july7') | P2 | User test (Benny) | Done | PARTIAL FIX shipped RR52: extractFromXtoY now handles 'X to Y', 'from X to Y', 'X → Y', abbreviations (KC→Kansas City). REMAINING: phrasings like '...3 nights july7' / '3 nights july2' (no separator between nights and date) still sometimes trigger the origin question. Inconsistent → parser fragile on the string tail. Tomorrow: harden parse for nights/date run-together. Open. ¦¦ RR53 FIX: bare "X to Y" origin capture (anchored to msg start, both-sides proper-noun guard, STOP set extended incl trip/flight/road to kill "Trip to Miami" false positive). 15/15 regression test (extractFromXtoY.test.ts). Commit fe4107e. Tested live. Pushed RR53 batch.
BUG-PLAN-BUILD-DIVERGE (Part 2) | Server now sole transit-stop inserter; honest measured drive-time notes; deterministic over-cap splitting | P1 | Session arc | Done | Whole Plan-is-Truth Part 2 arc. Server measures real Google drive times, inserts overnight transit stops, builds honest grounded notes from measured legHours. AI insertion rule removed. Tested across many live trips RR52. DEPLOYED (auto-deploy fired earlier). Local main has follow-on fixes below.
BUG-MODIFY-ONEWAY-ROUNDTRIP | Converting a round trip to one-way failed: removing return-home KC tripped the 'cannot delete home departure' guard, leaving trip half-modified | P2 | User test (Benny) | Done | Atomic makeOneWay server action: truncates everything after the turnaround (farthest-from-origin via Haversine). Guard now protects only the FIRST stop (departure), not every HOME. New make_one_way modify action wired through prompt+client. Built+merged local main, not yet runtime-retested on a fresh round trip (do tomorrow).
BUG-TITLE-DRIFT | Trip title mismatched destination (showed 'Portland, MO' / 'Indianapolis' instead of real destination) and didn't update on destination change | P2 | Tester FB-MYE1 + Benny | Done | Title now DERIVED from the turnaround (farthest-from-origin destination), flexible during planning, locked at Build, manual rename after. Fixed the round-trip 'picks return-leg city' bug (was showing Indianapolis; now correctly Bangor). Tested working RR52.
BUG-BUDGET-NONDETERMINISTIC | Budget-conflict refusal fired inconsistently for identical input (same trip built twice, refused once) and named a return-leg city, because it computed from the AI's variable per-run build | P1 | User test (Benny) | Done | Root cause: gate computed from AI's variable itinerary. Fix: minimalTripBudget computes conflict from the MINIMAL trip (origin→turnaround→origin), stable across runs. minNeeded=1+coreTransit (×2 round trip). Refusal now deterministic, names the turnaround (Bangor), states the minimum, offers to bump; 'yes bump it' builds at minNeeded. Tested 3× consistent build (10n) + 3× consistent refuse (3n) + one-way lower min (5). Local main.
BUDGET-REFUSAL-MIN-WOBBLE | Budget refusal fires deterministically but the quoted MINIMUM nights number wobbles across runs (e.g. '5-6' vs '9') because the AI paraphrases instead of stating the exact computed minNeeded | P3 | User test (Benny) | Done | The DECISION (refuse) is deterministic and the system HAS the right number (built at 9 when accepted), but the prose sometimes quotes a wrong lower estimate (5-6) instead of the computed minNeeded. Prompt-tightening: force the refusal to state the EXACT computed minNeeded verbatim, not an AI estimate. Same 'server stamps truth, model reports it' principle. Logged RR52. ¦¦ RR53 FIX: verbatim-echo of app-computed minNeeded + HISTORY_CAP defer guard + clause 3 (forbid fabricated miles/hours/driving-days/radius in budget justification; geography OK). Commits 2370553 + ac88959. Tested live AFTER clean restart: "why so many nights?" returns qualitative geography, zero fabricated numbers. Pushed RR53 batch.
FEAT-THREE-OPTION-REFUSAL | [Enhancement] When a trip can't fit requested nights, offer THREE paths not two: (1) add nights, (2) pick closer, (3) NEW: keep the nights & drive longer days (back-solve the required drive cap) | P2 | Benny idea | Open | Benny has 3 drivers, wants the option to keep tight nights by raising the daily drive limit. Recommended approach (Option A): back-solve the drive cap needed to fit requested nights and offer the specific number ('to keep 10 nights I'd stretch your driving to ~8h/day, OK?'). Real (possibly iterative) logic — its own focused build. Build on the now-deterministic minimalTripBudget foundation. Deferred to fresh day. Logged RR52.
UX-TRANSIT-NIGHT-INFLATE | [UX] Requested nights + required transit overnights inflate the displayed total (10 nights shows as 12-15n badge); disclosed in honest notes but the badge contradicts what the user typed | P3 | User test (Benny) | Open | Not a bug (Check C — mild overshoot allowed by design; every added overnight is explained in the honest drive-time notes). UX polish: panel could distinguish 'N nights at destinations + M driving nights = total' so the badge doesn't contradict the typed number. Deferred. Logged RR52.
BUG-BUDGET-SHAPE-MULTIPLIER | Stated minimum nights swings (e.g. 5→9) for identical trip input across turns because minNeeded's ×2 round-trip multiplier reads trip SHAPE from the AI's per-turn itinerary, which can flip one-way→round-trip between turns | P2 | User test (Benny) | Done | Found RR53. minNeeded = 1 + coreTransit, coreTransit = oneWayTransit ×(round-trip?2:1). Distance is deterministic; the ×2 shape multiplier follows the AI's emitted stops (computeTripShape reads last-stop-returns-to-origin). RR52 BUG-2 fix anchored DISTANCE to the minimal trip but still reads SHAPE + turnaround from AI stops. Fix: derive shape deterministically from the request (return language / explicit round-trip), not from AI's emitted itinerary. NOT caused by RR53 batch (both budget commits are prompt-only). Its own focused build. ¦¦ RR53 RESOLVED by structural pre-build budget fix: trip shape now derived deterministically via server-ported roundTripIntent (not AI per-turn itinerary). minNeeded stable across runs (one-way 4×5, round-trip 7×5). Commit b8c96fa. Pushed origin.
BUG-MILEAGE-OPENING-TURN | Model still volunteers fabricated mileage ("1,600+ miles one-way") on the INITIAL trip-acknowledgment turn; clause 3 (RR53) only covers the budget-justification ("why so many nights?") path | P2 | User test (Benny) | Done | Found RR53. Clause 3 verified working on the budget-justification turn (qualitative geography, no numbers) but the opening "KC to Bangor, 3 nights" acknowledgment turn still fabricates total mileage. Same leak class, adjacent path clause 3 doesn't reach. Recommended fix: lift the no-quantified-mileage/hours prohibition into criticalRulesBlock (high-salience, ALL turns) rather than another co-located clause. Pairs well before FEAT-THREE-OPTION-REFUSAL (keeps its drive-cap math honest). Its own focused build. ¦¦ RR53 RESOLVED by structural fix: app owns budget minimum pre-build (deterministic <destination> capture + parser primary). Model never states mileage/hours/days/nights — canonical suffix rule covers all turns; interim OPENING FLOW timing clause + BUDGET MINIMUM hedging DELETED/superseded. Tested 6/6 incl both-gates coexist. Commit b8c96fa. Pushed origin.
DEVENV-WSL-MIGRATIONS | [Dev env] Windows Smart App Control now blocks Prisma's unsigned schema-engine-windows.exe — local `migrate deploy`/`migrate diff` fail (EPERM/spawn). Worked around RR53 via Docker-container psql + manual _prisma_migrations INSERT. Recurs on EVERY future local migration. | P2 | Dev env (RR53) | Open | DURABLE FIX: run Prisma migrations from WSL (Linux schema engine, never subject to Windows SAC; applies + records _prisma_migrations atomically — no manual SQL surgery). Do NOT disable SAC (was irreversible pre-Dec2025; now reversible but global on/off, worse than WSL). prisma generate is NOT blocked (in-process WASM) — only the migrate schema engine. Next-session setup task. Logged RR53.
TEST-HARNESS-NOEXIT | [Dev env] CC test runners (extractFromXtoY.test.ts, prebuildBudget.determinism.ts) don't self-terminate on Windows — orphaned tsx/node processes accumulate (24 seen RR53), hold the query-engine DLL handle, and cause EPERM on `prisma generate`. Root cause of the RR53 generate-blocking saga. | P3 | Dev env (RR53) | Open | The determinism harness makes live Google Directions calls and hangs without exiting; unit runners stack up across runs. FIX: add a timeout + explicit process.exit() to the test harnesses so they terminate cleanly. Mitigation meanwhile: kill orphaned node by __tests__ command-line match before `prisma generate`. Logged RR53.
BUG-TRIP-MAPPINS-MX | Foreign map-pin bug, 2nd instance: a MEXICAN stop drops its pin in central US (Colorado fallback) — same root as the RR46/47 Vancouver→Colorado bug. The RR47 Canada fix was country-specific and left the body alive; Mexico (and any non-US/CA country) re-triggered it. | P2 | User test (Benny) | Done | RR53 RESOLVED with the GENERAL fix (find the body, not the heads). TripMapPage.tsx geocode previously forced "USA" + US componentRestrictions on every non-Canadian stop → foreign cities resolved to a US fallback coord. Fix: force US for {2-letter US state OR full US-state name OR blank}, force CA for CA provinces, UNRESTRICTED for any genuinely-foreign present state (Google resolves the country) — no per-country enumeration, cures the whole class. Hardening commit added full US-state-NAMES (data stores mixed "AZ" + "Arizona" formats) which also closed the "Georgia" US-state-vs-country hole. Commits 2e7aece (general) + b4b909c (hardening). Pushed origin, verified on prod (Mexican stop now lands in Mexico). NOTE: pre-existing bad rows (wrong-but-present coords) do NOT auto-heal — geocoder only re-resolves null coords; scoped NULL-and-re-geocode repair needed for any already-saved bad trip (Docker-psql local / Render Shell prod). Data finding: locationState stored inconsistently (2-letter AND full name) — audit elsewhere for read assumptions.
BUG-TRIP-SHAPE-ASSUME | Planner ASSUMES round-trip when shape was not stated. User: "plan a trip to Rocky point mexico from mesa arizona" (one-directional, no round-trip language). AI correctly ASKED one-way-vs-round-trip; user answered only date+nights ("july 1st for 6 days"), leaving shape unanswered — AI then built Mesa→Puerto Peñasco→Mesa (added a return-home leg the user never requested, prose said "and back"). | P2 | User test (Benny) | Done | Found RR53 on prod. Decision LOCKED: planner must NOT assume trip shape when unstated — build the literal one-way reading, user adds return via modify if wanted (lean: option 1; option 2 = re-ask/block-build still open). Root to scout: build-path shape default vs the server-ported roundTripIntent recognizer (tonight's budget fix) — if build defaults round-trip while budget uses roundTripIntent, they DISAGREE; cleanest fix may be making the build path respect the same recognizer (one source of truth for shape). roundTripIntent on this phrasing should return ONE-WAY (no "and back"/"return"/"round trip" language). Specific failure: an explicitly-asked-but-unanswered shape question resolves to round-trip — likely a hardcoded round-trip default. Scout queued. ¦¦ RR53 RESOLVED (find the body): build path rubber-stamped the model's round-trip on ambiguous input while budget path used hasRoundTripIntent (split-brain). Fix: aligned stripUnrequestedReturnLeg to strip-unless-positive-round-trip-intent → build==budget==prompt one-way default on the shared recognizer. 21/21 regression both directions. Pushed + verified prod.
FEAT-BOOKED-DEEPLINK | "Booked" status badge deep-links to its reservation (opens expanded) | P3 | User req (Benny) | Done | RR53 SHIPPED. Booked badge (stops-list pill + map popup) deep-links to /trips/:id/booking?stopId=; on-load handler now also opens the target Edit panel expanded (autoOpenEdit prop + one-shot ref guard so close stays closed; captured-once deepLinkStopId so in-page nav never re-opens). Commits 4eafff7 + e6775da. Pushed + verified prod.
BUG-PDF-TOSTRING | PDF render crashed on free-text check-in/out times ("3pm" no colon → NaN → toString threw, killed whole @react-pdf render). Cindy-reported prod. | P1 | Cindy (prod) | Done | RR53 RESOLVED at source via the time picker. Free-text time field was the single producer of malformed values; rest of system already uses canonical "HH:MM". Replaced with 3-dropdown picker emitting "HH:MM" — malformed input now impossible. Legacy rows lazy-self-heal on next Save; PDF Number.isFinite band-aid kept as defense-in-depth. Commit 7f909a5. Pushed, PDF verified clean.
FR-TIME-INPUT-PICKER | Time picker for booking check-in/out (replace free text) | P2 | Roadmap | Done | RR53 SHIPPED (same commit as BUG-PDF-TOSTRING cure). 3 dropdowns/field (hr, min 00/15/30/45, AM/PM), default PM-in/AM-out, stored "HH:MM", legacy on-load parse + self-heal. Commit 7f909a5.
FEAT-LEG-DIRECTIONS | Google Maps directions link per leg on map + itinerary pages | P3 | User req (Benny) | Done | RR53 BUILT (testing). Shared directionsUrl helper (maps/dir/?api=1, coords-preferred + City,State fallback). Map: per-stop-row "Directions to <next>" + popup, last omitted, stopPropagation guard. Itinerary: "Directions" on each DRIVE leg. New tab, MapPin. Commit 8c332b6. On local main at log time. ¦¦ REFINED RR53: two origins per leg ("from my location" omits origin→GPS · "from previous stop"); booked stops route to the campground NAME not the city (destinationForStop, path A, no fetch). RE-ANCHOR FIX: links now route TO each stop (not the next) — start stop has no link, each stop links to itself with prior stop as "from previous"; itinerary DRIVE rows were already correct (untouched), only map page fixed. Pushed + verified prod.
FR-RATE-DECIMAL | Booking rate-per-night: auto-format to decimals (type 5500 → 55.00) | P3 | User req (Benny) | Open | RR53 deferred — parked after time picker + directions. Currency-input formatter on the rate field in ReservationSection. Small, self-contained. Next booking-form item.
BUG-BOOKED-ADDR-HIDDEN | Booked stop hid the campground street address (collapsed booked row AND the edit/update panel both dropped it; unbooked cards showed it). User needs the address to confirm directions land on the right place. | P2 | User test (Benny) | Done | RR53 RESOLVED. BookedRowCard (collapsed) + the Edit expansion (ReservationSection panel) never rendered cg.address though cg (bookedCg lookup) was in scope. Added cg.address line to BOTH states, same field/format/guard as the unbooked RecommendedCampgroundCard. Pushed + verified prod (shows collapsed + expanded).

## Features & Roadmap
RoamReady.ai — Features & Roadmap
Updated RR52. Open/upcoming on top by priority; shipped (green) hidden — reveal via the Status filter.
ID | Feature | Priority | Status | Notes
PLAN-IS-TRUTH-PART2 | Real Google drive-time check DURING planning — transit stops appear in the approved plan + AI explains them honestly | — | Shipped | RR52 COMPLETE. Server measures real Google drive times during planning + is sole transit-stop inserter; AI stopped fabricating compliance; honest grounded notes (planning + modify); every stop-mutation path funnels through recheckLongLegs; keep-long-drive confirm modal; ack on Trip column. Built + merged local main. NOT pushed/deployed.
FR-MARKETING-OPTIN | Marketing opt-in popup after signup | P2 | Shipped | RR53 SHIPPED + DEPLOYED. Opt-in modal at onboarding (unchecked default, Option A: Save records checkbox state — no unaffirmed consent; warm copy, no "marketing" in user-facing text). marketingConsent + marketingConsentAt columns (migration 20260626120000, applied local via Docker-psql workaround + prod via Render auto-deploy). PATCH /users/me/marketing-consent (exempt from verified-email gate — fires pre-verification). Profile toggle (in-app opt-out). Owner-gated /admin/marketing-subscribers list + CSV (both client OwnerRoute + server requireOwner). UNSUBSCRIBE email-link not built — required when campaign-sending starts (FR-WINBACK era). Pushed + live.
FR-WINBACK | Cancelled-customer export for win-back | P3 | Deferred | Gated on FR-MARKETING-OPTIN (no opt-in basis today).
FR-TIME-INPUT-PICKER | Scrolling time picker (AM/PM) replacing free-text time field | P3 | Shipped | Root-cause cure for the PDF time crash. Standardized input.
FR-RIG-SPEC-AUTOFILL | Pick RV make/model/year → autofill specs | P3 | Deferred | Hybrid recommended: curated common-rig set + per-class defaults + manual override. No clean free RV spec DB exists; build curated, grow over time.
FR-ROUTE-HWYPREF-1 | Rig-aware “prefer major highways / 4-lane” routing preference | P3 | Deferred | Post-launch, low severity.
FR-SCOPE-HUMOR-1 | Scope-guard tone improvement with on-brand deflection | P3 | Deferred | A/B test before shipping.
FR-FEEDBACK-NOTIFY | 5th dev@ alert on feedback submission | P3 | Deferred | Scoped, not built.
JOURNAL-LOCATION | Optional place picker on freeform journal entries (pin stopless entries) | P3 | Deferred | Reuse AddressAutocomplete in AddEntryModal; columns exist from step 7; needs scout.
MOBILE-CHAT-INPUT | Chat input off-screen when keyboard opens (mobile) | P3 | Deferred | Pre-existing (baseline bf89b0a). Fix = visualViewport listener to lift input. Measure-first. Not pushed.
RIG-CHANGE | Full rig-change feature: trip-page selector + larger-rig warning + per-stop “booked for [rig]” + AI modify action | — | Shipped | All routed through one guarded swap path. Migration: 7 bookedForRig* cols. Dev-tested. Pushed, not yet deployed to prod.
STOP-GEO-RESLOT | Geo-reslot modify-added stops + booked-stop date-shift modal + originalBookedDate record | — | Shipped | Server geocode + min-detour reslot; center-screen modal; backfill done. Pushed.
STAY-CARD-TRUE-WINDOW | Itinerary stay card shows true booked window (nights + arrival→checkout); PDF matches | — | Shipped | Display-only (Option 1). Pushed.
NIGHTS-CONVERSION | Align modify days→nights with planning + explicit date-range rule | — | Shipped | Pushed. Fresh-thread test pending.
KEEP-LONG-DRIVE | User opt-in to drive an over-cap leg: confirm modal on overnight delete, ack persists, no nag | — | Shipped | Reused ConfirmModal. 'Remove this overnight stop?' wording, danger button. Ack on Trip.acknowledgedLongLegs (migration applied). Local main, not pushed.

## Launch Status
RoamReady.ai — Launch Status
Snapshot of LAUNCH_STATUS.md (repo root = live source of truth). Updated RR52.
Item | Status | Category | Notes
Site live at roamready.ai | LIVE | Launch | Real Stripe payments, DNS cutover complete, Render deployed.
PDF time-crash fix | DEPLOYED | Prod fix | Live on roamready-client (Cindy’s PDF works).
RR51 batch (rig, stop-sequence, nights, stay-card) | PUSHED, NOT DEPLOYED | Deploy pending | On GitHub. Deploy needs BOTH roamready-api (server) and roamready-client (client). Deliberate step.
Plan-is-Truth Part 1 | PUSHED, NOT DEPLOYED | Deploy pending | Built + merged to local main and pushed to origin. Not deployed to prod. Drive-time net OFF until Part 2.
Plan-is-Truth Part 2 | DEPLOYED | Push pending | RR53: structural pre-build budget fix (app owns minimum, deterministic shape) shipped + pushed; prod migrations current (45 found, up to date).
Marketing opt-in (FR-MARKETING-OPTIN) | DEPLOYED | Feature | RR53. Consent capture + modal + admin subscriber list. Schema migration 20260626120000 applied to prod (Render auto-deploy on push). Live on roamready.ai.