## Bug Tracker
RoamReady.ai - Bug Tracker (Master Log)
Updated June 23, 2026 (RR50). Complete history of bugs worked, RR1-RR49. Open at top by severity; fixed bugs hidden by default - click the Status filter dropdown to view any past bug. Status color: Red=P1/High open, Yellow=P2/Med open, Blue=P3/Low open, Green=Fixed.
ID | Title / Symptom | Severity | Session | Status | Resolution / Notes
BUG-CHAT-MARKDOWN | Raw ** markdown leaking into chat bubbles (asterisks shown literally instead of bold) | Low | RR50 | Fixed | FIXED RR50 (live). Raw ** markdown was leaking into both chat bubbles (planning + modify). Fix: new shared client/src/utils/cleanChatText.ts that strips <itinerary>/<modify> tags, normalizes markdown emphasis (**bold**/*italic*/headings/bullets -> plain) with a Safari-safe lookahead-only regex (no lookbehind, 17 edge cases incl 5*5 arithmetic + snake_case preserved), and collapses 3+ newlines to normal paragraph breaks (fixed the big vertical gaps). Both bubbles now route through the one helper (killed the duplicate cleanTexts). Plus a prompt rule telling the AI to write plain prose, carved out so it still emits the <itinerary>/<origin>/etc tags. Verified live: no asterisks, no <modify> leak, trips still build, spacing clean. Commits (markdown strip + blank-line collapse).
BUG-COMP-BOOKING-GATE | Comped Pro user hit with "Upgrade to Pro" paywall when booking (Pro feature gate ignores comp grant) | High | RR50 | Fix live - verifying | ROOT CAUSE (scout): client authStore.hasAccess had drifted from the server - it read only subscriptionTier and ignored compTier/compExpiresAt, so comped users were paywalled in the browser even though the SERVER hasAccess granted them. Grant/revoke tools are CORRECT by design ("Comped but FREE" is intentional - comp is orthogonal to subscriptionTier; only hasAccess combines them). Russ record clean + active to Jun 2027. FIX (pushed/live, commit d6a4d61): added comp clause + grace clause to client hasAccess (mirrors server; one function backs ALL client gates - booking/journal/PDF/packing/OHV unblocked at once); routed the two free-AI-cap checks through shared hasAccess; fixed heavy-usage tier label. VERIFY PENDING: (1) comped case - confirm Russ can book on live; (2) free-paywall case deferred - new accounts get a 7-day TRIAL (trial=access), so a true free/blocked user cannot be click-tested until the trial-account lapses (~7 days); additive logic, free tier gate untouched, CC regression-checked all 4 cases.
BUG-ROUNDTRIP-NIGHTS | Round trip drops return leg + nights shortfall (asked 6 nights/round trip, built 4 nights one-way) | High | RR50 | Fixed | REGRESSION - round trips worked before. Repro: new account momann+newuseralert2, prompt "round rock texas july 5th for 6 days and come home". Two stacked failures: (1) RETURN LEG NOT BUILT - "come home" confirmed in conversation but itinerary has only outbound stops (Mesa 0n, El Paso 1n, Midland 1n, Round Rock 2n = 4n total, card shows "4n"); no return overnights. (2) NIGHTS SHORTFALL NOT CAUGHT - 6 requested, 4 built; RR48 reconciler/server-guard/AI-conflict-hard-stop did NOT fire. PROSE was correct (said 6 nights, back July 11) but the CARD undercounts - narration-right/card-wrong, the dangerous direction since the card is what builds. On pushback the model offered to pad Round Rock or add a destination (wrong fix; real fix is the missing return leg). Scout in a NEW planning session. Not the dropdown work. Suspect a change since RR48 broke a working round-trip path. ¦ FIXED RR50: natural-language round-trip inference (model decides, deterministic strip as backstop), single-shot nights capture restored, deterministic where/when/length build-gate, origin lock for home-on-file + inverted guard relocated, direction question removed (default one-way). Tested live: direction gone, one-way builds clean, build-gate asks missing essentials together. Pushed in a stack. NOTE: home-on-file "say home -> lock" path not runtime-verified (test accounts were no-home / full-timer); fix is no-op-safe either way.
BUG-AI-NODATE-ASK-B | Backend silently defaults null startDate to today in recomputeStopDates | Medium | RR48 | Open | Part A shipped RR48 (opening flow asks+confirms). Part B (backend stop defaulting) not built.
FR-NIGHTS-BANNER-RESIDUAL | Shortfall banner should fire only on post-reconcile residual | Low | RR48 | Open | Banner can cry wolf; gate on residual after reconciler runs.
TZ-OFFBYONE | Off-by-one date display in behind-UTC timezones | Low | RR19 | Open | Underlying UTC-midnight storage round-trip still open; forecasts render correctly but display can be off by one.
MOBILE-CHAT-INPUT | Mobile chat input off-screen when keyboard opens | Low | RR33 | Open | Pre-existing (git-confirmed baseline). Fix = visualViewport listener to lift input above keyboard. Measure-first.
NIGHTS-PROSE-1 | Model narration can misstate nights vs the correct card | Low | RR48 | Open | Feed derived totals into the model summary so prose matches the card.
IOS-ZOOM-STUCK | Intermittent iOS Safari zoom-stuck bug | Low | RR3 | Open | Multiple mitigations shipped (16px inputs etc.); not reproduced/confirmed. Needs Mac+iOS Inspector real-device test.
BUG-STOP-APPEND | Server ignored order field, always appended stops to end | High | RR1-2 | Fixed | Integer shift-up insertion + HOME stop guard. Order field now honored.
BUG-ORDER-TRUNCATE | Fractional midpoint order values truncated to int, causing position ties | High | RR1-2 | Fixed | Switched to integer shift-up insertion; no fractional orders.
BUG-AI-PHANTOM-STOPS | AI hallucinated phantom stops from poisoned conversation history | High | RR1-2 | Fixed | Tag-stripping from stored history + 10-message history cap + ground-truth state injection.
BUG-AI-NO-MODIFY-TAG | AI produced confirmation text without emitting required <modify> tag | High | RR1-2 | Fixed | Auto-retry on tag-less confirmations + system-prompt ordering (CRITICAL first).
BUG-STALE-REACT-STATE | Client used stale React state for position math | Medium | RR1-2 | Fixed | Fresh trip-data fetch in applyModification.
BUG-PROMPT-CONFLICT | Conflicting system prompts from client and server | Medium | RR1-2 | Fixed | Server prompt authoritative; client prompt removed.
BUG-FIELD-MISMATCH | Schema mismatch: AI-emitted field names vs client-expected names | Medium | RR1-2 | Fixed | Field-name alignment between AI output and client.
BUG-POI-PERSIST | POIs (e.g. Prada Marfa) not persisting to itinerary generation | Medium | RR2 | Fixed | POI rule was in planning prompt but not itinerary-gen prompt; added.
BUG-RESERVE-HOME | Reserve page showed suggestions for the home/start stop | Low | RR2 | Fixed | Guard so HOME/start stop shows no reserve suggestions.
BUG-MOBILE-HEADER-OVERLAP | LandingPage header overlap on mobile | Low | RR3 | Fixed | Mobile header layout fix.
BUG-100VH-MOBILE | 100vh viewport bug on mobile | Low | RR3 | Fixed | Switched 100vh -> 100dvh.
BUG-IOS-AUTOZOOM | iOS Safari auto-zoom on input focus | Low | RR3 | Fixed | Global font-size:16px rule on inputs.
LB-1 | PDF lazy-loading: react-pdf not code-split out of main bundle | Medium | RR19 | Fixed | react-pdf lands in own chunk, not index. Verified via build inspection.
LB-2 | updateTrip footgun: schema permitted raw startDate/endDate/totalNights write | High | RR19 | Fixed | Fields removed from TripUpdateSchema; .strict() rejects.
LB-3 | Modify-AI long-conversation tag-loss: model stops emitting <modify> tags | High | RR19 | Fixed | annotate-not-strip + auto-retry + amber notice. Commit b3994ff. Was top launch risk.
LB-4 | Weather tab: forecast_days param + .split() date TypeError | Medium | RR19 | Fixed | Param removed; live branch uses Date directly; three sub-fixes in weatherFetch/trips.
LB-5 | Weather per-stop live->historical fallback for late stops | Medium | RR19 | Fixed | LIVE_WINDOW_END_DAYS=15 + per-stop fitness/modeMatch.
LB-6 | aiConversation silent 400: dead client write + stale exclusion query | High | RR19 | Fixed | Dead write removed; surprise-trip exclusion rewired to PlanningSession.messages.
LB-11 | UTC-midnight arrival timezone artifact in server weather path | Medium | RR19 | Fixed | parseTripDate helper added server-side (utils/dates.ts). Verified in 3 timezones.
BUG-DATEPICKER | Broken native date input on New Trip page | Medium | RR19 | Fixed | Replaced with react-day-picker popover.
BUG-MAP-PANBY | Map click-to-popup centering off (panBy sign inversion) | Low | RR19 | Fixed | Corrected panBy sign; centering verified.
BUG-FMTDATE-AI | fmtDate TZ cousin bug in ai.ts modify prompt date line | Medium | RR20 | Fixed | Routed UTC-midnight Prisma dates through parseTripDate. Commit a33d246.
BUG-HOME-COORDS | Trip start pin placed at home (Mesa) when origin city differs | High | RR20 | Fixed | 4 sites applied home coords on type==HOME alone; added homeCity match check.
BUG-FITBOUNDS-TDZ | Trip map fitBounds effect crashed (temporal dead zone) | Medium | RR20 | Fixed | Moved useEffect below the const it referenced. Commit 765e18a.
BUG-BUILD-BACKFILL | Pre-existing build error in backfillStayActivities.ts (Prisma Json typing) | Low | RR20 | Fixed | merged as unknown as Prisma.InputJsonValue. Commit ef45aeb.
BUG-ALWAYS-SEDONA | Surprise-trip always returned Sedona | Medium | RR20 | Fixed | Variety + one-question flow; fixed at root.
TM-1 | Map route polyline did not recompute when AI added a stop | High | RR27 | Fixed | Stale-consumer family; recompute trigger wired into modify save path.
TM-2 | Map popup showed estimated rate, not actual rate after booking | Medium | RR27 | Fixed | StopPopup now uses actualRate ?? siteRate fallback.
BUG-ORIGIN-EXTRACT | Origin extractor missed reversed word order / lowercase cities | Medium | RR33 | Fixed | Broadened to catch "to Y from X" and lowercase city names.
BUG-FULLTIMER-LEAK | Full-timer home-address save template leaked to full-time RVers | Medium | RR33 | Fixed | Gated on prompt body itself, not just injected directive.
BUG-VEHICLE-LAYER | Mobile vehicle-picker layering bug | Low | RR33 | Fixed | Added setSheetOpen(false) on build (sequencing, not z-index).
BUG-DEFAULT-CENTER | AllTripsMap DEFAULT_CENTER jump on load | Low | RR33 | Fixed | Extracted shared AllTripsMap component with the center-jump fix.
BUG-PACKING-MOBILE | Packing List page broken on mobile (buttons, PDF dropdown) | Medium | RR46 | Fixed | flex-wrap + stacking header; Export PDF dropdown left-0 with max-w guard.
BUG-TRIP-MAPPINS | Stop markers clustered in Colorado (Canadian stops fell back to default coords) | High | RR47 | Fixed | Geocode hardcoded USA; added CA_PROVINCES set + componentRestrictions. Repaired corrupted Vancouver row. Mileage 6554->4373 mi.
FR-MAP-DESKTOP-LAYOUT-BUG | Desktop map: outer page scrollbar, map too small | Low | RR47 | Fixed | Structural flex-fill layout; map fills width, stops scroll in own window.
WATCH-CLIENT-BIN | vite/tsx "not recognized": node_modules/.bin symlinks wiped | Medium | RR47 | Fixed | CC was junctioning node_modules into worktrees then deleting them. Fixed: main checkout, CLAUDE.md rule, npm install recovery.
BUG-TRIP-SEGROUTE-COUNTRY | trips.ts distance calc has same hardcoded-country blind spot as map pins | Low | RR47 | Fixed | Carried then resolved alongside geocode work.
BUG-CHAT-INPUT-CLIP | Desktop pulse glow on chat input box clipped at container edge | Low | RR46 | Fixed | Cosmetic; glow clip resolved.
BUG-TRIP-STOPORDER | Whistler sequenced before Vancouver turnaround (geographic zigzag) | Medium | RR48 | Fixed | Turnaround sequencing rule in services/ai.ts. Verified KC->Vancouver->Whistler. Commit 610c945.
BUG-TRIP-NIGHTS | 30-day request produced 20-night trip (duration shortfall) | High | RR48 | Fixed | Full arc: prompt rule + server MESA guard + client banner + duration capture/confirm + deterministic reconciler + AI conflict hard-stop.
FR-AI-DURATION-CONFLICT | AI silently auto-corrected target-vs-stops night mismatch | Medium | RR48 | Fixed | Hard-stop: AI resolves conflict conversationally, user chooses.
BUG-CHAT-ANCHOR-BOTTOM | Chat not anchored to bottom on load | Low | RR48 | Fixed | Structural mobile flex column justify-end (RR33 lineage).
DUP-CINDY | Duplicate Cindy account from email case-sensitivity | High | RR49 | Fixed | Deleted empty lowercase dup by CUID after zero-child verify. Keeper untouched.
BUG-EMAIL-CASE | Email treated case-sensitively, allowed duplicate accounts | High | RR49 | Fixed | Shared normalizeEmail() on 6 paths + one-shot backfill of 2 mixed-case rows. Mis-cased login works.
ONRENDER-REDIRECT | onrender client URL did not redirect to roamready.ai | Medium | RR49 | Fixed | Exact-match host guard in index.html head. Verified bounce + deep-link. b71d1df.
BILLING-COMP-DISPLAY | Comped user saw Free/Trial/Upgrade despite having Pro | Low | RR49 | Fixed | Added compTier/compExpiresAt to client type + 3-branch display. Verified.

## Features & Roadmap
RoamReady.ai - Features & Roadmap
Updated June 23, 2026 (RR50). Open/planned at top by priority; shipped hidden by default - use the Status filter to reveal. Status color-coded: Red=P1/Gate, Yellow=P2/in-progress, Blue=P3/deferred/polish, Green=Shipped.
ID | Feature / Item | Status | Severity / Category | Notes | Key commits
FR-RIG-DROPDOWNS | Shared RangeSelect dropdowns for all rig numeric fields (year/length/height/mpg/tank) | Deployed | RR50 / UX | SHIPPED & verified RR50. Replaced bare number inputs (year started at 0, click-up misery) with shared RangeSelect across OnboardingPage + RigPage + EditRigPage. New client/src/components/forms/RangeSelect.tsx + client/src/constants/rigOptions.ts (single source: YEARS newest-first, LENGTHS/HEIGHTS 0.5 steps, MPG 5-30, TANK 10-200 by 5). RHF Controller emits real numbers; year/towedYear Math.round to Int; out-of-range saved values spliced in so editing never blanks data. De-duped the YEARS array. Verified all 3 forms incl edit-prefill. Commits c5d0315 + 7228afe. | c5d0315,7228afe
FR-FEEDBACK-NOTIFY | dev@ alert on new user feedback submission | Open | P2 / Growth | The "better way" replacement for pulling admin/feedback by hand. Wire a 5th owner alert (sendFeedbackAlert) into the SAME feedbackNotification.ts mailer, fired right after the feedback create (prisma.feedback.create). Body: submitter email+name, type/category, message text, timestamp; handle anonymous/no-account gracefully. NOT built in the RR50 notification ship - deferred when Benny paused to think; he then pushed signup/sub/cancel only. Pick up next: scout the feedback create path first (file+line+Feedback fields), then one call site. Once live, feedback arrives in dev@ and gets triaged onto the User Submissions tab - no Chrome agent needed. | -
FR-FOUNDER-CANCEL-TEST | Runtime-verify founder-rate preservation before cancelling a real founder | Open - gate | P1 / Gate | Cancel-billing script is built and code-correct, but founder-rate preservation (admin_cancel metadata tag -> webhook skips forfeit) has NOT been watched at runtime. GATE: non-founder cancels fine; do NOT cancel a real founder-priced account until a test-mode founder sub is stood up and the rate confirmed to survive a cancel. (build-green != runtime-correct). | -
FR-DEV-NOTIFY | dev@ notification on signup / new paid sub / cancellation | Deployed | RR50 / Growth | SHIPPED & verified live RR50. Three owner alerts to dev@roamready.ai: new signup (email + Google), new paid subscription (plan label + $ amount + founder flag), and cancellation on the cancel-REQUEST transition (annotated admin-initiated vs self-cancel). All fire-and-forget (.catch) so an alert outage cannot break signup/checkout/webhook. Reused feedbackNotification.ts mailer; OWNER_NOTIFY_EMAIL code-defaulted. 4 server files, commit fdba321, pushed + deployed. NOTE: feedback-submission alert was NOT part of this ship - see FR-FEEDBACK-NOTIFY. | fdba321
FR-WINBACK | Win-back cancelled paying customers (export + campaign) | Open | P2 / Growth | Re-engage churned paid subs with incentives. APPROACH: one-shot read-only export script (cancelled paid subs -> email, cancel date, last plan) -> CSV on demand. NO always-on pipeline / no PII at rest. GATE before any promotional send: CAN-SPAM (working unsubscribe, Martini AI Media physical address, honor opt-outs) AND confirm signup/checkout captured email/marketing consent. Transactional email always OK; promotional win-back is the regulated part. The cancellation dev@ email is the informal start of this list. | -
FR-FRESH-ACCT-CHECK | Non-founder fresh-account click-through before announcing | Open - recommended | P2 / Pre-launch | Payment path proven; confirm first-time-visitor paywall/pricing display before soft launch to RV communities. | -
FR-TIER2-ANONYMIZE | Tier 2: one-way anonymize (true data erasure, retain billing shell) | Deferred | Post-launch / Legal | Designed + scouted (field map, Stripe-cancel-first ordering, free-text PII hiding spots incl co-traveler PII and rig plates, AdminActionLog). Under CCPA thresholds so not legally required yet. GATE: attorney to set retention + bless scrub-vs-keep field list before it runs on a real person. Script-first, dry-run on throwaway. | -
COMP-FILTER-NICETY | Add a Comped option to the Active/Suspended/All filter | Deferred | Polish / Low | Comped users visible in Active/All with the badge, just not filterable-to-only. Needs a new server-side account-status param. | -
FR-ROUTE-HWYPREF-1 | Rig-aware prefer major highways / 4-lane routing preference | Deferred | Post-launch / Low | Carryover. | -
FR-SCOPE-HUMOR-1 | Scope guard tone improvement with on-brand dry deflection | Deferred | Post-launch / Polish | Carryover. Touches sensitive prompt code; recommended for post-launch A/B test. | -
FR-ADMIN-DELETE-USER | Cascade-aware delete-user in admin panel | Deferred | Post-launch / Low | Superseded in practice by suspend (reversible) + Tier 2 anonymize (parked). True hard-delete remains for empties/tests only. | -
FR-ACCT-SUSPEND | Reversible account suspend/reactivate + auth-state enforcement + audit log | Deployed | RR49 / Admin | Verified in browser. Shared accountLifecycle service (one impl for script + buttons). Auth gates: requireAuth + refresh + Google OAuth all reject deactivated. Self- and owner-suspend guards. History timeline. Migration add_account_deactivation. | 212909e, f90859e
FR-ADMIN-MOD-UI | In-app admin moderation UI (Subscribers page) | Deployed | RR49 / Admin | Per-row Suspend/Reactivate buttons, Active/Suspended/All filter, Suspended badge + reason inline, required-reason confirm dialog, generic History modal (renders all action types incl. future ones). | f90859e
FR-CANCEL-BILLING | Optional Stripe cancel/refund on deactivate (script) with founder-rate preservation | Deployed | RR49 / Admin | SUSPEND default / CANCEL opt-in / --immediate / --refund. Stripe-first then DB; webhook owns downgrade; founder rate preserved via admin_cancel metadata tag. NOTE: see FR-FOUNDER-CANCEL-TEST gate before cancelling a real founder. | 4edd346
FR-GRANT-PRO | Grant/revoke complimentary Pro (admin) independent of Stripe | Deployed | RR49 / Admin | Verified (PDF export works for comped user; revoke clears). Schema add_complimentary_access. hasAccess additive comp clause, never touches Stripe fields. 1mo/1yr/lifetime/custom-date. Comped badge + history + honest Billing display. | 65c05da + billing fix
FR-EMAIL-NORMALIZE | Email case-normalization (root-cause fix + backfill) | Deployed | RR49 | Shared normalizeEmail() on every write + compare path; one-shot backfill of mixed-case rows. Mis-cased login now works on password and Google. | (normalizeEmail + backfill)
FR-ONRENDER-REDIRECT | onrender host redirect to roamready.ai | Deployed | RR49 | index.html host guard bounces the bare onrender URL to roamready.ai (path+query+hash preserved), exact-match so apex never loops; /api rewrite untouched. | b71d1df

## Launch Status
RoamReady.ai - Launch Status
Source of truth: LAUNCH_STATUS.md ¦ PRODUCTION LIVE at https://roamready.ai (RR50). Open at top by severity; done hidden by default - use the Status filter to reveal. Red=P1/Gate, Blue=deferred, Green=Done.
ID | Item | Status | Severity / Category | Notes
FOUNDER-CANCEL-TEST | Runtime-verify founder-rate preservation before cancelling a real founder | OPEN - gate | P1 / Gate | Non-founder cancels are fine to use; do NOT cancel a real founder-priced account until a test-mode founder sub is stood up and the rate confirmed to survive a cancel.
FR-TIER2-ANONYMIZE | Tier 2: one-way anonymize (true data erasure, retain billing shell) | DEFERRED | Post-launch / Legal | Attorney to set retention + bless scrub-vs-keep field list before it runs on a real person. Script-first, dry-run on throwaway. Under CCPA thresholds, not legally required yet.
BUG-AI-NODATE-ASK-B | Backend stops silently defaulting null startDate to today in recomputeStopDates | DEFERRED | Post-launch | Carryover. Part A shipped RR48 (opening flow asks+confirms start date).
FR-NIGHTS-BANNER-RESIDUAL | Fire shortfall banner only on post-reconcile residual | DEFERRED | Post-launch | Carryover.
TZ-OFFBYONE | Off-by-one date display in behind-UTC timezones | DEFERRED | Post-launch | Carryover.
MOBILE-CHAT-INPUT | Mobile chat input off-screen on keyboard | DEFERRED | Post-launch | Carryover. Fix = visualViewport listener to lift input above keyboard. Measure-first. Pre-existing.
NIGHTS-PROSE-1 | Model narration can misstate nights vs the correct card | DEFERRED | Post-launch / Polish | Carryover. Feed derived totals into the model summary.
CLEANUP-TESTSUB | Live test subscription from real-card test | CLOSED - kept | Cleanup | RR50: Reviewed live. The single Active sub is Cindy / RoamReady Pro $7.99/mo - the launch-test sub on a real account. Benny chose to KEEP it. If rebill ever unwanted: cancel + re-grant comp Pro. No action pending.
CLEANUP-JUNK | Archive junk myproduct products in live catalog | CLOSED - done | Cleanup | RR50: Already resolved. Catalog tabs show All 9 / Active 1 / Archived 8. Only RoamReady Pro (4 prices) Active; junk myproduct entries already in Archived.
LAUNCH-DNS | DNS cutover to roamready.ai | DONE | Launch | RR48. Apex A -> 216.24.57.1; www CNAME -> roamready-client.onrender.com. Email records preserved. SSL issued.
LAUNCH-STRIPE | Stripe test -> live flip | DONE | Launch | RR48. Real-card test: charge -> Pro -> refund. All 4 live pieces verified.
DUP-CINDY | Delete empty Cindy duplicate account | DONE | RR49 | Verified. Deleted by CUID after zero-child verify.
BUG-EMAIL-CASE | Email case-sensitivity normalize + backfill | DONE | RR49 | Verified. normalizeEmail on 6 paths + 2-row backfill.
ONRENDER-REDIRECT | onrender host -> roamready.ai redirect | DONE | RR49 | Verified bounce + deep link. b71d1df.
FR-ACCT-SUSPEND | Reversible account suspend/reactivate + audit log | DONE | RR49 / Admin | Verified in browser. See Features & Roadmap for detail.
FR-CANCEL-BILLING | Optional Stripe cancel/refund on deactivate (script) | DONE | RR49 / Admin | Built + pushed. See FOUNDER-CANCEL-TEST gate before cancelling a real founder.
FR-GRANT-PRO | Grant/revoke complimentary Pro (admin) | DONE | RR49 / Admin | Verified. Schema add_complimentary_access. Comped badge + history + honest Billing display.

## User Submissions
RoamReady.ai - User Submissions (from admin/feedback)
Source: https://roamready.ai/admin/feedback (admin-only; pulled via Claude in Chrome each session, not automatic). Open at top by priority; resolved hidden by default - use the Status filter to view. Red=P1/High, Yellow=P2/Med, Blue=P3/Low+deferred, Green=Resolved. Genuine bugs also mirrored into the Bug Tracker tab. Contains user PII - keep internal.
ID | Date | User | Submission | Type | Priority | Status
No submissions logged yet. Pull the admin/feedback page via Claude in Chrome and paste the entries; they will be triaged and filed here by priority.