## Tracker
ID | Item | Type | Priority | Status | Date | Area / Files | Notes
MESA-6b | Swept hardcoded example cities from modify-mode prompt | Fix | - | SHIPPED | 2026-06-05 | server/src/controllers/ai.ts | Closed origin-fabrication leak in modify mode (MESA-6 only covered services/ai.ts).
MODIFY-UX-1 | Three-state outcome: clarify / proposal / failed | Fix | - | SHIPPED | 2026-06-05 | ai.ts + ModifyTripPanel.tsx | Error banner now fires only on real failure, not on clarifying questions.
GEO-1 | Added stop must fall between bracketing stops | Fix | - | SHIPPED | 2026-06-05 | server/src/controllers/ai.ts | Route-aware pick; no more overshoot (Little Rock/Tulsa) inserts.
ANCHOR-1 | Resolve modify stop refs by NAME not stop number | Fix | - | SHIPPED | 2026-06-05 | ai.ts + ModifyTripPanel.tsx | Killed off-by-one inserts. Dropped dual-number data line; after_stop primary anchor.
CAP-1 / 1b | Honest, context-aware hard-cap messages | Fix | - | SHIPPED | 2026-06-05 | server/src/controllers/ai.ts | Planning vs modify copy; removed false carryover promise; planning string honest pre/post-promote.
MIC-SEND-1 | Send / Enter work while mic is listening | Fix | - | SHIPPED | 2026-06-05 | client/src/components/ChatInput.tsx | Single shared fix; mic stops on submit so it doesn't bleed into next turn.
RESET-1 | Reopen 'Modify with AI' starts a fresh session | Fix | - | SHIPPED | 2026-06-05 | client/src/components/trip/ModifyTripPanel.tsx | Fixed permanent lockout. Post only current-session msgs (Option X); display still shows scrollback.
CAP-2 | Raise conversation caps to 600 / 1000 | Tuning | - | SHIPPED | 2026-06-05 | server/src/controllers/ai.ts | Per-call cost flat via 10-msg window. SOFT 35->600, HARD 60->1000.
BUG-1 | Mobile home input box truncates placeholder text | Bug | P1 | OPEN | 2026-06-05 | client (home planning input) | First thing a new user sees. Possibly same root as iOS Safari min-h layout item. Needs scout.
BUG-3 | Asked for 5-stop trip, got 6 | Bug | P1 | OPEN | 2026-06-05 | planning prompt (ai.ts) | AI said '5-stop' in prose then built 6. Is 'stop' defined? Is count enforced? Needs scout.
BUG-2 | Trip-summary pill needs clear 'tap to preview' CTA | UX/Copy | P2 | OPEN | 2026-06-05 | trip summary pill component | Pill doesn't signal it's tappable. Decide tap-target scope + CTA wording. Copy-level.
BUG-4 | Planning AI never asks round-trip vs one-way | UX/Design | P2 | OPEN | 2026-06-05 | planning prompt (ai.ts) | Big impact on days/miles/fuel/bookings. Decision: always-ask vs infer-and-confirm (lean: infer-and-confirm).
RES-HONESTY | Reservation honesty pass (re-confirm status) | Verify | P1 | OPEN | 2026-06-05 | TBD | Flagged CRITICAL pre-launch in prior sessions. Confirm done vs open when reading LAUNCH_STATUS.md.
LAUNCH-DOC | Read real LAUNCH_STATUS.md & merge open items | Task | P1 | OPEN | 2026-06-05 | LAUNCH_STATUS.md (commit d0fd774) | Source of truth. First action tomorrow. Confirms Monday timeline feasibility.
FUNNEL-1 | Tiered free-300 + upgrade-CTA conversion funnel | Feature | P3 | DEFERRED | 2026-06-05 | ai.ts + billing/trial + client | Revenue feature. Needs tier-aware cap + usage metering + subscribe wiring. Design deliberately, not rushed.
CAP-OPT-B | Disable input + 'Start fresh' button at cap | UX | P3 | DEFERRED | 2026-06-05 | ChatInput.tsx + ModifyTripPanel.tsx | Cleaner than typeable-dead-box. Client reads hardCapReached flag (not read today).
HOME-MODAL | Save-home modal fires on 'somewhere else' origins too | Bug | P3 | DEFERRED | 2026-06-05 | save-home modal | Optional gating to fire only on 'home' origins.
CI-GREP | CI grep to block real city names in ai.ts examples | Infra | P3 | DEFERRED | 2026-06-05 | CI / ai.ts | Guardrail that would auto-catch MESA-6b-class leaks. Stable placeholder convention now exists.
TRACKER-D | Tracker filename dated 06-04 holds 06-05 rows | Cleanup | P3 | DEFERRED | 2026-06-05 | tracker file in repo | Rename / reconcile. Also reconcile THIS spreadsheet against the repo tracker.
REGEN-MERGE | Non-destructive Regenerate merge (preserveUserEdits) | Feature | P3 | DEFERRED | 2026-06-05 | server/trips.ts ~1182-1258 | Preserve checked/isCustom flags on regenerate. Post-launch TODO from Regenerate ConfirmModal work.
JOURNAL-PHOTO | Journal photos: build upload vs link external | Decision | P3 | DEFERRED | 2026-06-05 | journal feature | Strategic decision deferred.
GPS-COMPLETE | GPS-triggered trip completion | Feature | P3 | DEFERRED | 2026-06-05 | client | Web tab-only caveat; full background needs native app. v2.
MOBILE-APP | React Native + Expo mobile app | Feature | P3 | DEFERRED | 2026-06-05 | new app | Defer until ~1,000 web users post-launch.
LAUNCH | RoamReady public launch | Milestone | P1 | TARGET | 2026-06-08 | — | Monday target. Feasible if no sleeper blocker in LAUNCH_STATUS.md.

## Summary
RoamReady — Tracker Summary
As of 2026-06-05 • prod synced at commit 7d5578d • launch target Mon 2026-06-08
Status | Count
SHIPPED | 8
OPEN | 6
DEFERRED | 9
TARGET | 1
TOTAL | 24
Open P1 items (launch-critical) | 4