## Bug Tracker
RoamReady.ai - Bug Tracker
End of day: Monday, June 22, 2026 (RR48) - PRODUCTION LIVE
ID | Title / Symptom | Severity | Source | Status | Resolution | Key commits
AI-MODIFY-1 | Modify-with-AI showed '[checkmark] change already applied' x4 but only the first stop was applied to the itinerary (Cindy's Mesa-Niagara trip) | High | Prod user (Cindy) | Fixed - deployed | MESA-10 multi-action architecture: server is the single parse authority (actions[] in envelope), per-action applied state stamped server-side at execution, Apply-all sequential UI, model-emitted 'applied' claims stripped, legacy histories degrade to neutral text. Synthetic success bubbles removed. | 1a3e8b4, 5a9c740
MODIFY-UI-1 | Duplicate-stop guard error reported the wrong stop number (counted HOME departure) | Low | User test (Benny) | Fixed - deployed | Guard now numbers against the displayed (non-HOME) stop list; add-home duplicates say 'as your home stop'. | bc71580
FB-HONESTY-1 | Feedback modal showed 'Thanks for your feedback!' even when the request failed (seen live on prod with a 401) | High | Internal test | Fixed - deployed | try/catch with status-specific messages, visible error box, disabled 'Sending...' state; raw req.body replaced with strict Zod validation (FeedbackSubmitSchema) via validateBody; unvalidated PUT /feedback/:id/status removed in favor of PATCH /admin/feedback/:id. | c8df51f
FB-ZOD-1 | Strict feedback schema rejected valid minimal submissions - title/importance became required (Zod v4 preprocess/optional placement gotcha) | Medium | Internal test | Fixed - deployed | Outer .optional() added to preprocessed fields; 8-case safeParse verification; gotcha saved to project memory. | a6addbd
MIGRATE-EOL-1 | Prisma 'migration modified after applied' checksum failures, three incidents in one day (founder-rate migration); migrate dev offered destructive DB resets | High | Dev infrastructure | Fixed - deployed | Root cause: core.autocrlf=true rewriting applied migration SQL CRLF on checkout; pre-pin worktrees stayed poisoned. Fix: .gitattributes eol=lf pin, repo-local core.autocrlf=false, byte repairs across all trees, DB checksum corrections (zero data loss, no resets). Guards: scripts/check-migration-eol.js, npm run preflight, hard-abort check wired into save-progress.bat. | 4305e98, 2be0de4
AI-PACK-1 | Packing list AI generation silently persisted an EMPTY list (200 + ~0.9 kB) - max_tokens 4096 truncation broke JSON parse, code swallowed it as []. Live on prod; regenerate could silently wipe an existing list. | High | User test (Benny) | Fixed - deployed | max_tokens raised to 8192 with stop_reason detection and loud parse logging; controller 502s on empty/non-array generation and never overwrites the stored list; carry-over extracted to utils/packingMerge.ts with a 10-case regression check (npm run check:packing-merge). | 3851ca3
PACK-PERSIST-1 | Packing list checkmarks did not persist - checked state lived only in React state; regenerate also wiped all checks | High | User report (Benny) | Fixed - deployed | New PUT /trips/:id/packing-list (ownership-checked, strict Zod, 30x100 caps); optimistic toggle + 500ms debounced save with flush-on-unmount and visible failure banner + retry; regenerate carries checked state over by case-insensitive name match; per-item remove (x) for curation. | fd58085
PDF-GATE-1 | pdfExport: ['PRO'] feature-table rule was never enforced - free users could download trip PDFs (client-side render skipped the gate) | Medium (revenue) | CC audit | Fixed - deployed | All three PDF surfaces (trip summary, trip map, packing list) now call the gated exportPdf endpoint first; 403 opens the paywall via the central interceptor; one deletable line per surface if ever ungated. | 4ad4329
UI-GLYPH-1 | TripMapPage stop-row glyphs unintelligible: purple weather badge was a bare count; tent/bed/red-triangle/booking-dot had no labels | Low | User report (Benny) | Fixed - deployed | Badge replaced with a labeled pill (CloudRain + 'N weather alert(s)', brand purple, compact form on narrow widths) with detail tooltip; all four glyphs now have explanatory title tooltips. | 46ea101
UI-PALETTE-1 | Three off-palette purples (TripMapPage text-purple-600, TripPDF #7C3AED, SessionTipCard #8458B4) | Low | CC sweep | Fixed - deployed | All consolidated to the registered brand token purple.DEFAULT #7F77DD; every client purple now derives from one token. | a3444de
PACK-UI-1 | Redundant 'Generate with AI' + 'Generate packing list' buttons; regenerate had no confirm despite replacing the list | Low | User report (Benny) | Fixed - deployed | One action per state: empty state owns the CTA, header shows 'Regenerate with AI' only when a list exists, gated by a ConfirmModal that honestly warns removed items will return. | 3851ca3
UI-DOT-1 | Purple dots on the dashboard journal map questioned as possible bug | Low | User report (Benny) | Closed - by design | Per-trip marker colors on AllTripsMap (active trip = RV Blue, others cycle a deliberate 4-color ramp; gold ring = journal entry). Registered brand accent; no change made. | n/a
RT-STRIP-1 | Round-trip return leg silently amputated; AI narrated a full round trip but only the one-way half persisted (card/badge disagreed with chat). Found via Mesa->NY 'and back' test. | High | Prod behavior (Benny/Cindy) | Fixed - deployed | Root cause was our own stripUnrequestedReturnLeg guard, not the model: it cut the return leg unless one of 7 blessed phrases was present ('and back' was not). Widened phrase detection (client guard + model prompt, kept in sync); strips now show a loud client notice instead of silent surgery; nights/summary derived from persisted stops. Plus AI-PACK-1 treatment on planning call (max_tokens 8192, stop_reason logging, parseItinerary refuses unterminated blocks). | 79c97f6
ORIGIN-FREETEXT-1 | Origin stated in the first message ('from mesa') was ignored; assistant still asked 'Where are you starting this trip from?' | Medium | User test (Benny) | Fixed - deployed | Origin directive amended: if the user message already names a starting point, emit <origin> and proceed; only ask when none stated anywhere. MESA-7 user-typed validation unchanged. | 16ed35a
SCOPE-META-1 | Scope guard refused an app meta-question ('why isnt it showing on the list on the right?') with the off-topic refusal. | Medium | User test (Benny) | Fixed - deployed | IN-SCOPE carve-out extended: questions about RoamReady, the current conversation, the itinerary being built, or what is on screen are always in scope (with honest cannot-see-the-UI framing). Off-topic refusal kept for genuinely unrelated topics. | d18e932
SESS-COMPOSER-1 | Chat message composer clipped at the viewport bottom on /sessions/:id (worse with the email-verification banner present and on mobile Safari). | Low | User test (Benny) | Fixed - deployed | Replaced hardcoded viewport-height arithmetic with a flex column (scroller flex-1 min-h-0, natural input row); re-measures on resize/layout shift. Bug-class history preserved in the line-907 comment (SESS-LAYOUT-2). | bd8cc05
SESS-HOOKS-1 | SessionPage crashed in a loop ('Rendered more hooks than during the previous render') on every /sessions/:id load - introduced by the SESS-COMPOSER-1 fix. | High | Local test (Benny) | Fixed - deployed | Rules-of-Hooks violation: the SESS-LAYOUT-2 hook cluster was placed below an early return. Relocated to the unconditional top hook section; added hydrating to the effect deps so measurement re-fires post-hydration. Lesson: tsc/build cannot catch this - runtime only; hooks on big page components go at the top. | 8944b56
BUILD-DUPE-1 | Clicking 'Build full itinerary' a second time (e.g. via browser back) returned raw 'Request failed with status code 400'; the trip already existed. | Low | User test (Benny) | Fixed - deployed | Build made idempotent: server returns 200 {alreadyBuilt, trip} for an already-promoted session; client short-circuits the stop-creation pipeline and navigates to the existing trip (avoids doubling stops). ConfirmVehiclesModal confirm path now also guarded against double-submit. Genuine failures still surface the red error. | a8b4897
NIGHTS-PROSE-1 | Model's free-text narration can still misstate the night count (e.g. says 'about 17 nights' while the card correctly shows 15). | Low | Observed in RT-STRIP-1 testing | Open - polish | Card/badge are now always truthful (derived from persisted stops); only the model prose can drift. Full fix deferred (claim-stripping on creation prose is invasive NLP). Likely cheap path: feed derived totals back into the model summary so it quotes the real number. | -
ENV-JUNCTION-1 | Overnight worktree-cleanup's 'zero data loss' claim was wrong: junction audit (dir /AL /S) followed through junctions and deleted symlink entries inside main's node_modules (.bin dirs, >=1 package). | Medium | Found next session (RR38) | Fixed - repaired | Repaired in-session via clean npm installs (root/client/server) + prisma generate; tsc/vite/tsx all verified working. Lesson: junction enumeration must not recurse through reparse points; unlink link-only, never recursive. | -
PACK-SPEED-1 | Packing list generation took ~60-65s (200-item list); too slow for launch. | Medium | User test (Benny) | Fixed - deployed | Prompt-driven size, not infra (warm, single Sonnet call, ended end_turn not truncation). 'comprehensive' drove ~200 items uncapped. Fix: prompt capped to ~120 items (8-14 cats, <=15/cat); max_tokens 8192->5120. Result ~36s, ~3100 out_tok, end_turn. Temp probe added+removed. | 26fc6c2, 39b932d
SELF-PERSON-1 | Account holder never counted as an adult; 'Made for X' read 0/1 adult for a Benny+Cindy trip. | High | User test (Benny) | Fixed - deployed | Case A: no self-person ever auto-created (lazy-only / backfill-flag-only). Fix: createParty seeds self on default party (idempotent); deletePerson rejects isSelf; party UI 'You' marker + delete suppressed on self row; backfillSelfPerson.ts repair run (1 self for Benny). No migration. Verified subtitle now '2 adults - 1 dog'. | 8e3dafd
STALE-SNAPSHOT-1 | 'Regenerate' button gave no why/when; packing list silently went stale when party/trip changed. | Medium | User report (Benny) | Fixed - deployed | New packingListMeta Json? column stores a generated-for snapshot; server computes stale + current vs snapshot; 'Made for X' subtitle + persistent-dismissable banner naming what changed; button -> 'Refresh suggestions'. Custom items + checks survive regenerate. Migration applied (additive nullable). | c315f06, 5349dd6, 6d0ef41, 2260e58
PRISMA-CHECKSUM-2 | migrate dev flagged founder-rate migration 'modified after applied' + offered reset; generated Prisma client also stale. | Medium | Dev infrastructure | Fixed - resolved | Founder-rate migration had a deliberate post-apply hand-edit (phantom DROP DEFAULT removed) -> file checksum != recorded. Fixed by recomputing SHA-256 + UPDATE the one _prisma_migrations row (zero data loss, answered N to all resets). A phantom auto-migration (DROP DEFAULT on JournalEntry.search generated col) failed P3018 -> rolled back + deleted. Stale client (EPERM during generate) fixed by closing backend + regenerating. Lesson: generate with backend fully closed; the phantom DROP DEFAULT recurs on every auto-migrate - always decline. | -
Summary
Total items | 24
Fixed - deployed | 20
Fixed - push pending | 0
Closed - by design | 1
Open - polish | 1
Fixed - repaired | 1
Fixed - resolved (dev infra) | 1
High severity | 8
NOTE: All RR39 items deployed to prod. NIGHTS-PROSE-1 (Low) still deferred. 'Fixed - resolved' = PRISMA-CHECKSUM-2 (dev infra). Next-session headlines on Backlog sheet: reusable/saved packing lists; resource-distance Phase 2 shipped this session.
BUG-EMAIL-CASE | Email treated case-sensitively - allows duplicate accounts (cindy@ vs Cindy@) | High | RR48 / launch | OPEN | Root cause of Cindy duplicate. Fix: normalize-on-write (signup/OAuth/all create paths) + lowercase-on-compare (all lookups) + backfill existing uppercase emails. Delete duplicate FIRST (backfill would collide on unique constraint). Scout before building.
DUP-CINDY | Duplicate Cindy account from mid-cutover signup | High | RR48 / launch | OPEN | Keep Cindy@roamready.ai (Jun 2, real data); delete empty cindy@roamready.ai (Jun 22). Read-only scout issued. Process: verify empty id via Render Shell read-only query -> confirm -> targeted delete by id. No admin delete-user action exists yet.

## Launch Status
RoamReady.ai - Launch Status
Source of truth: LAUNCH_STATUS.md ¦ STATUS: PRODUCTION LIVE at https://roamready.ai (RR48)
ID | Item | Status | Severity / Category | Notes
BUG-1 | Mobile placeholder truncation - chat input placeholder text is cut off at mobile widths | OPEN | P1 | Open launch-blocking bug.
BUG-2 | Trip-summary pill CTA - booking pill call-to-action wording/affordance needs work | OPEN | P2 | Open launch-blocking bug.
BUG-3 | Stop count accuracy - displayed stop count does not match the actual stops | OPEN | P1 | Open launch-blocking bug.
BUG-4 | Round-trip vs one-way prompt - AI prompt mishandles round-trip vs one-way intent | OPEN | P2 | Open launch-blocking bug.
10b | Travel Party Phase B / C | DEFERRED | Post-launch | Deferred - AccessibilityPage per-person, dormant field UI, per-trip override, legacy cleanup.
12 | iOS Safari zoom-stuck bug | PARTIAL | Post-launch | Multiple mitigations shipped; specific bug reproduction not confirmed. Needs a real-device test before launch.
14 | OHV/off-road destinations: own data source | DEFERRED | Post-launch | Rec.gov/RIDB does not index most USFS/BLM OHV areas. Real fix = ingest govt GIS feeds into own DB. Substantial standalone project.
15 | OHV Destinations - code-split the page with lazy() | DEFERRED | Low priority | First-app-load improvement only. Wrap route import in lazy()+Suspense.
16 | OHV Destinations - optional client-side result retention | DEFERRED | Nice-to-have | Cache last GPS + results so return visits render instantly.
17 | OHV link-checker - activation | DEFERRED | Post-launch | Checker logic built+merged. Needs: confirm table migrated, wire monthly trigger, smoke-test.
1 | PDF lazy-loading - @react-pdf/renderer code-split out of main bundle | DONE | Launch-blocking | Verified via build chunk inspection.
2 | updateTrip footgun - TripUpdateSchema raw date/total write | DONE | Launch-blocking | Fields removed from schema; .strict() rejects them.
3 | Modify-AI long-conversation tag-loss | DONE | Launch-blocking | annotateAppliedModify + auto-retry. Commit b3994ff.
4 | Weather Tab live forecast - forecast_days + .split() date bug | DONE | Launch-blocking | Param removed; live branch uses Date directly; canonical anchor probe.
5 | Weather per-stop live->historical fallback | DONE | Launch-blocking | LIVE_WINDOW_END_DAYS=15; per-stop fitness + modeMatch.
6 | aiConversation silent 400 + dead exclusion query | DONE | Launch-blocking | Dead client write removed; exclusion rewired to PlanningSession.messages.
11 | UTC-midnight arrival timezone artifact (server weather path) | DONE | Launch-blocking
11b | fmtDate cousin bug - modify-mode Dates: line shifted stop dates | DONE | Launch-blocking | Documented cousin of #11.
7 | Regenerate ConfirmModal gates - destructive flows confirmed | DONE | Launch-blocking
8 | Share Trip - end to end | DONE | Launch-blocking
9 | Reservation Honesty Pass - Book buttons open real reservationUrl | DONE | Launch-blocking
10 | Travel Party v1 - unified People + Pets at /profile/party | DONE | Launch-blocking
MESA-6b | Modify-mode prompt example-city sweep | DONE | Launch-blocking | Commit e52c7f7.
MODIFY-UX-1 | Three-state modify outcome (clarify vs proposal vs failure) | DONE | Launch-blocking | Commit c96f339.
GEO-1 | Add-stop geographic bracketing | DONE | Launch-blocking | Commit 6715744.
ANCHOR-1 | Modify stop refs resolved by NAME, not number | DONE | Launch-blocking | Commit b023efe.
CAP-1/1b | Honest context-aware hard-cap messages | DONE | Launch-blocking | Commits 308ad81, b6eb8ac.
MIC-SEND-1 | Send/Enter while mic listening - mic stops cleanly | DONE | Launch-blocking | Commit 6d70718.
RESET-1 | Reopening Modify-with-AI starts a fresh session | DONE | Launch-blocking | Commit d135be4.
CAP-2 | Conversation caps raised to SOFT 600 / HARD 1000 | DONE | Launch-blocking | Commit 31edef4.
RR38-1 | Feedback pipeline - user feedback capture + analysis | DONE | Launch-blocking
RR38-2 | FROM_EMAIL display name - friendly transactional sender | DONE | Launch-blocking
RR38-3 | PDF export gate - packing/trip PDF export is Pro-gated | DONE | Launch-blocking
13 | Map click-to-popup centering | DONE | Post-launch | panTo + panBy clearance math.
INFRA | Render cold-start mitigation | RESOLVED | Infrastructure | Upgraded roamready-api Starter->Standard always-on. Warm ~0.12-0.5s. Resolved June 14, 2026.
LAUNCH-DNS | DNS cutover to roamready.ai (GoDaddy -> Render) | DONE | Launch | Apex A @ -> 216.24.57.1; www CNAME -> roamready-client.onrender.com. Email records (Google MX, Resend SPF/DKIM, _dmarc) preserved. SSL issued. onrender URL kept live in parallel (intentional). CLIENT_URL set to https://roamready.ai.
LAUNCH-STRIPE | Stripe test -> live flip | DONE | Launch | LIVE. sk_live_ + 4 live price IDs (API+client, client rebuilt) + live webhook (whsec_) to /api/v1/subscriptions/webhook. Real-card test: charge -> redirect -> account PRO -> refunded. All 4 live pieces verified.
CLEANUP-TESTSUB | Cancel live subscription from real-card test | OPEN | Cleanup / Low | Payment refunded; subscription may still be active and could rebill. Cancel immediately in Stripe Live.
CLEANUP-JUNK | Archive 7 'myproduct' $15 junk entries in live catalog | OPEN | Cleanup / Low | Copied sandbox->live. Checkout unaffected (code uses only the 4 real price IDs). Tidiness only.

## Features Shipped
Features shipped - RR39 (Sunday, June 14, 2026)
Feature | What it does | Status | Key commits
Feedback pipeline (core) | Validated submissions (strict Zod), honest error states, screenshot attachments (up to 3, client downscale, magic-byte + size checks server-side, route-scoped 25mb JSON limit), support notification email, submitter acknowledgment email, private-by-default (isPublic false + migration), admin PATCH endpoint. | Deployed | c8df51f, 5cda816, d436834-era
Feedback lifecycle emails + refs | [FB-XXXX] reference code in subject/body of all three system emails; automatic 'shipped' email on status transition (plain-language copy, BUG vs FEATURE variants, once-ever via shippedNotifiedAt stamp); 'Notified' badge in admin; silent declines by design. | Deployed | 2e2b977, dd5af5a, 0280989
Admin feedback workspace | Five filter tabs (Active default / Shipped / Declined / Archived / All) with count badges; reversible archive (archivedAt) that never touches public roadmap; submitter line with Find in Gmail (ref search) as the sole reply path; mailto removed. | Deployed | d436834, 64771ed, 3500328
MESA-10 multi-action modify | Server-parsed actions[], per-action Apply cards with persisted applied state, Apply-all, deterministic strip of model 'applied' claims, state-aware model-bound history. Closes AI-MODIFY-1. | Deployed | 1a3e8b4, 5a9c740
Packing list system | Persistence (PUT + debounced saves), per-item remove, regenerate carry-over of checks, blank-checklist PDF export (PackingListPDF, TripPDF pattern), one-button-per-state UI with regenerate confirm, empty-generation 502 guard. | Deployed | fd58085, 3851ca3
PDF Pro gate | pdfExport enforced on all three PDF surfaces for the first time; paywall opens cleanly on 403. | Deployed | 4ad4329
Trip card lifecycle dates | 'Started <date> - Edited <relative>' bottom row on dashboard cards; 'Created <date>' on trip detail header. | Deployed | a6c6436
Plain-language customer copy | Shipped email rewritten without dev jargon (fixed/built/available, 'Happy travels' sign-off); public roadmap third column relabeled 'Completed'; Help page blurb aligned. | Deployed | 0280989, 98b791e
Round-trip honesty bundle | Return legs persist for natural phrasing (and back / there and back / return / back to <origin>); silent strips replaced with a loud notice; trip summary/nights derived from persisted stops; AI-PACK-1 guard rails on the planning call. | Deployed | 79c97f6
Origin from first message | Assistant captures the starting point when it is stated in the opening message instead of re-asking. | Deployed | 16ed35a
Scope carve-out for app questions | Questions about RoamReady, the conversation, or the on-screen itinerary are answered instead of refused. | Deployed | d18e932
Idempotent Build | Clicking Build twice / via back button lands on the existing trip rather than a 400; no duplicated stops. | Deployed | a8b4897
Cold-start mitigation (infra) | roamready-api upgraded Starter->Standard (always-on). Cold wake was ~50.88s on Starter; verified 0.29s after >20min idle on Standard. roamready-client (static) unaffected. | Deployed | (config + LAUNCH_STATUS.md)
Packing custom items + add/edit/remove | PackingItem.custom flag; add-your-own item per category, inline rename (promotes AI items to custom), remove; custom items survive Regenerate (mergePackedState). Mobile-visible edit controls. 'added' cue on custom items. | Deployed | 5349dd6, 6d0ef41
Packing current-state PDF + export dropdown | Export PDF dropdown: 'Current state' (packed items shown as solid Pine boxes, includes added items) and 'Blank checklist' (pen-and-paper). Distinct filenames. iCloud-style list polish (hairline rows, section headers, ghost add-line). | Deployed | 2260e58, c236edc
Packing staleness (snapshot + banner) | packingListMeta snapshot column; 'Made for X adults - N nights' subtitle; persistent-dismissable banner naming what changed (party/nights); 'Refresh suggestions' relabel + clearer Rebuild modal copy. Migration applied (additive nullable). | Deployed | c315f06, 2260e58
Self-person auto-creation | createParty auto-seeds a self-person on the default party; account holder now counted in all party-aware features; 'You' marker + delete-guard (server + UI); backfillSelfPerson.ts repair for existing accounts. Fixes the adult undercount at source. | Deployed | 8e3dafd
Packing build progress message (2-stage) | Replaces the bare spinner: stage 1 'Packing for a trip is no small job - building/rebuilding your list...'; after ~8s stage 2 'Hang tight, just a few more seconds...'. Rig-neutral. Timer cleared on completion + unmount. | Deployed | 24e8cf1
Packing size cap (speed) | Prompt capped to ~120 focused items (was ~200 'comprehensive'); max_tokens 5120. Generation ~60s -> ~36s. Also more usable (a 120-item list is workable; editable so anything missing can be added). | Deployed | 26fc6c2, 39b932d
Resource distance - Phase 1 (Near me) | Each resource shows 'X mi away' from live GPS, nearest-first (server already computed haversine + sorted; it was discarding the value). Server-attach distanceMiles; quiet badge mirroring OhvDestinationsPage. Missing-coord resources show no badge. | Deployed | cb77f46
Resource distance - Phase 2 (Near my stop) | Toggle on Resources page: 'Near me' (GPS, default) / 'Near my stop' (re-centers search on a chosen trip stop, distance from the stop). Trip->stop picker pre-filled with most-recent trip's first mapped stop; coordless stops filtered; no GPS prompt in stop mode. Client-only (server reference-agnostic). | Deployed | 88ea738

## Backlog & Open Items
Backlog and open items - updated RR39 (June 14, 2026)
Priority | Item | Notes
1 - Next session | Reusable / saved packing lists | Most RV packers reuse ~80% the same list every trip. Save-as-template OR copy-from-previous-trip OR AI-seed-from-base (3 shapes). Needs schema + migration; interacts with custom-flag + staleness. Deserves a mockup of 'start from template vs AI generate'. HEADLINE for next session.
4 - Polish | Roadmap-page feedback modal default type | Default Type to Feature Request when opened from the roadmap page; one-line tweak. (Carried from RR38.)
4 - Polish | Duplicate-card 'Try again' dead end | Deterministic rejections (duplicate stop) could offer Dismiss instead of a retry that can never succeed. (Carried.)
4 - Polish | Admin type filter | Re-add a bug-vs-feature type dropdown inside the status tabs if missed. (Carried.)
4 - Polish | Night-count prose mismatch (NIGHTS-PROSE-1) | Model narration can misstate nights vs the (correct) card. Feed derived totals into the model summary so it quotes the real number. (Carried, still open.)
4 - Polish | Travel Party 'Add yourself' empty-state copy | Now that a self-person ('You') auto-appears, the empty-state 'Add yourself and anyone traveling with you' wording is slightly redundant. Minor copy tweak. (New, found in SELF-PERSON-1 work.)
5 - Someday | Declined-email revisit | Declines are silent by design today; machinery exists if an automated gentle 'no' is ever wanted. (Carried.)
Dev infra note | Prisma generate / phantom DROP DEFAULT | Two recurring dev gotchas: (1) run 'prisma generate' with the backend FULLY closed or it EPERM-locks the engine DLL and leaves a stale client; (2) auto-migrate regenerates a phantom 'ALTER TABLE JournalEntry ... DROP DEFAULT' on the generated tsvector col every time - always decline / never name a new migration at that prompt. Never accept a DB reset.
1 - Next session | Delete Cindy duplicate + fix email case-sensitivity | Delete empty cindy@ (by id, via Render Shell, scout-verified) THEN fix case (normalize-on-write + lowercase-on-compare + backfill). Order matters: backfill collides if dupe still present.
2 - Post-launch | FR-ADMIN-DELETE-USER: cascade-aware delete-user in admin panel | Needed for GDPR/CCPA deletion requests, spam, dupes, test accounts. Build once properly vs repeated DB surgery. Admin Subscribers page currently lists only - no delete action.
3 - Cleanup | Stripe post-launch tidy: cancel test sub, archive 7 junk products | Quick. Stripe Live dashboard.
4 - Recommended | Non-founder fresh-account click-through before announcing | Payment path proven; confirm first-time-visitor paywall/pricing display looks right to a real new user before soft launch to RV communities.