## Bug Tracker
RoamReady.ai — Bug Tracker
Updated end of RR52. Claude owns this file. Open items on top; completed (green) hidden — reveal via the Status filter.
ID | Title / Symptom | Severity | Source | Status | Resolution / Notes
BUG-MODIFY-INTENT-CONFUSION | “Create a stop in [city]” on an open trip is sometimes mistaken for new-trip planning; AI asks planning questions instead of adding the stop | P2 | User test (Benny) | Done | FIXED (prompt-only): added a change-destination path (remove old + add new, carry over nights) + a guard so modify mode never re-asks origin/start-date/total-nights + scoped the clarifying-question line. Tester-confirmed + local-tested ('change destination to Denver' swaps cleanly, no re-interrogation). Local main.
TZ-OFFBYONE | Off-by-one dates on weather day, journal edit prefill, reservations bucketing, admin session inspector | P2 | User test (Benny) | Done | Routed four surfaces through parseTripDate; weather day numeric. Pushed.
BUG-ROUNDTRIP-MODIFY-DROP | Round trip on an already-built trip via modify did not insert the return leg | P1 | Prod behavior | Done | buildModifyInstructions gained a round-trip action. Pushed.
BUG-ROUNDTRIP-PLANNING | Mid-planning “make it a round trip” didn’t rebuild; malformed <modify> tags leaked | P2 | User test (Benny) | Done | Planning re-emits full itinerary inline; stray tags scrubbed; strip regex broadened. Pushed.
BUG-AI-NODATE-ASK-B | recomputeStopDates fabricated + persisted today’s date for dateless trips (silent fake DB write) | P1 | CC audit | Done | Leaves stop dates null when no real anchor. Anchor path byte-identical. Pushed.
BUG-PDF-TOSTRING | Cindy’s PDF crashed on free-text times without a colon (“3pm”) | P1 | Prod user (Cindy) | Done | Finite-check fallback to raw string. DEPLOYED TO PROD (roamready-client).
STORED-NIGHTS-OFFBYONE | Stored Stop.nights one short for stays entered as “N days” via modify (9-day stay stored as 8) | P1 | User test (Benny) | Done | Root: modify prompt said days-minus-1 while planning said days=nights. Aligned both + added date-range rule. Pinecrest row corrected manually + backfill. Pushed. (Fresh-thread test pending.)
ITIN-NIGHTS-MISMATCH | Itinerary stay card showed 3 disagreeing numbers (badge 8 / span 8 / cost 9) for one stop | P1 | User test (Benny) | Done | Display-only fix: badge, date range, day-span all show true booked window (true nights, arrival→checkout). PDF matches. Pushed.
BUG-MODIFY-ADDSTOP-SEQUENCE | Stop added via modify landed in the wrong geographic position (Fort Stockton before Toyahvale) | P2 | User test (Benny) | Done | Server geocodes the new stop + re-slots only it by min-added-detour; origin/finish/booked pinned. Pushed.
BUG-PLAN-BUILD-DIVERGE (Part 1) | Built trip differed from approved plan: phantom transit stop + scrambled nights | P1 | User test (Benny) | Done | Part 1 (build verbatim) + Part 2 (server-sole drive-time check) COMPLETE. See BUG-PLAN-IS-TRUTH-P2. Pushed status: local main.
BUG-LONGLEG-CANT-DELETE | User couldn't delete a transit/overnight stop on a still-over-cap leg — recheck immediately re-inserted it, overriding the user | P1 | User test (Benny) | Done | Design fix: replaced silent enforcement with a confirm modal ('Remove this overnight stop?') showing real merged-leg hours. Confirm = delete + acknowledge leg (suppress re-insert); cancel = restore. Ack persists; resets if leg endpoints change. Local main.
BUG-RECHECK-DELETE-INVISIBLE | Delete on map-page trash-can appeared to skip drive-time recheck (no log, no overnight on a 6.5h merged leg) | P2 | User test (Benny) | Done | Not a bug — recheckLongLegs ran but only logged on insert; 6.5h leg was within the 1h grace (cap 6h tolerates 7h). Fixed by adding full observability logging on every recheck path + per-leg hours. Local main.
BUG-LONGLEG-ACK-NO-SESSION | Keep-long-drive acknowledgment stored in planning session — a session-less Trip would silently drop it (latent, not user-reachable today) | P3 | CC audit | Done | Moved ack to Trip.acknowledgedLongLegs JSONB column (migration 20260625120000, applied). Latent future-proof; every current user trip has a session. Cleaner design, removes session dependency. Local main.
DEAD-CREATETRIP-ENDPOINT | createTrip (POST /trips) is a live auth-gated endpoint with NO in-app caller; tripsApi.create is dead client code | P3 | CC audit | Open | Decision for later: either wire a manual 'blank trip' create flow, or retire the endpoint + dead client method. Not urgent. Logged RR52.
BUG-MODIFY-GHOST-ROUTE | After an AI-modify destination change, the old map route line ('ghost path') stayed drawn until a manual page refresh | P2 | User test (Benny) | Done | Two causes: (1) route polyline dedup key wasn't invalidated on modify apply so it short-circuited the redraw; (2) geocoding effect had no .catch — a failed coord write left geocoding stuck true, permanently gating the route redraw until reload. Fix: invalidate dedup key on onTripUpdated + add .catch resetting geocoding flag. Client-only, local main.
MODIFY-CLARIFY-VERBOSE | When user references a stop not on the trip ('go to Boise instead of Salt Lake City' when SLC isn't a stop), AI gives a wordy 'I don't see X' clarifying reply | P3 | User test (Benny) | Open | Not a bug — AI correctly won't guess which stop to swap (guessing = silent wrong-swap risk). Low-pri tone item: could make the clarifying question tighter/less wordy. Do NOT make it guess. Logged RR52.
BUG-PLAN-ORIGIN-LOOP | Planning sometimes re-asks for the starting location. Fixed common cases (bare 'X to Y', arrow 'X→Y', abbrev 'KC') but still flaky on run-together phrasings where night-count abuts the date ('3 nights july7') | P2 | User test (Benny) | Open | PARTIAL FIX shipped RR52: extractFromXtoY now handles 'X to Y', 'from X to Y', 'X → Y', abbreviations (KC→Kansas City). REMAINING: phrasings like '...3 nights july7' / '3 nights july2' (no separator between nights and date) still sometimes trigger the origin question. Inconsistent → parser fragile on the string tail. Tomorrow: harden parse for nights/date run-together. Open.
BUG-PLAN-BUILD-DIVERGE (Part 2) | Server now sole transit-stop inserter; honest measured drive-time notes; deterministic over-cap splitting | P1 | Session arc | Done | Whole Plan-is-Truth Part 2 arc. Server measures real Google drive times, inserts overnight transit stops, builds honest grounded notes from measured legHours. AI insertion rule removed. Tested across many live trips RR52. DEPLOYED (auto-deploy fired earlier). Local main has follow-on fixes below.
BUG-MODIFY-ONEWAY-ROUNDTRIP | Converting a round trip to one-way failed: removing return-home KC tripped the 'cannot delete home departure' guard, leaving trip half-modified | P2 | User test (Benny) | Done | Atomic makeOneWay server action: truncates everything after the turnaround (farthest-from-origin via Haversine). Guard now protects only the FIRST stop (departure), not every HOME. New make_one_way modify action wired through prompt+client. Built+merged local main, not yet runtime-retested on a fresh round trip (do tomorrow).
BUG-TITLE-DRIFT | Trip title mismatched destination (showed 'Portland, MO' / 'Indianapolis' instead of real destination) and didn't update on destination change | P2 | Tester FB-MYE1 + Benny | Done | Title now DERIVED from the turnaround (farthest-from-origin destination), flexible during planning, locked at Build, manual rename after. Fixed the round-trip 'picks return-leg city' bug (was showing Indianapolis; now correctly Bangor). Tested working RR52.
BUG-BUDGET-NONDETERMINISTIC | Budget-conflict refusal fired inconsistently for identical input (same trip built twice, refused once) and named a return-leg city, because it computed from the AI's variable per-run build | P1 | User test (Benny) | Done | Root cause: gate computed from AI's variable itinerary. Fix: minimalTripBudget computes conflict from the MINIMAL trip (origin→turnaround→origin), stable across runs. minNeeded=1+coreTransit (×2 round trip). Refusal now deterministic, names the turnaround (Bangor), states the minimum, offers to bump; 'yes bump it' builds at minNeeded. Tested 3× consistent build (10n) + 3× consistent refuse (3n) + one-way lower min (5). Local main.
BUDGET-REFUSAL-MIN-WOBBLE | Budget refusal fires deterministically but the quoted MINIMUM nights number wobbles across runs (e.g. '5-6' vs '9') because the AI paraphrases instead of stating the exact computed minNeeded | P3 | User test (Benny) | Open | The DECISION (refuse) is deterministic and the system HAS the right number (built at 9 when accepted), but the prose sometimes quotes a wrong lower estimate (5-6) instead of the computed minNeeded. Prompt-tightening: force the refusal to state the EXACT computed minNeeded verbatim, not an AI estimate. Same 'server stamps truth, model reports it' principle. Logged RR52.
FEAT-THREE-OPTION-REFUSAL | [Enhancement] When a trip can't fit requested nights, offer THREE paths not two: (1) add nights, (2) pick closer, (3) NEW: keep the nights & drive longer days (back-solve the required drive cap) | P2 | Benny idea | Open | Benny has 3 drivers, wants the option to keep tight nights by raising the daily drive limit. Recommended approach (Option A): back-solve the drive cap needed to fit requested nights and offer the specific number ('to keep 10 nights I'd stretch your driving to ~8h/day, OK?'). Real (possibly iterative) logic — its own focused build. Build on the now-deterministic minimalTripBudget foundation. Deferred to fresh day. Logged RR52.
UX-TRANSIT-NIGHT-INFLATE | [UX] Requested nights + required transit overnights inflate the displayed total (10 nights shows as 12-15n badge); disclosed in honest notes but the badge contradicts what the user typed | P3 | User test (Benny) | Open | Not a bug (Check C — mild overshoot allowed by design; every added overnight is explained in the honest drive-time notes). UX polish: panel could distinguish 'N nights at destinations + M driving nights = total' so the badge doesn't contradict the typed number. Deferred. Logged RR52.

## Features & Roadmap
RoamReady.ai — Features & Roadmap
Updated RR52. Open/upcoming on top by priority; shipped (green) hidden — reveal via the Status filter.
ID | Feature | Priority | Status | Notes
PLAN-IS-TRUTH-PART2 | Real Google drive-time check DURING planning — transit stops appear in the approved plan + AI explains them honestly | — | Shipped | RR52 COMPLETE. Server measures real Google drive times during planning + is sole transit-stop inserter; AI stopped fabricating compliance; honest grounded notes (planning + modify); every stop-mutation path funnels through recheckLongLegs; keep-long-drive confirm modal; ack on Trip column. Built + merged local main. NOT pushed/deployed.
FR-MARKETING-OPTIN | Marketing opt-in popup after signup | P2 | Queued | Captures explicit marketing consent (none exists today) — legal blocker gating win-back export under CAN-SPAM. Store consent flag+timestamp; wire to marketing email only. After Part 2.
FR-WINBACK | Cancelled-customer export for win-back | P3 | Deferred | Gated on FR-MARKETING-OPTIN (no opt-in basis today).
FR-TIME-INPUT-PICKER | Scrolling time picker (AM/PM) replacing free-text time field | P3 | Deferred | Root-cause cure for the PDF time crash. Standardized input.
FR-RIG-SPEC-AUTOFILL | Pick RV make/model/year → autofill specs | P3 | Deferred | Hybrid recommended: curated common-rig set + per-class defaults + manual override. No clean free RV spec DB exists; build curated, grow over time.
FR-ROUTE-HWYPREF-1 | Rig-aware “prefer major highways / 4-lane” routing preference | P3 | Deferred | Post-launch, low severity.
FR-SCOPE-HUMOR-1 | Scope-guard tone improvement with on-brand deflection | P3 | Deferred | A/B test before shipping.
FR-FEEDBACK-NOTIFY | 5th dev@ alert on feedback submission | P3 | Deferred | Scoped, not built.
JOURNAL-LOCATION | Optional place picker on freeform journal entries (pin stopless entries) | P3 | Deferred | Reuse AddressAutocomplete in AddEntryModal; columns exist from step 7; needs scout.
MOBILE-CHAT-INPUT | Chat input off-screen when keyboard opens (mobile) | P3 | Deferred | Pre-existing (baseline bf89b0a). Fix = visualViewport listener to lift input. Measure-first. Not pushed.
RIG-CHANGE | Full rig-change feature: trip-page selector + larger-rig warning + per-stop “booked for [rig]” + AI modify action | — | Shipped | All routed through one guarded swap path. Migration: 7 bookedForRig* cols. Dev-tested. Pushed, not yet deployed to prod.
STOP-GEO-RESLOT | Geo-reslot modify-added stops + booked-stop date-shift modal + originalBookedDate record | — | Shipped | Server geocode + min-detour reslot; center-screen modal; backfill done. Pushed.
STAY-CARD-TRUE-WINDOW | Itinerary stay card shows true booked window (nights + arrival→checkout); PDF matches | — | Shipped | Display-only (Option 1). Pushed.
NIGHTS-CONVERSION | Align modify days→nights with planning + explicit date-range rule | — | Shipped | Pushed. Fresh-thread test pending.
KEEP-LONG-DRIVE | User opt-in to drive an over-cap leg: confirm modal on overnight delete, ack persists, no nag | — | Shipped | Reused ConfirmModal. 'Remove this overnight stop?' wording, danger button. Ack on Trip.acknowledgedLongLegs (migration applied). Local main, not pushed.

## Launch Status
RoamReady.ai — Launch Status
Snapshot of LAUNCH_STATUS.md (repo root = live source of truth). Updated RR52.
Item | Status | Category | Notes
Site live at roamready.ai | LIVE | Launch | Real Stripe payments, DNS cutover complete, Render deployed.
PDF time-crash fix | DEPLOYED | Prod fix | Live on roamready-client (Cindy’s PDF works).
RR51 batch (rig, stop-sequence, nights, stay-card) | PUSHED, NOT DEPLOYED | Deploy pending | On GitHub. Deploy needs BOTH roamready-api (server) and roamready-client (client). Deliberate step.
Plan-is-Truth Part 1 | PUSHED, NOT DEPLOYED | Deploy pending | Built + merged to local main and pushed to origin. Not deployed to prod. Drive-time net OFF until Part 2.
Plan-is-Truth Part 2 | BUILT, LOCAL ONLY | Push pending | RR52 COMPLETE on local main (server-sole drive-time check, honest notes, keep-long-drive modal, ack Trip column). Migration 20260625120000 APPLIED to dev DB. Not pushed to origin, not deployed. Deploy needs BOTH roamready-api + roamready-client.