## Bug Tracker
RoamReady.ai - Bug Tracker
Updated June 20, 2026 (RR46 scout - all green; repo in sync, migrations clean, preflight green, assets intact). Open items at top by severity; fixed/closed hidden by default - use the Status filter to view. Only Severity is colored. VERIFY items are uncertain carry-overs - confirm on prod and close if resolved.
ID | Item | Severity | Status | Category | Notes | Key commits
BUG-TRIP-NIGHTS | 30-day trip request produced only a 20-night itinerary; AI prose admits 10 nights unplaced; trip saved + labeled as the plan with no flag that it under-delivers requested duration by 1/3. MESA-honesty class: model self-reports a plan the build does not fulfill. | High | Build 1 verified (full 30n) - Build 2 pending (RR47) | Bug | Found RR46 via friend test trip (KC MO -> Vancouver BC round trip, 30 days). AI itinerary stops sum to 20 nights, wrapper totalNights said 30, prose said 20 on road + 10 left. App card shows 20 nights / Ends Jul 21. Highest-trust-damage bug: app appears to ignore explicit 30-day request. Likely shares root cause with BUG-TRIP-MILES (AI self-reports numbers server does not reconcile). Scout issued (combined nights+miles+lake). SCOUT RESULT: confirmed real defect. Root cause: requested duration lives ONLY as chat free-text; NO prompt rule to fill/honor requested length; NO server check that stop-nights sum == request. recomputeStopDates (trips.ts:108-178) sums stops and stamps totalNights=20, silently discarding the 30-day request, endDate Jul 21. DECISION (Benny RR46): BOTH LAYERS - (1) prompt rule: AI distributes nights to fill requested duration weighting destinations, respect maxDriveHours; (2) server-side MESA guard: compare stops-sum vs requested duration, surface gap to user instead of silently saving short. Requested duration may need extraction since it is only free-text. Second narrower scout issued before build. SECOND SCOUT done: NO structured duration exists (free-text only); strongest available signal is AI wrapper totalNights vs sum(stops.nights) at chat parse point controllers/ai.ts ~1247-1262 (only spot holding wrapper+stops together, inherently AI-only scoped, no false-positives on manual trips). Guard detects AI internal inconsistency (stated vs built), not divergence from guaranteed request. Must count OVERNIGHT_ONLY as 1 night to mirror recomputeStopDates (trips.ts:148). No existing client notice channel - modifyOutcome is modify-mode only. SURFACING DECISION (Benny RR46): OPTION B - server-computed durationGap notice field + client banner (server stamps truth, matches MESA convention; NOT model self-report). BUILD SPLIT: Build 1 = prompt rule only (services/ai.ts after DRIVE-TIME ~189) ISSUED RR46; Build 2 = server guard + client notice banner, pending after Build 1 prod test. BUILD 1 BUILT RR46: merged --no-ff 175e35e, not pushed. One rule added services/ai.ts after DRIVE-TIME CONSTRAINT. tsc clean, exactly one line. Prompt-only NUDGE - not enforced (Build 2 makes it deterministic). Deploys to roamready-api (server code: restart backend, no migration). Remaining: push, prod test with the KC->Vancouver 30-day prompt, report nights built + distribution, then Build 2 calibrated to result. BUILD 1 PROD TEST RR46: SUCCESS - same KC->Vancouver 30-day prompt now builds 25 nights (was 20), with quality stops (North Platte, Casper, Bozeman, Cranbrook, Kamloops, Bellingham, Pendleton, Twin Falls) and correct destination nights (Glacier 3, Whistler 3, Vancouver 4, Seattle 3). Prose addressed lake + rig. RESULT = closer but still short (25 of 30) - confirms Build 2 server guard is needed to detect+disclose the shortfall deterministically. Note this was the agreed-stops stage (pre Build full itinerary), ~0 mi expected. UPDATE: after fully agreeing all stops, trip reached full 30 nights (stops 1-18, KC->...->KC). Duration fix confirmed landing at target. Build 2 server guard still wanted as deterministic net for cases where AI lands short.
BUG-TRIP-STOPORDER | AI places a DESTINATION out of geographic route order. KC->Vancouver test: outbound sequence is Kamloops -> Whistler (stop 8) -> Vancouver (stop 9, the stated turnaround). Whistler is ~75mi NORTH of Vancouver up Sea-to-Sky, so routing Whistler BEFORE the Vancouver turnaround makes the path double back (up to Whistler, back down to Vancouver, back up toward Bellingham/Seattle). Zigzag, not a clean out-and-back. | Medium | Logged - scout (RR46) | Bug | Found RR46 on the fixed 30-night KC->Vancouver test trip. User flagged stop 8 (Whistler) as out of order. Whistler sits past Vancouver; with Vancouver as the stated turnaround, Whistler should come AFTER Vancouver (day-trip up) or be folded in without doubling back. POSSIBLY related to BUG-TRIP-MAPPINS (sequencing/coordinate handling). Scout: how does the AI order stops along the route, is there any turnaround/apex logic, and does it know stop geographic positions when sequencing. UNCONFIRMED cause - could be mis-sequence vs defensible apex interpretation; either way does not match request. Scout alongside or after map-pins.
BUG-CHAT-INPUT-CLIP | Desktop: the pulsing Type your answer here chat input box is visually cut off / clipped at its container edge (the pulse glow-ring appears chopped). Seen on the session planning chat screen, desktop browser. | Low | Logged - future fix (RR46) | Bug | Found RR46 on desktop (localhost session chat, same view as the 30-day test trip). The pulsing answer input at bottom of the planning chat is clipped at its container edge - likely the pulse/glow animation ring or box-shadow exceeding overflow-hidden bounds, or insufficient padding around the input. Desktop only per Benny. Low priority cosmetic. Scout the session chat input component + its container overflow/padding when picked up.
BUG-TRIP-MAPPINS | Trip map markers plot at wrong locations. On the KC->Vancouver test trip, several stop pins (6 Vancouver, plus 10/11/12 return-leg stops) cluster around Colorado/Utah instead of their real locations. Stops LIST is correct (Vancouver = stop 6, 4n, correct mileage); only the MAP pin positions are wrong. | Medium | Fixed + verified (RR47) | Bug | Found RR46 (friend test trip, same KC->Vancouver round trip). User flagged pin 6 appearing in Colorado and read it as a Colorado stop. ANALYSIS (Benny + Claude, from screenshot - NOT yet code-scouted): highlighted stop 6 in the list IS Vancouver and is correct; the Colorado-area cluster of pins (6,10,11,12) is the MAP mis-plotting markers, classic symptom of missing/zeroed lat-long falling back to a default center-US coordinate. Likely a map-display/coordinate bug, NOT a routing/itinerary defect - but UNCONFIRMED, must scout to distinguish (a) map-only wrong coords vs (b) a real bad location written into a stop. Probably related to the geocoding/coordinate path feeding TripMapPage markers. Scout AFTER BUG-TRIP-NIGHTS Build 1+2 ship. SCOUT ISSUED RR46: trace pin coordinate source, where coords are set (AI vs server geocode vs client), the fallback/default coordinate (likely culprit), why some stops (Canadian/BC?) fail while others succeed, and whether stop-ordering shares a code path with coordinates (possible shared root cause with BUG-TRIP-STOPORDER). FIXED RR47: root cause confirmed by scout - client geocode query in TripMapPage.tsx (~line 826) hardcoded 'USA' onto every stop, so ambiguous non-US names (Vancouver, BC) resolved to a wrong US match (Vancouver persisted at 38.79,-106.53 = central Colorado) and never self-corrected (geocode effect only runs on null-coord stops). FIX: added CA_PROVINCES set (all 13 prov/terr incl YT/NT for the Alaska-via-BC corridor); isCanadian check on locationState (2-letter codes confirmed in dev DB); query now appends Canada vs USA + geocoder componentRestrictions {country: CA¦US} so Google honors the country. Built via main-checkout-branch workflow (no worktree junction). Corrupted Vancouver row repaired: SELECT confirmed 1 row in Colorado, UPDATE nulled lat/lng (guarded on exact coords), map reload re-geocoded to real BC coords. VERIFIED on dev: Vancouver pin now lands in BC, route mileage corrected (was bloated by the Colorado detour, now 4,373 mi). KNOWN FOLLOW-UP: segment-routing path in trips.ts (~269-274) has the SAME hardcoded-country blind spot in its distance-calc string fallback - logged as new row BUG-TRIP-SEGROUTE-COUNTRY, deferred. | f3c49d4 (code) + 619c93a chain
BUG-TRIP-MILES | Mileage mismatch: AI itinerary JSON totalMiles=4800 but trip card shows 6,554 mi for the same trip. Two different distances shown depending on where user looks. | Medium | Closed - not a bug (RR46) | Bug | Found RR46 same test trip. AI guesses totalMiles (4800); routing engine (Google Directions / fetchAllSegmentRoutes) computes 6,554; card shows 6,554. Suspect AI totalMiles is vestigial/overwritten - cross-ref dead code generateRouteStringsAI. Likely same root cause as BUG-TRIP-NIGHTS. Scout issued (combined). SCOUT RESULT: NOT A BUG. AI totalMiles (4800) is a throwaway placeholder; client TripMapPage recomputes real distance via Google Routes API (6,554) and overwrites/persists it - truth wins by design. Tester just caught the stale AI estimate in chat before the map page recomputed. SessionPage already nulls AI totalMiles in the slicing path (knows it is unreliable). Optional cosmetic polish only (hide the AI placeholder) - not worth touching trip-gen. Closed.
BUG-TRIP-LAKE | User asked campsite be on a lake (esp. Whistler lakeside); itinerary gives no signal the on-a-lake preference was honored or understood. Candidate sets mostly not lakes. | Low | Parked - fix after nights (RR46) | Bug | Found RR46 same test trip. Free-text campground preference (on a lake) appears dropped in candidate selection. Separate root cause from nights/miles (prompt + candidate logic, not trip math). Scout issued (combined). SCOUT RESULT: confirmed separate + actionable. Free-text campground preference (on a lake) never threaded into candidate generation (services/ai.ts:243 rule says nothing about location preference) nor downstream Places search (campgrounds.ts name+city/state only, no water keyword). No guard. Parked as own small follow-up after nights fix.
BUG-PACKING-MOBILE | Packing List mobile: (A) action buttons Export PDF / Save as template / Refresh suggestions overflow right edge, Refresh clipped + unreachable, row does not wrap/scroll. (B) Export PDF dropdown menu spills off LEFT edge, option text cut off and unreadable. | Medium | Fixed (prod) | Bug | Spotted RR46 on mobile (roamready-client.onrender.com). User chose WRAP for the button row (all visible, no horizontal scroll). Dropdown needs repositioning to stay on-screen on narrow viewport. CC scout issued: identify Packing List component, button-row flex/wrap classes, and dropdown positioning. Scout done: both in PackingListPage.tsx. A = header flex justify-between + button row flex gap-2 no wrap. B = Export PDF dropdown absolute right-0 w-60 spills left. Decision: ONE commit both fixes (small, independent, same reported problem). Fix A: header stacks on mobile (flex-col -> sm:flex-row) + button container flex-wrap. Fix B: dropdown right-0 -> left-0 + max-w viewport guard. Save-as-template modal untouched. Needs MOBILE prod eyeball. BUILT RR46: merged --no-ff 1f3f913, not yet pushed. tsc clean, +3/-3 className-only. Purely visual mobile fix - NEEDS phone eyeball before close (not reasoning-acceptable since the whole point is mobile appearance). Remaining: push via save-progress.bat then Benny phone check (button wrap + Export PDF menu fully on-screen). VERIFIED on mobile prod RR46 - Benny confirmed buttons wrap cleanly and Export PDF menu opens fully on-screen. Closed. | fix packing list mobile button wrap and export pdf menu overflow [1f3f913]
BUG-DRIVECAP | Per-trip drive-time limit stated in chat not respected as an override; final summary quotes profile default (6h) when user said 5h in chat. | Low | Open - to fix | Bug | Profile max drive time is the default; a chat-stated limit overrides ONLY its leg/trip (either direction - shorter cap OR a deliberate long haul, which the chat must explicitly call out). Summary must quote the OPERATIVE number, never silently revert to profile default. NIGHTS-PROSE-1 family. | -
BUG-NIGHTS-PROSE | Model free-text narration can misstate the night count vs the (correct) card; also covers the drive-cap summary number. | Low | Open - polish | Bug | Card/badge always truthful; model prose can still drift. Feed derived totals + operative constraints into the model summary. | -
BUG-DEADCODE-ROUTESTRINGS | Dead code: generateRouteStringsAI (server/src/services/ai.ts) defined but never called - Google Directions (fetchAllSegmentRoutes) replaced it. Not imported anywhere. | Low | Open - cleanup | Tech debt | Confirmed dead during the LS-AI-USAGE-CAP cost scout. Safe to delete in a standalone post-launch chore commit; deliberately not bundled into launch work. | -
BUG-RESV-PASTDATE | Reservations tab buckets Upcoming vs Past with raw new Date(stop.arrivalDate) (ReservationsTabContent.tsx:77) while displaying via formatTripDate. UTC-midnight family (like fixed #11/#11b): in a negative-offset zone a stop labeled e.g. "Jul 10" can sort to Past a day early. | Low | Open - to fix | Bug | One-line fix: parseTripDate(stop.arrivalDate) at line 77. Negative-offset, day-of edge. Found by RR43 CAPTURE-AUDIT sweep. ALSO (separate, very low): resolvePackingCounts (packingMeta.ts:31-47) returns 0 adults when party is null, ignoring legacy TravelProfile.adults - legacy account w/ profile but no party could show "Made for 0 adults". self-person backfill makes it rare. | -
BUG-TM-POLYLINE | Map polyline stale on AI add-stop - when the AI adds a stop, the route line on the map may not refresh. Flagged P1 in an earlier session; status unconfirmed - may already be fixed. | High | Fixed - deployed | Bug | Fixed by composite Polyline key (commit 21b3f4c, May 28); also fixed sibling trash-delete stale-line bug. Reactive wiring re-confirmed June 10 audit. Verified working by Benny (RR43). Closed. | -
BUG-PLANNER-FIDELITY | Planner dropped previously-agreed stops on long trips and omitted legs past the headline destination (last-10-message window, no agreed-stops grounding). Confirmed on Cindy prod Mesa->Poulsbo. | High | Fixed - deployed | Bug | Persist agreed stop-set to partialTripData; re-inject as ground-truth every planning turn (survives HISTORY_CAP). Multi-destination directive added. Proven on prod with Austin 24-stop round-trip. | 3da0ac8, 6f84089
BUG-SESSION-INSPECTOR | No way to inspect a customer conversation + built trip without manual prod DB spelunking (Cindy diagnosis took ~1 hr). | High | Fixed - deployed | Bug | Admin-only read-only Session Inspector (/admin/session-inspector). Lookup by trip id or email (case-insensitive). Shows conversation, persisted stops, emitted-vs-built diff, AI usage tokens. Owner-gated; no schema. | 35ca9ec, 661dd9d
BUG-AI-MODIFY | Modify-with-AI claimed x4 applied but only first stop applied (Cindy). | High | Fixed - deployed | Bug | MESA-10 multi-action: server single parse authority, per-action applied state stamped server-side. | 1a3e8b4, 5a9c740
BUG-RT-STRIP | Round-trip return leg silently amputated; AI narrated an unbuilt stop. | High | Fixed - deployed | Bug | Root cause our own stripUnrequestedReturnLeg guard; return legs now persist for natural phrasing. | 79c97f6
BUG-SELF-PERSON | Account holder never counted as an adult; party undercounted. | High | Fixed - deployed | Bug | Self-person lazy auto-creation on default party. | 8e3dafd
BUG-SESS-HOOKS | SessionPage crashed in a loop after composer relayout. | High | Fixed - deployed | Bug | Rules-of-Hooks fix; hook cluster moved above early return. | 8944b56
BUG-FB-HONESTY | Feedback modal showed "Thanks!" even on failure (401). | High | Fixed - deployed | Bug | try/catch status messages, visible error box, strict Zod. | c8df51f
BUG-MIGRATE-EOL | Prisma checksum failures (CRLF rewrite of applied migrations). | High | Fixed - deployed | Bug | .gitattributes eol=lf, autocrlf=false, byte repairs, preflight guard. | 4305e98, 2be0de4
BUG-AI-PACK | Packing AI silently persisted an EMPTY list (truncation broke parse). | High | Fixed - deployed | Bug | max_tokens 8192 + stop_reason detection; 502 on empty, never overwrites. | 3851ca3
BUG-PACK-PERSIST | Packing checkmarks did not persist; regenerate wiped checks. | High | Fixed - deployed | Bug | PUT packing-list, optimistic+debounced save, carry-over by name. | fd58085
BUG-KBD | Mobile keyboard pushed chat input off-screen. | High | Fixed - deployed | Bug | visualViewport listener lifts input above keyboard. Confirmed closed this session. | -
BUG-MOBILE-PLACEHOLDER | Mobile placeholder truncation - chat input placeholder cut off on mobile. (Former launch-blocker.) | High | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-STOP-COUNT | Stop count accuracy - displayed stop count vs actual. (Former launch-blocker.) | High | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ITINERARY-BTN-FOLD | When the itinerary is built, the "View itinerary" button sits below the fold on mobile - user cannot see it without knowing to scroll, so they think nothing happened. | Medium | Fixed - deployed | Bug (mobile) | FIXED (mobile only, desktop untouched). Final approach after iteration: "View itinerary" is now a gold btn-primary button IN the mobile action-bar row next to PDF (wraps with Journal/Packing/Share/PDF) - so it is visible on load regardless of trip-detail height, the robust fix for ANY trip. Mobile map reverted to original 45vh. Earlier attempts (combined pin legend / 34vh shrink / full-width top strip) superseded. Desktop keeps its sidebar CTA unchanged. One CTA per breakpoint, no duplicates. Built + merged local main (c23d246/db14c62); VERIFY on prod after push on a content-heavy trip (Mesa-to-Maine). Confirmed pushed + live on prod (RR45 scout: git in sync with origin). | -
BUG-MAP-PDF | Itinerary PDF map shows only a Start (S) pin on round trips - Finish pin stacked at identical coords, so it reads as one-way on the printed map. | Medium | Fixed - deployed | Bug | Round-trip PDF map now collapses stacked Start/Finish pins into ONE combined marker: a hosted S/F teardrop icon (client/public/sf-pin.png, served from the app - no external dependency) on prod, auto-falling back to an orange "S" pin on localhost where Google cannot fetch the icon. Plus a PDF legend ("Start / Finish (round trip)" + "Stop"), gated on tripLoopsToOrigin so legend and pin always agree. One-way trips unchanged (separate green S/F pins). Aligned last-stop H/F to FINISH-ORIGIN-1 origin rule. Verified working on PROD by Benny (RR43). | -
BUG-PLANNER-CACHE | ~8k planner prompt re-sent uncached every turn - dominant input cost. | Medium | Fixed - deployed | Bug | Anthropic prompt caching on the static prefix; 5 interpolations moved to an uncached suffix. ~half input cost on long trips. | 3da0ac8, 6f84089
BUG-ORIGIN-FREETEXT | Origin in first message ("from mesa") ignored. | Medium | Fixed - deployed | Bug | Origin directive honors an origin already named in the message. | 16ed35a
BUG-SCOPE-META | Scope guard refused an app meta-question. | Medium | Fixed - deployed | Bug | IN-SCOPE carve-out for questions about RoamReady/the conversation. | d18e932
BUG-PDF-GATE | pdfExport PRO rule not enforced on all surfaces. | Medium | Fixed - deployed | Bug | All three PDF surfaces Pro-gated. | 4ad4329
BUG-STALE-SNAPSHOT | Regenerate gave no why/when; packing list silently stale. | Medium | Fixed - deployed | Bug | packingListMeta snapshot + made-for banner. | c315f06, 2260e58
BUG-PACK-SPEED | Packing generation ~60-65s. | Medium | Fixed - deployed | Bug | Prompt size cap ~120 items; single warm call. | 26fc6c2, 39b932d
BUG-FB-ZOD | Strict schema rejected valid minimal feedback. | Medium | Fixed - deployed | Bug | Outer .optional() on preprocessed fields. | a6addbd
BUG-PILL-CTA | Trip-summary pill CTA - booking pill call-to-action wording/behavior. (Former launch-blocker.) | Medium | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ROUNDTRIP-PROMPT | Round-trip vs one-way prompt handling. (Former launch-blocker; related to PLANNER-FIDELITY-1.) | Medium | Fixed - deployed | Bug | Closed in RR42. Confirmed closed by Benny. | -
BUG-ADMIN-HDR-MOBILE | Admin page header + tab row do not wrap or scroll on mobile. The admin header info and the top tabs run off the right edge on a phone; you cannot scroll right to see them - must rotate to landscape to read it all. | Medium | Fixed - deployed | Bug (mobile) | Fixed RR45. Admin landing header packed title + 5 nav buttons into one non-wrapping flex row; on mobile they overflowed and were clipped by the global overflow-x:clip rule, forcing landscape. Mobile-scoped fix (AdminDashboardPage.tsx): outer header flex-col gap-3 sm:flex-row sm:items-center sm:justify-between (stacks title over buttons on mobile, side-by-side at sm+); button group flex-wrap gap-2. Desktop unchanged. No shared class or global CSS touched. | fix(admin): wrap landing-page header tabs on mobile (BUG-ADMIN-HDR-MOBILE) [4edc4ea]
BUG-CAPTURE-AUDIT | Capture-vs-display audit - recurring consistency check between what the app captures (stops, dates, counts) and what it shows. Flagged P1 in an earlier session; status unconfirmed. | Low | Closed - swept | Bug | Systematic capture-vs-display sweep run RR43 (read-only scout, hand-verified). Write and read agree across dates, counts, costs, status flags, field shapes. Two agent over-claims verified false. One straggler split to BUG-RESV-PASTDATE. Umbrella resolved. | -
BUG-INSPECTOR-LABELS | Inspector list had no headers; bare "COMPLETED" (conversation status) read as the trip status. | Low | Fixed - deployed | Bug | Column headers + relabeled "Conversation: ..." pill + legend + separate "Trip: ..." status pill. trip.status added to selects. | b136f7c, ca560ff
BUG-MODIFY-UI | Duplicate-stop guard reported the wrong stop number. | Low | Fixed - deployed | Bug | Numbers against the displayed (non-HOME) list. | bc71580
BUG-SESS-COMPOSER | Chat composer clipped at viewport bottom on mobile. | Low | Fixed - deployed | Bug | Flex layout replaced hardcoded viewport arithmetic. | bd8cc05
BUG-BUILD-DUPE | Build full itinerary twice could double-build. | Low | Fixed - deployed | Bug | Build made idempotent. | a8b4897
BUG-UI-DOT | Purple dots on dashboard journal map questioned. | Low | Closed - by design | Bug | Per-trip marker colors are intentional. | n/a
BUG-CHATPULSE-CLIP | Awaiting-reply input pulse glow was clipped at the bottom by the fixed bottom nav (nav z-40 opaque painted over the lower half of the glow; input sat flush with no bottom padding). | Low | Fixed - deployed | Bug (mobile) | Added pb-3 to the fixed chat-input wrapper (md:pb-0 desktop reset) so the full pulse ring renders in the gap above the nav. Part of the onboarding-cue work (Fixes 4+2 added the awaiting pulse + bottom-anchored layout; this fixed the glow clipping). Built+merged; verify on prod. Confirmed pushed + live on prod (RR45 scout: git in sync with origin). | -
WATCH-CLIENT-BIN-SYMLINKS | client/node_modules/.bin symlinks (tsc etc) missing - likely interrupted npm op | Low | Resolved - permanent fix (RR47) | Infra | Noticed RR46 during FR-VERIFY-SPAM-HINT build: client/node_modules/.bin/tsc symlinks absent (were present earlier same day). CC worked around via node node_modules/typescript/bin/tsc directly. Not blocking. FIX IF IT BITES: if a future CC/npm script fails with cannot find tsc or a .bin entry, run a fresh npm install in client/. No action needed now. ROOT-CAUSED & FIXED RR47: the recurring vite/tsx 'not recognized' (.bin wiped) was caused by Claude Code junctioning client/server node_modules into a git worktree and then recursively deleting that worktree on cleanup - on Windows the delete follows the junction and wipes the REAL node_modules/.bin (packages survive, .bin shims die). Happened ~11x in one session. PERMANENT FIX: (1) workflow change - CC now works in the MAIN checkout on a short-lived branch for source edits (no worktree, no junction); (2) CLAUDE.md created at repo root with a 'node_modules / worktree safety (CRITICAL)' section encoding the rules so they persist across sessions; (3) if vite/tsx is ever 'not recognized' the fix is `npm install` in the affected folder, NEVER a DB rebuild. First feature built under the new workflow (leaving-site popup) confirmed .bin survived. Closing the watch. | n/a
BUG-TRIP-SEGROUTE-COUNTRY | Segment-routing distance calc in trips.ts (~lines 269-274) falls back to 'locationName, locationState' strings with the same hardcoded-country blind spot that BUG-TRIP-MAPPINS had on the map. Cross-border (BC/Canada) stops can compute wrong segment distances when coords are absent and the string fallback is used. | Medium | Logged - deferred (RR47) | Bug | Identified during the BUG-TRIP-MAPPINS scout RR47 as the sibling of the map-pin geocode bug - same root pattern (no concept of country beyond an implicit US assumption). Separate code path from the map pins; fixing the pins did NOT fix this. Lower urgency now that pins are correct (segment calc is coordinate-driven once stops have good coords). Scout when picked up: confirm whether the string fallback is still reachable for stops that have valid coords, and whether it needs the same CA_PROVINCES/country treatment. Close the loop before advertising cross-border (Alaska-via-Canada) routing. | -

## Features & Roadmap
RoamReady.ai - Features, Improvements & Roadmap
Updated June 20, 2026 (RR46 scout - all green; repo in sync, migrations clean, preflight green, assets intact). Open/planned items at top by severity; shipped hidden by default - use the Status filter to view. Only Severity is colored (yellow P2 / blue P3 / green Shipped).
ID | Item | Severity | Status | Category | Notes | Key commits
FR-VERIFY-SPAM-HINT | Post-signup check-your-email screen: add hint to check spam folder and mark Not Spam | Low | Shipped (prod) | Feature | Deliverability context: email setup is healthy (mail-tester 10/10, SPF+DKIM aligned on send.roamready.ai, DMARC p=quarantine already live on roamready.ai). Friend's verification hit spam due to NEW sending-domain reputation (warms up over time), not a config bug. No DNS/code email change needed. This hint rescues signups who land in spam AND trains domain reputation via Not Spam clicks. Client-only copy add on the check-your-email confirmation screen. Scout done: target EmailVerificationGate.tsx (full-page check-your-email takeover, shown when grace expires - exactly where stuck users look). Signup itself routes to /onboarding with no inline check-email screen. Existing spam mention only appears transiently after Resend; build makes it persistent on first view as a muted gray text-xs hint below main message. BUILT RR46: merged --no-ff to local main f68fa1b, not yet pushed. tsc clean, +5/-1, one file. Hint renders unconditionally (no state gate) so reasoned-correct but not browser-verified. NOTE: this screen only shows after grace period expires - hard to trigger on prod; acceptable to treat as verified-by-reasoning given trivial change. UPDATE: pushed and VERIFIED on prod in RR46 (built, merged, pushed via save-progress.bat, confirmed live). Closing - was stale at 'merged local'. | add spam folder hint to email verification screen [f68fa1b local, unpushed]
FR-RIG-YEAR-DROPDOWN | Rig Year fields become year dropdowns (newest first) instead of 1-start number spinners | Low | Shipped (prod) | Feature | Friend feedback: number spinner started at 1, so reaching 2026 by up-arrow was absurd. Fix: convert primary year + both towedYear fields to native <select> dropdowns, options from (current year + 1) down to 1990 descending, Select year placeholder, required guard (form has no resolver). Both RigPage.tsx and EditRigPage.tsx. Drop valueAsNumber, use setValueAs to avoid NaN on blank. Client-only, reuses existing fuelType/vehicleType select pattern. CC scout done; build prompt issued RR46. BUILT RR46: merged --no-ff to local main 8b9b2c0, not yet pushed/eyeballed. tsc clean (exit 0), 6 selects across both files, +34/-6. YEARS = currentYear+1 down to 1990 (2027 top). Edit pre-select reasoned correct (RHF stringifies number onto option) but NOT browser-verified. Remaining: push via save-progress.bat then Benny prod eyeball on Add + Edit forms. VERIFIED on prod RR46 - Benny confirmed dropdowns render and work on Add + Edit forms. | fix rig year dropdown add+edit [8b9b2c0]
FR-DRIVECAP | Drive-cap override + summary number (DRIVECAP-OVERRIDE-1) | Low | Planned - P3 | Feature | See Bug Tracker. Profile default; chat overrides its leg; summary quotes operative number. | -
FR-MAP-PDF | Round-trip PDF map Start/Finish marker (MAP-PDF-STARTFINISH-1) | Low | Planned - P3 | Feature | Combined S/F marker on the PDF map for round trips. See Bug Tracker. | -
FR-NIGHTS-PROSE | Night-count prose mismatch (NIGHTS-PROSE-1) | Low | Planned - P3 | Feature | Feed derived totals into the model summary. | -
FR-FEEDBACK-DEFAULT | Roadmap-page feedback modal default type | Low | Planned - P3 | Feature | Default Type to Feature Request when opened from the roadmap page. | -
FR-DUPE-RETRY | Duplicate-card "Try again" dead end | Low | Planned - P3 | Feature | Deterministic rejections should offer Dismiss, not an impossible retry. | -
FR-PARTY-EMPTYSTATE | Travel Party "Add yourself" empty-state copy | Low | Planned - P3 | Feature | Self-person now auto-appears; empty-state wording slightly redundant. | -
FR-EV-FUEL | EV support + auto-MPG + estimate disclosures (EV-FUEL-1) | Low | Planned - P3 | Feature | EV + charging stations as a route-aware resource (NREL API). Auto-MPG by year/make/model from fueleconomy.gov (EPA). Liability disclosure on any auto MPG/range/cost estimate. | -
FR-DECLINE-EMAIL | Declined-email revisit | Low | Planned - P3 | Feature | Declines silent by design; machinery exists if an automated gentle no is wanted. | -
FR-PDF-ROADS | PDF map route follows real roads (match on-screen map) - optional future polish so the printed route curves along highways instead of straight lines between stops. | Low | Planned - P3 | Feature (polish) | Move from Bug Tracker to roadmap (RR43): NOT a bug - the straight-line PDF route is pre-existing and the map is functionally correct. This is an OPTIONAL future polish to make the PDF route follow real roads like the on-screen map. SCOUT FINDINGS (scenario b): road polyline is fetched client-side via the new Routes API and never persisted, so the server cannot reuse it. Two build options - (1) QUICK: in getTripMapImage make one whole-trip Directions call, emit path=enc:<overview_polyline>, keep straight-line as fallback; +1 Google Directions call per PDF render, within free credit; needs a ~8KB URL-length guard (long multi-stop trips can exceed the Static Maps URL cap and would fall back to straight lines). (2) BETTER (later): persist the encoded polyline at itinerary-generation time so the PDF just reads it - no per-PDF API call, but a bigger change. No schema change for option 1; option 2 needs a polyline field. Medium effort. Not launch-blocking. | -
FR-SAVED-PACKING | Reusable / saved packing lists | Medium | Shipped (dev) | Feature | v1 SHIPPED on dev + code pushed to prod (Render deployed); PROD MIGRATION HELD until cutover (see LS-PROD-MIGRATE-PACKING). v1 = save-as-template (Pro) + copy-from-previous-trip (free, MERGE). AI-seed-from-base deferred to v2. Additive PackingTemplate model; reuses mergePackedState + staleness snapshot unchanged. Tested on dev: 3-option chooser, save/start-from-template (Pro-gated), copy-from-previous (free) all working. Merge semantics = source becomes base, target custom items + checks preserved on top (same as Regenerate contract). NOTE on prod: feature CODE is live but save/start-from-template endpoints will 404 until the prod migration runs; copy-from-previous + generate work (no new table). | 09c00f3, d97e63b
FR-RIG-MISMATCH | Rig-mismatch detection + update prompt (RIG-MISMATCH-1) | Low | Deployed | Shipped | COMPLETE end-to-end (RR42). Detection: AI emits a <rig> tag capturing the user OWN stated rig - context-aware, excludes a friend/hypothetical rig (verified: "my friend has a fifth wheel but we are in our Class C" -> RV_CLASS_C). Banner: dismissable amber notice on the planning page when statedRig != profile rig, links to /profile/rig, states mileage/cost depend on rig. Calcs unchanged (run off profile rig). No false nag. | d37f48d, bed9065
FR-PLANNER-FIDELITY | Planner fidelity (agreed-stops grounding) | Low | Deployed | Shipped | Running agreed-stops list re-injected every planning turn; supports legs past the headline destination + return legs. | 3da0ac8, 6f84089
FR-PLANNER-CACHE | Planner prompt caching | Low | Deployed | Shipped | Static ~8k planner prefix cached; ~half input cost on long trips. | 3da0ac8, 6f84089
FR-SESSION-INSPECTOR | Admin Session Inspector | Low | Deployed | Shipped | Read-only owner-gated lookup of any customer conversation + built trip; emitted-vs-built diff; AI usage tokens. | 35ca9ec, 661dd9d, b136f7c
FR-FEEDBACK-PIPELINE | Feedback pipeline + admin workspace | Low | Deployed | Shipped | Validated submissions, honest error states, lifecycle emails w/ refs, 5 admin filter tabs. | c8df51f, d436834
FR-MESA-MODIFY | MESA-10 multi-action modify | Low | Deployed | Shipped | Server-parsed actions[], per-action Apply cards. | 1a3e8b4, 5a9c740
FR-PACKING-SYSTEM | Packing list system | Low | Deployed | Shipped | Persistence, per-item remove, regenerate carry-over, custom items, staleness banner, current-state PDF, speed cap. | fd58085, 3851ca3
FR-PDF-GATE | PDF Pro gate | Low | Deployed | Shipped | pdfExport enforced on all three PDF surfaces. | 4ad4329
FR-ROUNDTRIP-ORIGIN | Round-trip honesty + origin capture | Low | Deployed | Shipped | Return legs persist; origin captured from first message. | 79c97f6, 16ed35a
FR-SELF-PERSON | Self-person auto-creation | Low | Deployed | Shipped | Account holder counted in the party. | 8e3dafd
FR-RESOURCE-DISTANCE | Resource distance (Near me / Near my stop) | Low | Deployed | Shipped | Distance from GPS or a chosen stop. | cb77f46, 88ea738
FR-COLD-START | Cold-start mitigation (infra) | Low | Deployed | Shipped | roamready-api always-on Standard. | config
FR-ADMIN-USERLIST | Admin user list - all users (free + Pro) as sortable/filterable table with CSV export (ADMIN-USERLIST-1) | Medium | Shipped (prod) | Feature | Shipped RR45. Admin Subscribers page previously listed PRO users only (backend filtered subscriptionTier != FREE). Now shows ALL users. Backend (getSubscribers): removed the where filter. Frontend (AdminSubscribersPage) rebuilt as a spreadsheet-style table: columns Name / Email / Tier (PRO green, FREE muted gray badge) / Joined / Renews (em-dash for free); live search over name+email; tier filter All/Pro/Free; sortable column headers (caret, free sinks to bottom); Download CSV of currently-visible rows (plain JS Blob, roamready-users-YYYY-MM-DD.csv); header Users (N) - X Pro - Y Free. Owner-gated, read-only PII. Works dev + prod (same page, reads pointed DB). | feat(admin): all-users sortable/filterable table with CSV export (FR-ADMIN-USERLIST) [c2ef7fe]
FR-UX-SENIOR-INPUTS-1 | Senior-friendly chat inputs: voice-clear, non-slashed red mic, blue caret, home start-here pulse (iOS-safe rounded glow) | Medium | Shipped (prod) | Feature | Shipped RR45 (prod-verified on iPhone Safari). Four senior-friendly chat-input fixes: (1) voice input clears the box after send (stoppedRef guard in useVoiceInput.ts drops the trailing post-stop SpeechRecognition result that was re-filling the box); (2) recording mic is now a NON-slashed red Mic + red pulse (was lucide MicOff/slashed, which read as off/broken to non-technical users); (3) visible blue caret-[#1F6F8B] on chat textareas (hero+compact); (4) blue-gold start-here pulse added to the home/hero input, gated isAwaiting && !focused && !value.trim(), self-suppressing on focus/type. Pulse done iOS-safe: box-shadow-only glow on the rounded WRAPPER (new .hero-input-awaiting class) so it hugs the rounded box, + isolation:isolate on the mic button. IMPORTANT iOS NOTE: the voice mic is HIDDEN on dev over http:// (LAN IP/localhost) because iOS Safari disables the Web Speech API over insecure http - this is EXPECTED, not a bug. Desktop shows the mic over http; prod (https) shows it on phone. We are NOT using ngrok. Test voice logic on desktop dev; verify phone view on PROD https. Long detour this session: mic appeared to vanish after the first batch -> chased as a code regression (pulse-on-wrapper theory) -> full rollback to c2ef7fe -> root cause was the http/https environment, never the code -> reapplied all four, then fixed the hero glow to hug the rounded box. | feat(ux): senior-input batch [d24debe]; reapply [e7fadb3]; rounded glow [74e9f0f/bd44c91]
FR-RIG-ADD-SCROLL | Add-a-rig button scrolls the revealed form into view + focuses first field | Low | Shipped (prod) | Feature | Shipped RR45. The rig page Add-a-rig button toggled showForm to reveal an inline form but never scrolled to it - on a long page / mobile it looked like nothing happened. Fix (RigPage.tsx): useEffect keyed on showForm -> requestAnimationFrame -> formRef.scrollIntoView({behavior:smooth, block:start}) with scroll-mt-20 to clear the fixed header, then setFocus(vehicleType) so the cursor lands ready (focus delayed ~400ms so it does not cut the smooth scroll; instant + immediate focus under prefers-reduced-motion). Client-only, scoped to RigPage. RR46 scout: push CONFIRMED on origin/main (ae7276f + merge 6c1e70e live on remote); Render client deploy follows. VERIFIED on prod RR46 - Benny confirmed scroll-into-view works. Closed. | fix(rigs): scroll Add a rig form into view [ae7276f / 6c1e70e]
FR-MAP-DESKTOP-LAYOUT | Desktop trip map layout overhaul: taller map, fills available width, and the stops list scrolls in its own bounded window while the map stays in view - no outer page scrollbar. | Medium | Shipped (dev) - verify on prod | Feature | Built RR47 as a series of small desktop-only changes in TripMapPage.tsx (mobile/tablet untouched, full-page scroll preserved): (1) map height raised from 550px; (2) map fills remaining width via flex:1/minWidth:0 instead of fixed 650px (grows up to the max-w-7xl 1280px container, shrinks when sidebar open); (3) stops list bounded with its own overflow-y:auto so it scrolls inside the sidebar while trip info + tabs stay pinned; (4) outer page scrollbar eliminated STRUCTURALLY via flex-fill - page root is a flex column bounded to calc(100dvh - 4rem nav anchor), wrapper+row flex:1/minHeight:0, columns height:100% - so breadcrumb/action-bar/any future strip are absorbed automatically with no hardcoded pixel offset (earlier 5rem/9rem/9.5rem pixel-offset attempts superseded; they kept drifting as strips were missed). All via main-checkout-branch workflow. Verified by Benny at 100% zoom (80% zoom made it look stretched - red herring). NEEDS prod eyeball. | 619c93a restructure desktop map flex-fill
FR-BOOKING-LEAVESITE-POPUP | Confirmation popup before a user leaves RoamReady to book on a campground's external site - names the park, warns they're leaving, and reminds them to come back and record their confirmation number. | Medium | Shipped (dev) - verify on prod | Feature | Built RR47 for the senior/non-technical audience who don't realize an external 'Book' button leaves the app. SCOUT CORRECTION: the stop-list 'Book ->' is INTERNAL navigation to the in-app booking page (TripBookingPage) - the external hop happens only on TripBookingPage's three buttons (primary 'Book at {name}', alt-campground gold button, inline 'Reserve' link), all using cg.reservationUrl + cg.name. Feature retargeted there. Reuses existing components/ui/ConfirmModal (JSX body bolds park name, custom confirm label). Centralized via requestExternalBooking(cg, onProceed?) + one modal driven by pendingBooking state. Modal: title 'Leaving RoamReady', bold park name, reminder to come back and click 'Already booked? Record conf #' (which sits right there on the same page), confirm 'Continue to site ->' opens in new tab, cancel 'Stay here'. INTENDED behavior change: alt-card button now promotes the campground only on CONFIRM (was unconditional on click). Built via main-checkout-branch workflow - first feature under new workflow, confirmed node_modules/.bin survived. tsc clean. VERIFIED on dev by Benny (all three buttons trigger, works perfectly). NEEDS prod eyeball. | d88d479 add leaving-site confirmation popup

## Launch Status
RoamReady.ai - Launch Status
Source of truth: LAUNCH_STATUS.md (repo root). Updated June 20, 2026 (RR46 scout - all green; repo in sync, migrations clean, preflight green, assets intact). Open blockers/gates/security at top by severity; done/deferred hidden by default - use the Status filter to view. Only Severity is colored. VERIFY/OPEN items need Benny to confirm or close.
ID | Item | Severity | Status | Category | Notes | Key commits
LS-BANK-ACCOUNT | Open a business bank account for Martini AI Media LLC. | High | OPEN - blocker | Launch gate / action | In progress - bank asked for a "business license." AZ has NO general business license, so this is loose wording. EIN is DONE (LS-EIN) - have it ready. NEXT ACTION: call the bank and ask the EXACT document needed (stamped Articles of Organization / EIN letter / Operating Agreement / TPT?). Likely set: EIN (have) + Articles + Operating Agreement (multi-member, you + Cindy). TPT only if SaaS taxable in AZ - confirm w/ tax pro. Unblocks Stripe. | -
LS-STRIPE | Stripe live flip - sandbox -> live payments. | High | OPEN - blocker | Launch gate | Sandbox -> live payments. Blocked on the business bank account (LS-BANK-ACCOUNT), which is blocked on EIN (LS-EIN). Launch chain: EIN -> bank account -> Stripe live flip -> DNS. THE true critical path. TPT/SaaS-tax question -> confirm w/ tax pro. | -
LS-DBPW-ROTATE | Prod DB password rotation - the production Postgres password was pasted into chat during RR27 diagnosis and flagged for rotation before launch. Still not rotated. | High | OPEN - security | Launch gate / security | Rotate the Render Postgres password before the Stripe live flip / public launch. Update DATABASE_URL in Render env. Plaintext-in-chat credential = real exposure once live + public. Pair with LS-STRIPE. | -
LS-PROD-TESTPASS | Full feature test pass on the LIVE Render site - plan a real trip on prod, hit the paywall, run a Stripe TEST payment, download a PDF, verify Modify-AI + AI planning in the real prod environment. | High | OPEN - gate | Launch gate / QA | The pre-launch regression check. Catches "worked in dev, broke in prod" before a customer does. Does NOT depend on the bank account - buildable now. Highest-value at-keyboard launch-prep task. | -
LS-DNS | DNS cutover - point roamready.ai at the app (apex A + www CNAME to Render; remove GoDaddy forwarding; protect Google Workspace MX/SPF/DKIM). | Medium | OPEN - gate | Launch gate | Deliberate LAST step, done right before launch. Not blocked externally; kept private behind onrender.com until payments live. | -
LS-S3 | AWS S3 credentials activation (wired, not active). | Medium | OPEN - gate | Launch gate | Needs credentials. | -
LS-PROD-MIGRATE | One-trip dev->prod migration - move a test trip from dev into the live DB to verify the migration path works end to end. | Medium | OPEN - gate | Launch gate | Needs a schema-dependency scout FIRST (Trip->stops->candidates/POIs/bookings/party, insertion order, unique-constraint collisions, non-trip-owned refs like Rig). Uses Render External DB URL. Not started. | -
LS-PROD-MIGRATE-PACKING | Run the add_packing_template migration on PROD (held since RR43). | Medium | OPEN - gate | Launch gate / migration | The PackingTemplate code is LIVE on prod but the migration is intentionally UNAPPLIED (guardrail: held until cutover). Until run, save-as-template / start-from-template 404 on prod (copy-from-previous + generate still work). RUN AT CUTOVER: from project ROOT, backend context, npx prisma migrate deploy (or migrate dev on a connected prod URL per your process) - confirm the preflight phantom tripwire is in place first so the JournalEntry.search phantom cannot apply. Migration file sha256 0b160b7f..., byte-identical to the dev-applied one. Do NOT forget at cutover. | -
LS-IOS-ZOOM | iOS Safari zoom-stuck bug | Low | PARTIAL | Post-launch | Mitigations shipped; exact repro elusive. | -
LS-DEPLOY-WEBHOOK | Render auto-deploy webhook flaky - auto-deploy missed pushes on 06-02. Workaround in use. | Low | OPEN - monitor | Infrastructure | Workaround: if no deploy within ~1 min of a push, use Manual Deploy -> Deploy latest commit. Check GitHub->Render webhook health. Logging so it is not just tribal knowledge. | -
LS-TRAVEL-PARTY-BC | Travel Party Phase B / C | Low | DEFERRED | Post-launch | Per-person accessibility, dormant fields. | -
LS-OHV-DATA | OHV/off-road destinations data source | Low | DEFERRED | Post-launch | Rec.gov/RIDB does not index most USFS/BLM OHV areas. | -
LS-OHV-LINK-CHECKER | OHV link-checker activation | Low | DEFERRED | Post-launch | Built+merged; needs migration + scheduler + smoke test. | -
LS-PRIOR-BLOCKERS | Prior launch-blocking set (PDF lazy-load, updateTrip schema, modify-AI tag-loss, weather live/historical, share trip, reservation honesty, travel party v1, +more) | High | DONE | Launch-blocking | All verified/deployed RR33-39. See Features tab + commit history. | -
LS-AI-USAGE-CAP | Per-user daily AI-call cap + owner alert - hard 200/day auto-cap and 100/day warning email across all 7 AI-spending endpoints. | High | DONE | Launch gate | Tier-agnostic (Pro/trial/owner all bounded). Warn email via feedbackNotification Resend client to support@roamready.ai, once/user/day. Route-cache paths gated post-cache. Client shows friendly "resets in X hours" message (also fixed the free-tier DAILY_LIMIT message). No schema change. Shipped + live June 17, 2026 (RR43). Closes the pre-launch uncapped-cost gap before the Stripe live flip. | -
LS-EIN | Confirm or obtain an EIN (federal tax ID) for Martini AI Media LLC. | Low | DONE | Launch gate / action | EIN obtained for Martini AI Media LLC. Confirmed by Benny. Have it ready to supply when opening the business bank account. | -
LS-COLD-START | Render cold-start mitigation | Low | RESOLVED | Infrastructure | roamready-api Standard always-on. | -
MAINT-FTS-PHANTOM | Permanent fix for the recurring migration drift (JournalEntry.search phantom). | High | DONE - RR43 | Infrastructure / maintenance | ROOT-CAUSED & FIXED this session (the recurring "erase database" drift, 7-8 prior incidents). Cause: Prisma v6 cannot model the GENERATED ALWAYS tsvector column JournalEntry.search, so every migrate dev re-proposes ALTER COLUMN "search" DROP DEFAULT, which Postgres rejects (42601). Was hand-patched each time; slipped through in RR43 and failed. PERMANENT FIX: new scripts/check-migration-phantom.js wired into npm run preflight - mechanically BLOCKS any migration containing that statement from being committed/applied (strips comments so documented precedent passes). Tested both ways. This class of failure can no longer silently recur. | -
MAINT-MIGRATION-REBASELINE | Squash migration history to a clean baseline (post-launch). | Medium | DEFERRED - post-launch | Infrastructure / maintenance | The durable cleanup beyond the RR43 tripwire: collapse the accumulated migration history (tombstones, hand-patched phantoms, checksum scars from 7-8 incidents) into one clean baseline so dev + prod agree from a known-good foundation. Do as its OWN dedicated session AROUND prod cutover, DB BACKUP FIRST, scout full migration state, squash, re-baseline dev then prod. Not urgent; the tripwire (MAINT-FTS-PHANTOM) stops the bleeding in the meantime. Natural to fold into the cutover since you sync dev->prod schema then anyway. | -