## Bug Tracker
RoamReady.ai - Bug Tracker
End of day: Thursday, June 12, 2026 (RR38 session) - all RR38 items deployed to prod
ID | Title / Symptom | Severity | Source | Status | Resolution | Key commits
AI-MODIFY-1 | Modify-with-AI showed '[checkmark] change already applied' x4 but only the first stop was applied to the itinerary (Cindy's Mesa-Niagara trip) | High | Prod user (Cindy) | Fixed - deployed | MESA-10 multi-action architecture: server is the single parse authority (actions[] in envelope), per-action applied state stamped server-side at execution, Apply-all sequential UI, model-emitted 'applied' claims stripped, legacy histories degrade to neutral text. Synthetic success bubbles removed. | 1a3e8b4, 5a9c740
MODIFY-UI-1 | Duplicate-stop guard error reported the wrong stop number (counted HOME departure) | Low | User test (Benny) | Fixed - deployed | Guard now numbers against the displayed (non-HOME) stop list; add-home duplicates say 'as your home stop'. | bc71580
FB-HONESTY-1 | Feedback modal showed 'Thanks for your feedback!' even when the request failed (seen live on prod with a 401) | High | Internal test | Fixed - deployed | try/catch with status-specific messages, visible error box, disabled 'Sending...' state; raw req.body replaced with strict Zod validation (FeedbackSubmitSchema) via validateBody; unvalidated PUT /feedback/:id/status removed in favor of PATCH /admin/feedback/:id. | c8df51f
FB-ZOD-1 | Strict feedback schema rejected valid minimal submissions - title/importance became required (Zod v4 preprocess/optional placement gotcha) | Medium | Internal test | Fixed - deployed | Outer .optional() added to preprocessed fields; 8-case safeParse verification; gotcha saved to project memory. | a6addbd
MIGRATE-EOL-1 | Prisma 'migration modified after applied' checksum failures, three incidents in one day (founder-rate migration); migrate dev offered destructive DB resets | High | Dev infrastructure | Fixed - deployed | Root cause: core.autocrlf=true rewriting applied migration SQL CRLF on checkout; pre-pin worktrees stayed poisoned. Fix: .gitattributes eol=lf pin, repo-local core.autocrlf=false, byte repairs across all trees, DB checksum corrections (zero data loss, no resets). Guards: scripts/check-migration-eol.js, npm run preflight, hard-abort check wired into save-progress.bat. | 4305e98, 2be0de4
AI-PACK-1 | Packing list AI generation silently persisted an EMPTY list (200 + ~0.9 kB) - max_tokens 4096 truncation broke JSON parse, code swallowed it as []. Live on prod; regenerate could silently wipe an existing list. | High | User test (Benny) | Fixed - deployed | max_tokens raised to 8192 with stop_reason detection and loud parse logging; controller 502s on empty/non-array generation and never overwrites the stored list; carry-over extracted to utils/packingMerge.ts with a 10-case regression check (npm run check:packing-merge). | 3851ca3
PACK-PERSIST-1 | Packing list checkmarks did not persist - checked state lived only in React state; regenerate also wiped all checks | High | User report (Benny) | Fixed - deployed | New PUT /trips/:id/packing-list (ownership-checked, strict Zod, 30x100 caps); optimistic toggle + 500ms debounced save with flush-on-unmount and visible failure banner + retry; regenerate carries checked state over by case-insensitive name match; per-item remove (x) for curation. | fd58085
PDF-GATE-1 | pdfExport: ['PRO'] feature-table rule was never enforced - free users could download trip PDFs (client-side render skipped the gate) | Medium (revenue) | CC audit | Fixed - deployed | All three PDF surfaces (trip summary, trip map, packing list) now call the gated exportPdf endpoint first; 403 opens the paywall via the central interceptor; one deletable line per surface if ever ungated. | 4ad4329
UI-GLYPH-1 | TripMapPage stop-row glyphs unintelligible: purple weather badge was a bare count; tent/bed/red-triangle/booking-dot had no labels | Low | User report (Benny) | Fixed - deployed | Badge replaced with a labeled pill (CloudRain + 'N weather alert(s)', brand purple, compact form on narrow widths) with detail tooltip; all four glyphs now have explanatory title tooltips. | 46ea101
UI-PALETTE-1 | Three off-palette purples (TripMapPage text-purple-600, TripPDF #7C3AED, SessionTipCard #8458B4) | Low | CC sweep | Fixed - deployed | All consolidated to the registered brand token purple.DEFAULT #7F77DD; every client purple now derives from one token. | a3444de
PACK-UI-1 | Redundant 'Generate with AI' + 'Generate packing list' buttons; regenerate had no confirm despite replacing the list | Low | User report (Benny) | Fixed - deployed | One action per state: empty state owns the CTA, header shows 'Regenerate with AI' only when a list exists, gated by a ConfirmModal that honestly warns removed items will return. | 3851ca3
UI-DOT-1 | Purple dots on the dashboard journal map questioned as possible bug | Low | User report (Benny) | Closed - by design | Per-trip marker colors on AllTripsMap (active trip = RV Blue, others cycle a deliberate 4-color ramp; gold ring = journal entry). Registered brand accent; no change made. | n/a
RT-STRIP-1 | Round-trip return leg silently amputated; AI narrated a full round trip but only the one-way half persisted (card/badge disagreed with chat). Found via Mesa->NY 'and back' test. | High | Prod behavior (Benny/Cindy) | Fixed - deployed | Root cause was our own stripUnrequestedReturnLeg guard, not the model: it cut the return leg unless one of 7 blessed phrases was present ('and back' was not). Widened phrase detection (client guard + model prompt, kept in sync); strips now show a loud client notice instead of silent surgery; nights/summary derived from persisted stops. Plus AI-PACK-1 treatment on planning call (max_tokens 8192, stop_reason logging, parseItinerary refuses unterminated blocks). | 79c97f6
ORIGIN-FREETEXT-1 | Origin stated in the first message ('from mesa') was ignored; assistant still asked 'Where are you starting this trip from?' | Medium | User test (Benny) | Fixed - deployed | Origin directive amended: if the user message already names a starting point, emit <origin> and proceed; only ask when none stated anywhere. MESA-7 user-typed validation unchanged. | 16ed35a
SCOPE-META-1 | Scope guard refused an app meta-question ('why isnt it showing on the list on the right?') with the off-topic refusal. | Medium | User test (Benny) | Fixed - deployed | IN-SCOPE carve-out extended: questions about RoamReady, the current conversation, the itinerary being built, or what is on screen are always in scope (with honest cannot-see-the-UI framing). Off-topic refusal kept for genuinely unrelated topics. | d18e932
SESS-COMPOSER-1 | Chat message composer clipped at the viewport bottom on /sessions/:id (worse with the email-verification banner present and on mobile Safari). | Low | User test (Benny) | Fixed - deployed | Replaced hardcoded viewport-height arithmetic with a flex column (scroller flex-1 min-h-0, natural input row); re-measures on resize/layout shift. Bug-class history preserved in the line-907 comment (SESS-LAYOUT-2). | bd8cc05
SESS-HOOKS-1 | SessionPage crashed in a loop ('Rendered more hooks than during the previous render') on every /sessions/:id load - introduced by the SESS-COMPOSER-1 fix. | High | Local test (Benny) | Fixed - deployed | Rules-of-Hooks violation: the SESS-LAYOUT-2 hook cluster was placed below an early return. Relocated to the unconditional top hook section; added hydrating to the effect deps so measurement re-fires post-hydration. Lesson: tsc/build cannot catch this - runtime only; hooks on big page components go at the top. | 8944b56
BUILD-DUPE-1 | Clicking 'Build full itinerary' a second time (e.g. via browser back) returned raw 'Request failed with status code 400'; the trip already existed. | Low | User test (Benny) | Fixed - deployed | Build made idempotent: server returns 200 {alreadyBuilt, trip} for an already-promoted session; client short-circuits the stop-creation pipeline and navigates to the existing trip (avoids doubling stops). ConfirmVehiclesModal confirm path now also guarded against double-submit. Genuine failures still surface the red error. | a8b4897
NIGHTS-PROSE-1 | Model's free-text narration can still misstate the night count (e.g. says 'about 17 nights' while the card correctly shows 15). | Low | Observed in RT-STRIP-1 testing | Open - polish | Card/badge are now always truthful (derived from persisted stops); only the model prose can drift. Full fix deferred (claim-stripping on creation prose is invasive NLP). Likely cheap path: feed derived totals back into the model summary so it quotes the real number. | -
ENV-JUNCTION-1 | Overnight worktree-cleanup's 'zero data loss' claim was wrong: junction audit (dir /AL /S) followed through junctions and deleted symlink entries inside main's node_modules (.bin dirs, >=1 package). | Medium | Found next session (RR38) | Fixed - repaired | Repaired in-session via clean npm installs (root/client/server) + prisma generate; tsc/vite/tsx all verified working. Lesson: junction enumeration must not recurse through reparse points; unlink link-only, never recursive. | -
Summary
Total items | 20
Fixed - deployed | 17
Fixed - push pending | 0
Closed - by design | 1
Open - polish | 1
Fixed - repaired | 1
High severity | 7
NOTE: All RR38 items deployed to prod. Open polish item NIGHTS-PROSE-1 (Low) deferred; ENV-JUNCTION-1 repaired - see lessons in the RR39 handoff doc.

## Features Shipped
Features shipped today
Feature | What it does | Status | Key commits
Feedback pipeline (core) | Validated submissions (strict Zod), honest error states, screenshot attachments (up to 3, client downscale, magic-byte + size checks server-side, route-scoped 25mb JSON limit), support notification email, submitter acknowledgment email, private-by-default (isPublic false + migration), admin PATCH endpoint. | Deployed | c8df51f, 5cda816, d436834-era
Feedback lifecycle emails + refs | [FB-XXXX] reference code in subject/body of all three system emails; automatic 'shipped' email on status transition (plain-language copy, BUG vs FEATURE variants, once-ever via shippedNotifiedAt stamp); 'Notified' badge in admin; silent declines by design. | Deployed | 2e2b977, dd5af5a, 0280989
Admin feedback workspace | Five filter tabs (Active default / Shipped / Declined / Archived / All) with count badges; reversible archive (archivedAt) that never touches public roadmap; submitter line with Find in Gmail (ref search) as the sole reply path; mailto removed. | Deployed | d436834, 64771ed, 3500328
MESA-10 multi-action modify | Server-parsed actions[], per-action Apply cards with persisted applied state, Apply-all, deterministic strip of model 'applied' claims, state-aware model-bound history. Closes AI-MODIFY-1. | Deployed | 1a3e8b4, 5a9c740
Packing list system | Persistence (PUT + debounced saves), per-item remove, regenerate carry-over of checks, blank-checklist PDF export (PackingListPDF, TripPDF pattern), one-button-per-state UI with regenerate confirm, empty-generation 502 guard. | Deployed | fd58085, 3851ca3
PDF Pro gate | pdfExport enforced on all three PDF surfaces for the first time; paywall opens cleanly on 403. | Deployed | 4ad4329
Trip card lifecycle dates | 'Started <date> - Edited <relative>' bottom row on dashboard cards; 'Created <date>' on trip detail header. | Deployed | a6c6436
Plain-language customer copy | Shipped email rewritten without dev jargon (fixed/built/available, 'Happy travels' sign-off); public roadmap third column relabeled 'Completed'; Help page blurb aligned. | Deployed | 0280989, 98b791e
Round-trip honesty bundle | Return legs persist for natural phrasing (and back / there and back / return / back to <origin>); silent strips replaced with a loud notice; trip summary/nights derived from persisted stops; AI-PACK-1 guard rails on the planning call. | Deployed | 79c97f6
Origin from first message | Assistant captures the starting point when it is stated in the opening message instead of re-asking. | Deployed | 16ed35a
Scope carve-out for app questions | Questions about RoamReady, the conversation, or the on-screen itinerary are answered instead of refused. | Deployed | d18e932
Idempotent Build | Clicking Build twice / via back button lands on the existing trip rather than a 400; no duplicated stops. | Deployed | a8b4897

## Backlog & Open Items
Backlog and open items
Priority | Item | Notes
3 - Pre-launch | Render cold start mitigation | Prod request observed at 50.88s (service sleeping). Keep-alive ping or always-on tier before launch. Add to LAUNCH_STATUS.md.
3 - Pre-launch | LAUNCH_STATUS.md update | Record: feedback pipeline shipped, FROM_EMAIL display name set ('RoamReady <noreply@send.roamready.ai>'), PDF gate enforced, cold-start item.
4 - Polish | Packing generation progress UI | Generation honestly takes ~10-15s of AI authoring; show 'Building your list - about 15 seconds' instead of a bare spinner.
4 - Polish | Add-your-own packing item | PUT endpoint already supports it; small client addition (e.g. 'Cindy's medication', 'dog ramp').
4 - Polish | Roadmap-page feedback modal default type | Default Type to Feature Request when opened from the roadmap page; one-line tweak.
4 - Polish | Duplicate-card 'Try again' dead end | Deterministic rejections (duplicate stop) could offer Dismiss instead of a retry that can never succeed.
4 - Polish | Admin type filter | Old mixed status+type chips were replaced by status tabs; re-add a type dropdown inside tabs if bug-vs-feature filtering is missed.
5 - Someday | Declined-email revisit | Declines are silent by design today; machinery exists if an automated gentle 'no' is ever wanted.
5 - Someday | Packing PDF 'current progress' variant | Blank checklist is the shipped default; a packed-state printout is a small variant if users ask.
4 - Polish | Night-count prose mismatch (NIGHTS-PROSE-1) | Model narration can misstate nights vs the (correct) card. Feed derived totals into the model summary so it quotes the real number.