## Tracker
ID | Item | Type | Area | Proposed Priority | Status | Verify vs current code? | Source | Notes / What remains
LB-1 | PDF lazy-loading — @react-pdf/renderer code-split out of main bundle | Perf | Build/Bundle | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #1 | react-pdf lands in own chunk, not index. Closed.
LB-2 | updateTrip footgun — schema permitted raw startDate/endDate/totalNights write | Bug | Trips/Schema | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #2 | Fields removed from TripUpdateSchema; .strict() rejects. Closed.
LB-3 | Modify-AI long-conversation tag-loss — model stops emitting <modify> tags | Bug | AI | P0 — Launch blocker | DONE (audit 05-28) | YES — highest stakes, re-verify | LAUNCH_STATUS.md #3 / recap 05-23 | Was flagged biggest launch risk. Fixed commit b3994ff 05-23 (annotate not strip + retry + amber notice). RE-VERIFY against current ai.ts before launch.
LB-4 | Weather Tab live forecast — forecast_days param + .split() date bug | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #4 | Three sub-fixes in weatherFetch.ts/trips.ts. Closed.
LB-5 | Weather per-stop live→historical fallback for late stops | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #5 | LIVE_WINDOW_END_DAYS=15 + per-stop fitness/modeMatch. Closed.
LB-6 | aiConversation silent 400 — dead client write + stale exclusion query | Bug | AI/Trips | P0 — Launch blocker | DONE (audit 05-28) | YES — AI path, re-verify | LAUNCH_STATUS.md #6 | Dead write removed; surprise-trip exclusion rewired to PlanningSession.messages. RE-VERIFY (AI path, user-visible if regressed).
LB-11 | UTC-midnight arrival timezone artifact in server weather path | Bug | Weather | P4 — Post-launch | DONE (audit 05-28) | Yes — re-verify before launch | LAUNCH_STATUS.md #11 | parseTripDate helper added server-side. Verified in 3 timezones. Closed.
TM-1 | Map route polyline does NOT recompute when AI adds a stop | Bug | Trip Map | P1 — High | OPEN | N/A — open | recap 05-27 #1 | Map draws stale route, visibly skips the new stop. Same 'stale-consumer' family. Scout-first: find polyline coord source + recompute trigger + why Modify-AI save path misses it. ~10-30 line fix.
TM-2 | Map popup shows estimated rate, not actual rate after booking | Bug | Trip Map | P2 — Medium | OPEN | N/A — open | recap 05-27 #2 | Popup reads siteRate w/o the actualRate ?? siteRate fallback wired on Booking page (commit bdb4192). ~5-10 lines in StopPopup. Bundle with TM-3.
TM-3 | 'Book campgrounds' button has no hover state | Bug | Trip Map | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-27 #3 | Cosmetic inconsistency. Add hover: variant matching other action buttons. Bundle with TM-2 as one polish commit.
TM-4 | What is 'Start trip' supposed to do? (product question) | Todo/Scout | Trip Map | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #4 | Flips status ACTIVE, unlocks Mark completed, shows dates. May not earn prominent slot. Scout: every trip.status read, ACTIVE-only behaviors, can status auto-detect from dates. Decide fix/retire/expand after.
TM-5 | Weather sub-tab is non-interactive | Bug/Todo | Trip Map / Weather | P2 — Medium | SCOUT needed | N/A — scout | recap 05-27 #5 | Tab lists stops+dates but nothing clickable. Scout: scaffolded-but-unwired vs wired-but-no-affordance vs abandoned. Then finish / add affordance / remove tab.
AUDIT-1 | Systematic 'fields we capture vs fields we display' audit | Todo/Audit | Whole app | P1 — High | OPEN | N/A — open | recap 05-27 cross-cutting | Same stale-consumer bug shape hit 6x in 9 days. Own session. Walk every page, list field consumers, check each reads canonical source not stale/parallel field. Known clusters: siteRate/actualRate, campgroundName/candidates, locationName/lat-lng re-geocode, trip totals vs per-stop sums, AI-written fields user can override w/o recompute.
PW-1 | Two cosmetic dead feature-gates (rigCompatibilityFilter, aiPlannerUnlimited naming) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Wire to a route or delete from both FEATURE_GATES tables. Marginal.
PW-2 | Extract TRIAL_DURATION_MS constant (7-day literal duplicated) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | 7*24*60*60*1000 copy-pasted in 2 places. Drift risk, not a bug.
PW-3 | Two parallel FEATURE_GATES tables hand-synced (server + client) | Todo/Cleanup | Paywall | P3 — Low / cosmetic | OPEN | N/A — open | recap 05-23 follow-ups | Extract a shared module. Drift risk, not a bug.
AI-1 | Meter the AI for free/trial users (usage count + free limit) | Todo/Feature | AI | P4 — Post-launch | OPEN | N/A — open | recap 05-23 / memory | AI currently hard-gated (expired = no AI). Softer metered model is the fallback if hard gate hurts conversion. Best designed against real AIUsageLog data. Deferred.
EV-1 | Email verification | Todo/Feature | Auth | P1 — High | OPEN — confirm | Yes — confirm status & placement | memory / RR22 backlog | Previously flagged 'essential for real customers,' scoped & deferred. CONFIRM whether you still consider this launch-critical — it may belong at P0. Verify current state in code.
IOS-1 | iOS Safari zoom-stuck bug | Bug | Mobile/UI | P1 — High | DONE (06-02) | Verify on phone (fresh bundle) | memory / RR22 backlog + recap 06-02 evening | iOS Safari/Chrome auto-zoomed on input focus (text ballooned, Send pushed off-screen, never reset). Root cause took 3 passes: (1) a global input,textarea,select{font-size:16px} guard already existed in index.css but was DEAD — it sat in @layer components and lost to text-sm. (2) Moved it OUTSIDE @layer on the theory unlayered beats layered — did nothing, because Tailwind v3.4.19 FLATTENS @layer at build time (compiled CSS has zero native @layer), so the guard was just a (0,0,1) type selector losing to text-sm/.input (0,1,0) on plain specificity → stayed 14px → iOS zoomed. (3) FIX (commit b9f0225 -> merged 5dd984c): added !important to the coarse-pointer guard so it beats the utility classes regardless of specificity, still scoped to @media (pointer: coarse) so desktop keeps 14px. PROVEN in compiled bundle: @media (pointer: coarse){input,textarea,select{font-size:16px!important}}. Verified working on device. KEY LEARNING: under Tailwind v3, unlayered CSS does NOT beat utility classes (no native layers emitted); a global rule that must beat a utility needs !important or specificity >=(0,1,0). Also verify the COMPILED bundle, not just source.
OHV-POC | OHV Destinations real data POC (directions / pass / fee) | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Page still has no real functionality beyond resource links (metadata was hardcoded). Recreation.gov scout was in progress. Build real directions/pass/fee once scout evaluated.
OHV-TRIP | OHV add-to-trip | Todo/Feature | OHV | P4 — Post-launch | OPEN | N/A — open | memory / RR21-22 | Let users add an OHV destination into a trip. Deferred feature.
BOOK-WAVE | Full booking modal wave (confirmation #, site #, hookup, rate, gate code, notes, edit/cancel, conflict detection) | Todo/Feature | Booking | P4 — Post-launch | OPEN | N/A — open | memory | Larger booking feature set. Post-launch.
OHV-LAZY | Code-split OhvDestinationsPage with lazy() | Perf | OHV/Bundle | P4 — Post-launch | OPEN (logged #15) | N/A — logged | this session 06-02 / LAUNCH_STATUS #15 | First-app-load only; per-visit load already fixed (GPS maximumAge + coarse OHV cache key). Low priority.
OHV-RETAIN | Client-side OHV result retention for instant return-visits | Perf | OHV | P4 — Post-launch | OPEN (logged #16) | N/A — logged | this session 06-02 / LAUNCH_STATUS #16 | Cache last GPS + last result so back-nav is instant. Nice-to-have, not a bug.
OHV-CHECK | OHV link-checker — ACTIVATION | Todo/Ops | OHV | P4 — Post-launch | OPEN (logged #17) | N/A — logged | this session 06-02 / LAUNCH_STATUS #17 | Three-state checker BUILT+merged (OK/DEAD/REVIEW, WAF allowlist, emails on DEAD/REVIEW). To activate: (1) confirm OhvLinkCheck table migrated; (2) wire monthly cron like trial-end email cron; (3) smoke-test w/ a known 404. First run will email a REVIEW list — expected; tune allowlist.
PROD-1 | One-trip migration (dev DB → prod DB), re-pointed to prod user | Todo/Ops | Database/Deploy | P1 — High | OPEN | N/A — open | recap 06-02 | Move ONE specific trip from local dev to production, re-point to prod user. Schema-dependency scout FIRST (Trip→stops→candidates/POIs/bookings/party, insertion order, unique-constraint collisions, non-trip-owned refs like Rig). Uses Render External DB URL. PowerShell/psql gotchas apply. NOT started.
PROD-2 | Full feature test pass on live Render site | Todo/Test | Whole app | P1 — High | OPEN | N/A — open | recap 06-02 | Plan full trip on live site, hit paywall, run Stripe TEST payment, download PDF, verify Modify-AI (LB-3) and aiConversation (LB-6) in real prod env. First real-environment regression check.
PROD-3 | Point roamready.ai at the client (GoDaddy DNS → Render) | Todo/Ops | Deploy/DNS | P2 — Medium | OPEN | N/A — open | recap 06-02 | Phase 3. Domain owned at GoDaddy. Currently on onrender.com URLs. Update GoDaddy DNS to Render. Will affect CLIENT_URL, GOOGLE_CALLBACK_URL, Google Cloud authorized URIs once cut over.
PROD-4 | Wire AWS S3 (3 credential vars) — unblocks journal photo upload | Todo/Ops | Storage/Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Only AWS_REGION set in prod; 3 S3 credential vars omitted. Journal photo upload fails until wired. Known, non-blocking.
PROD-5 | Stripe live flip | Todo/Ops | Payments/Deploy | P4 — Post-launch | OPEN — deferred | N/A — open | recap 06-02 | Deferred until business bank account exists (LLC already exists). Then: activate Stripe (tax ID+bank+gov ID), recreate 4 founder price IDs in LIVE mode, stand up prod webhook, swap 6 env vars test→live. ~1hr contained session.
PROD-6 | Render auto-deploy webhook flaky — check GitHub webhook health | Bug/Ops | Deploy | P3 — Low | OPEN | N/A — open | recap 06-02 | Auto-deploy missed pushes twice on 06-02. Workaround: Manual Deploy → Deploy latest commit if no deploy within ~1 min. Check GitHub→Render webhook health.
DISC-1 | Schema changes MUST go through migrate dev, NEVER db push | Discipline | Database | P1 — High | ACTIVE RULE | N/A — rule | recap 06-02 | LOAD-BEARING now that prod is live. stayActivities crash + OhvLinkCheck table were both db-push drift (in dev, absent in prod, no migration). Any uncommitted-migration schema change silently breaks prod and surfaces as a Sentry email.
HOME-MODAL | First-trip home-address capture (SaveHomeAddressModal) — opt-in to save trip start as home | Feature | Trips/Profile | P1 — High | DONE (06-02) | Verify in browser | recap 06-02 | SHIPPED client-only (modal + SessionPage wiring). Scout found the full home-address persistence layer already existed (User has all 8 home fields, profile edits them, AI pre-fills from them). Only gap was the opt-in modal at first trip. Fires when !user.homeLocation, saves only on active opt-in, per-trip override never overwrites saved home. Both builds green, merged. NOTE: currently saves city-only — see PROF-2.
PROF-1 | Profile home-address field renders empty despite populated DB data | Bug | Profile/UI | P2 — Medium | DONE (06-02) | Verify cold-load in browser | recap 06-02 | Stale-consumer bug (AUDIT-1 family). The visible address <input> was uncontrolled (defaultValue) + unregistered, so reset(user) hydration only fed the hidden registered fields (saves always worked, box stayed blank). Fix: controlled off watch(homeAddress), keeps input unregistered so Google Autocomplete keeps its ref. 1 file, +10/-1. Both builds green, merged. Confirmed only other defaultValue= hit (MembershipsPage:191) is NOT the same defect.
AI-MESA-1 | AI announces phantom home city for no-home users (Mesa → Roswell) | Bug | AI | P1 — High | DONE (06-02) | Verify w/ fresh no-home session | recap 06-02 | Two-part root cause, fixed across two commits. (1) Prompt had hardcoded real-city examples (Mesa, Austin/TX) in HOME-position; model borrowed them when [CITY] was unfillable. Fix: de-seeded all home-position examples to [HomeCity]/[HomeState] placeholders, preserved JSON structure (LB-3 modify prompt untouched + verified). (2) Deeper cause: userProfile drops undefined home keys via JSON.stringify, so model could not SEE home was empty and defaulted to the confident assert template. Fix: inject explicit noHomeDirective sentence in chatWithAI when !homeCity && !homeLocation (covers all 3 planning callers), + patched services/ai.ts:96 else-ask branch. When home exists, directive is empty string → momann path byte-identical (no regression). Prompt/service-only, no schema. VERIFY: fresh session, no-home user should ASK where starting from, not invent a city.
PROF-2 | SaveHomeAddressModal captures city-only, not a full structured address | Bug | Trips/Profile | P2 — Medium | OPEN — design done, build AM | N/A — open | recap 06-02 + mockup | Modal is a pure confirm dialog (no input); on opt-in SessionPage saves 3 city-level fields (homeLocation="Mesa, AZ", homeCity, homeState) and relies on getMe geocode backfill — which resolves the CITY CENTROID, not the real street address. Thin/half-useless home record. FIX (mockup approved 06-02): embed Google Places Autocomplete inside the modal, pre-seeded with trip start city; GATE "Save as my home address" so it only enables after a real place is SELECTED (populates all 8 fields); change modal contract onDone(bool) -> onDone(bool, address?{8 fields}); SessionPage sends full 8-field object to updateMe (server already accepts it). RECOMMENDED: extract shared client/src/components/ui/AddressAutocomplete.tsx (loader + Autocomplete + onPlaceChanged 8-field parser) — must NOT assume react-hook-form; returns parsed obj via onPlace callback. Ship modal on it first, migrate ProfilePage as follow-up. "Not now" = skip saving, city still used for planning (two clean paths, no muddy city-centroid middle). FIDDLY Google Places integration — do with fresh head (InfoWindow-saga lesson). Bundle near AUDIT-1.
AI-SURPRISE-1 | Surprise-trip rule misfires on named-destination trips (asks scope question) | Bug | AI | P1 — High | DONE (06-02) | Verify both paths in fresh session | recap 06-02 evening + scout | Planner asked a weekend/about-a-week/stay-regional-or-go-farther scope question for "Create me a trip from Fargo to Del Rio" — a fully-specified ~1,500mi cross-country trip. Root cause (scouted): that scripted question is STEP 1 of the Surprise-trip rule in services/ai.ts; model wrongly entered the surprise branch because the rule trigger has a loose model-judged catch-all ("any message indicating they want YOU to select where to go") and nothing hard-stopped it when a destination was already named. Scope question fires as FIRST response with NO distance precondition; the real distance reasoning (DRIVE-TIME CONSTRAINT) lives downstream in the build branch and never ran. FIX (prompt-only, +3/-1, commit 90be198 -> merged 6761fe6): prepended a PRECEDENCE guard to the top of the Surprise-trip rule — applies ONLY when no destination named; any "from X to Y"/"trip to Y"/"going to Y" pattern hard-disqualifies the surprise branch, routes straight to NAMED DESTINATION RULE. Catch-all trigger left intact so genuine "surprise me / you pick" still asks STEP 1. No server logic/schema/controller change. Server tsc green. VERIFY (restart backend + fresh browser session): (1) Fargo->Del Rio plans directly, NO scope question; (2) "surprise trip, you pick where" STILL asks the scope question (real surprise flow not broken).
MOBILE-CHAT-OVERFLOW | Chat bubbles could overflow horizontally on mobile (long tokens / no break-words) | Bug | Mobile/UI | P3 — Low | DONE (06-02) | Verify on phone | recap 06-02 evening (found while chasing IOS-1) | Found while debugging the IOS-1 zoom (initially mis-read as a horizontal page-shift). The in-session message bubble <p> (SessionPage.tsx) had whitespace-pre-wrap but no break-words, so a long unbreakable token (URL/long word) could overflow its max-w-[80%] box; overflow leaked through the message list (overflow-y-auto -> overflow-x:visible) into the overflow-hidden chat column. FIX (commit a92f1f9 -> merged 48e18b3, +2/-2): added break-words to the bubble <p> (source fix, wraps long tokens) + min-w-0 to the message-list flex container (guard, can never establish min-content wider than column). Avoided a blunt overflow-x:hidden (would clip tokens mid-word). NOTE: this was correct hygiene but NOT the cause of the reported zoom — that was IOS-1 (font-size). Client tsc && vite build green.

## Legend & How to use
RoamReady — Bug & Todo Tracker
Built | 2026-06-02 from LAUNCH_STATUS.md (audit basis 2026-05-28), session recaps 05-23 & 05-27, and this session's OHV work. ¦ Updated 2026-06-02: appended PROD-1..6 + DISC-1 from the production-deployment (Render) session. ¦ Updated 2026-06-02 evening: appended HOME-MODAL, PROF-1, AI-MESA-1 (all DONE, verify in browser) + PROF-2 (design done, build AM).
IMPORTANT — staleness | DONE items come from the 2026-05-28 audit, not a live re-check. Anything with 'Verify vs current code?' = YES should be re-verified against current main before you trust it for launch. This is the stale-April-audit lesson.
Priorities are PROPOSALS | Each priority is Claude's suggestion with rationale in Notes. You own the launch calls — the Priority and Status columns are dropdowns; override freely, then re-sort/filter.
Priority key
P0 — Launch blocker | Must fix before launch. Currently only AI-path items, all marked DONE — re-verify.
P1 — High | Strongly want before launch or right after; real user-facing damage.
P2 — Medium | Should fix; not catastrophic at launch.
P3 — Low / cosmetic | Polish / cleanup; safe to defer.
P4 — Post-launch | Explicitly deferred; logged for later.
Status colors | Green = DONE/VERIFIED · Red = OPEN · Amber = SCOUT needed
Gap to close | This sheet is built from docs + memory, NOT a live repo read. For a fully authoritative version, run a CC scout that dumps all 3 LAUNCH_STATUS.md tables + greps the code for TODO/FIXME, and reconcile against this sheet.